# ADDENDUM C TO THE PRESENTATION ON THE COMPREHENSIVE RURAL DEVELOPMENT PROGRAMME: INSTITUTIONAL ARRANGEMENTS

# Progress Implementation Report: Muyexe

| TASKS | ACTIVITIES | COMMUNITY NEED ADDRESSED | RESP. INSTIT. | BUDGET | COMPLETION TARGET DATE | PROGRESS (General) | SOCIAL IMPACT (Jobs created etc) |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Budget Committed | Expenditure to Date + % |  |  |  |
| AGRARIAN TRANSFORMATION |
| Preliminary Survey | Collection of data on agricultural activities status | Planning Agric development | Local District Authority (LDA) | No budget required |  | Ongoing | Data collected, analysis is underway (80% complete) |  |
| Soil Suitability Analysis | Identification of soil types at potential areas of development Soil sampling | Food Security | LDA | No budget required |  | Done | Soil analysis results available |  |
| Arable Lands | Fencing of 16 km (9 Strand) | Fencing for agric development | LDA | R 1 133 931.69 |  | February 2010 | Submitted quotation to DRDLR for funding |  |
| Grazing Lands | Repairing of 12 km fence (6 Strand) Buffer Zone Fence (17 km ( 9 strand fence) Sitting, drilling and testing of borehole | Fencing for agric development | LDA | R 612 992.64 R 1 197 820.24 R 82 000.00 |  | February 2010 March 2010 December 2009 | Submitted quotation to DRDLR for funding Refining initial plan to suit community additional requirements |  |
| Eradication of Animal Disease | Control of foot and mouth disease | Animal Diseases | LDA |  |  | Ongoing | Ongoing control of animal foot and mouth disease |  |
| Provision of Agricultural Support | Supply of 6 X 500 g spinach, 2X500g cabbage, 1X 50kg 2:3:2(22) fertilizers,1X50kg KAN fertilizers | Food Security | LDA | R 5 000.00 |  | Done | Delivered o Muyexe primary school |  |
| Establishment of Household gardens | Evaluated 500 households for agricultural backyard gardens | Feasibility for agric development | LDA | Personnel expenditure and travelling |  | October | 300 household evaluated |  |
| Revitilisation of Macena Garden | Fencing of 1.6 km Testing of the borehole Installation of a Pump & Construction of concrete pumphouse Electrification of pumphouse & Garden Irrigation System Installation Construction of Packhouse Construction Ablution blocks Purchase of a Tractor Purchase of Disc Plough Purchase of Trailer Purchase of Rotivator Purchase of Boom Spray Purchase of disc harrow | Food Security | LDA | R 266 22.25 R 44 000.00 R 336 18.01 R 150 000 R 1533 330.44 R 391 000 R 170 000 R 476 520 R 27 800 R 65 000 R 82 000 Awaiting quotation Awaiting quotation |  | October August October November September October October August August August August August (07/08/2009) August (07/08/2009) | Submitted quotation to Department of Rural Development and Land Reform (DRDLR) for funding Department of Water & Environmental Affairs ready to do the test ( borehole H14-0454) Submitted quotation to DRDLR for funding for all Requisition of quotation Requisition of quotation |  |
| Revitalization of Manganyi garden | Fencing of 6 ha garden Jojo tank with Stand 07 LDPE Pipe Class (25mm X 100mm) | Food security | LDA | R 160 215.83 R 40 185.00 R 2 886.66 |  | November November September | Funding available at DRDLR. LDA to submit quotations |  |
| Fencing of household Gardens | Fencing 0f the first 300 homes at the rate of one erf (1000 sqm) a day | Food security |  | R4 607034 |  | 30 Nov 2009 | Fencing completed 7th Aug 09 on 10 households visited during Ministerial visit. |  |
| 2. RURAL DEVELOPMENT |
| Water Supply | Assessment of ground water availability at Muyexe and surrounding villages. | Water | DWEA | ( Done internally) |  | Complete | Information on ground water availability done in 36 boreholes within the villages around Muyexe, 11 of the 36 boreholes are at Muyexe Village |  |
| Water Quality | Assessment of Water quality | Water | DWEA | (Done internally) |  | Complete | 39 Boreholes tested and analysed for chemical & bacteriological analyses, and the water may have chronic effect due to high Nitrate content. |  |
| Water for schools | Survey for Water supply | Water | DWEA | (Done internally) |  | Completed | The Water supply survey completed and enough water is available at the schools |  |
| Delivery of basic services (water) | Testing of 19 boreholes Installation of PRV (Pressure Reducing Valve on the Bulk supply pipeline next to Mahlava) Linking of Mahlava old supply system and new in order to regulate usage. Investigation of the current water reticulation system for upgrading. Equipping of borehole (next to dipping tank) with a hand pump. Installation of water storage tanks for tinkering purposes | Water | Mopani District Municipality | R5 000 000 R20 000 R15 000 | 0% 100% | 21/08/2009 21/08/2009 19/08/2009 14/08/2009 14/08/2009 31/07/2009 | 10% 0% 0% 50% 0% Installation of water tanks has been completed |  |
|  | Erection 0f jojo tanks for water harvesting during rainy season at 17 households and ECD center | Water | Greater Giyani Local Municipality in partnership with Independent Dev.Trust | R594,000 | R100,000 | Sept 2009 | Contractor on site | 18 |
| Upgrading of Roads | Repair existing fence along the road Install road signs Maintain & upgrade drainage structures Spot re-gravelling on the eroded structures | Roads | Dept. of Roads and Transport | R1 900 000 |  | 4 months from the date the contractor is on site | Inspection of road D3799 that runs through Muyexe conducted |  |
| 350 Housing Units | Beneficiary Administration and social facilitation EIA Geo – technical report Consumer Education Construction of Houses | Housing | Dept. Local Govt & Housing | R300,500 R 490,000 R 332,500 R20, 000 R 19 100,000 | Nil Nil Nil Nil Nil | 30 Oct 2009 30 Oct 2009 30 Oct 2009 March 2010 March 2011 | Beneficiary list available |  |
| Schools Sanitation | Sanitation (ablution blocks) to 2 schools | Sanitation | DWEA | R 1,600,000 | To pay on completion. | 12/08/2009 | All Blocks construction works are at its advanced stage of completion and planned to be complete by 07/08/2009. Roofing on 3 blocks at the high school has started. | 25 local jobs created (14 male, 11 Female) 10 permanent jobs created (2 Male & 8 Female) |
| Health & Hygiene awareness | H&H at schools and House Hold level | Sanitation | DWEA / Dept. of Housing/ Community Devt. Workers | Done internally |  | 14th Aug 2009 | Health & Hygiene conducted at the 2 schools and 500 households visited at Muyexe. |  |
| Establish client orientated clinic | Full time professional nurse to operate at the visiting point eight hourly and five days per week | Clinic | Depart. of Health and Social Devt. |  |  | 16th July 2009 | Nurse is onsite |  |
| Establish Mass Participation Hub | Mobilise community into various sporting codes: football, netball, basketball, handball, volleyball and dibeke Appoint hub co-ordinator and four activity co-ordinators | Recreation | Dept. Sport & Arts & Culture (DSAC) | 0 R 8400 per month | 0 | End of September 2009 Stipends to start end of September 2009 | The site for playing football identified and graded. Volunteers and target group of participants have been identified. Posts to be advertised. |  |
| Mass Participation in Schools | Organise learners of the two schools in Muyexe into participating in the School Sport Mass Participation Programme Hand-over of apparel and kit to schools | Recreation | DSAC | R 1500 | R 1500 | Ongoing Done | Inter-school games organized for August Courtesy of Transnet Foundation the Premier of Limpopo handed over the kits |  |
| Recreation: Sport for the elderly | Identify participants Handing over of apparel & kit | Recreation | DSAC | R 50 000 R100 000 | R 0.00 R0.00 | 7th August 2009 Before 17th August 2009 to allow for participation on President’s visit | Liaison with community volunteers done Quotations being sought. |  |
| Club Development | Sporting codes to be identified and training provided for coaches and participants | Recreation | DSAC | R 300 000 | R 0.00 | Ongoing | Volleyball identified for Muyexe. Two people to undergo capacity training for coaching and refereeing on 14 – 16 September 2009. |  |
| Identify cultural groups and artists within Muyexe | Identify groups and individuals and list in the DSAC data base. Training & capacity building. | Recreation | DSAC | R 0.00 | R 0.00 | Ongoing | Ongoing |  |
| Establishment of integrated sports centre |  | Sports centre | GGM | R4,4m |  | March 2010 | Site identified and tenders will be advertised soon |  |
| Early Childhood Development Centre (ECD) | Provide and erect a Jungle Gym Build one additional Creche | ECD | Department of Education: ECD Dept Health and Soc. Dev. | R1 500 000 |  | End Aug 2009 | Chief has identified a site for the erection of the crèche |  |
| Establishment of Thusong service centre | Construction of Thusong service centre |  | GGM in partnership with IDT | R10 mil | 500,000 | Sept. 2009 | Contractor on site | 08 |
| Satellite police Station | Conduct feasibility study Establish sector policing Establish Contact Point Provision/erection of a satellite police station Launch neighbourhood watch and safer schools projects Conduct crime awareness campaign Provision of Gr-12 training |  | SAPS |  |  | 31july2009 31 July2009 31July2009 August 2010 August 2009 11August 2009 | - Feasibility study has been conducted. - Sector Manager appointed and introduced to the local structure , sector policing is in place - Site secured for contact point/Satellite police station - Safer schools will be rolled out to schools in the vicinity and the schools are identified. - Door-to –door policing campaign was conducted on 18July2009 and the other crime awareness campaign is scheduled for 11 August 2009. |  |
| Business Development | Business profiling Business registration Business plan development Facilitation of access to finance Business linkage and access to market Business mentoring |  | LIBSA | R20 000 R30 000 R20 000 R20 000 R25 000 R15 000 | 40% 30% 10% 10% 0% 0% | 24 July 2009 End Aug 2009 End Sept 2009 End Sept 2009 End Nov 2009 End Dec 2009 | 5 businesses profiled 2 enterprises registered as cooperatives; (Pfunanani brick manufacturing and Macena garden) Business plan for Pfunanani brick manufacturing and Mhaka trading have been developed Pfunanani brick manufacturing assisted with grant funding of R300 000 from DTI. R240 000 approved by DTI |  |
| Skills Development Programme | Training of 6 Projects at Muyexe Community | Skills and Youth Development | Depart. of Labour | R 530 423 |  | April 2010 | Finalizing the skills audit of the beneficiaries |  |
|  | Provision of Gr-12 training |  | SAPS |  |  |  | - 20 slots guaranteed by Manyeleti Youth Academy for Muyexe - HOD for Safety, Security and Liaison negotiating more slots - Training to commence end of August 2009 |  |
|  | Recruitment of the youth to join SANDF and Reserves Military Skills Development System (MSDS) selection |  | SANDF |  |  | 31 January 2010 | - 11 Candidates invited for the interviews. - 8 candidates passed the psychometric test and completed the medical tests, waiting for feedback from the National Office |  |
| 3. LAND REFORM |
| Fast tracking outstanding land claims | Finalizing claimant verification Finalising the restitution option in consultation with SANParks and DWEA Settlement Post settlement |  | DRDLR (RLCC) | The budget will be advised by the finalization of restitution option |  | End Sept 2009 End Sept 2009 End Mar 2010 End Mar 2011 | The claim researched Gazetted Stakeholders meeting Survey and Mapping done Options workshop conducted |  |
| Provision of security of tenure | Consultation with the community Surveying Vesting of the property Implementation of Communal Land Rights Act (CLARA) |  | DRDLR (PLRO) | In house |  | Oct 2009 Nov 2009 Upon implementation of CLARA |  |  |
| 4.OTHER COMMUNITY INTERVENTIONS – ATTACH DETAILS OF BENEFICIARIES |
| Provision and administration of social grants | Application intake Capturing and approval Payment of grants monitoring |  | SASSA | Old Age=R1010-00 Disability Grant=R1010-00 War Veteran=R1030 Foster Child grant=R680-00 Care Dependency=R1010-00 Child Support =R240-00 Grant-in –aid=R240-00 Social Relief of Distress |  | Ongoing | 3 Old age applications 7 Child Support grant applications SASSA participated on the 67min project intended to celebrate Madiba’s birthday on the 16th of July 2009 Participated on the SAPS crime awareness campaign on the 18th of July 2009 Workshop on qualifying criteria was conducted to task team for social services on the 21st of July 2009 306 beneficiaries were paid on the 22nd of July 2009 Mobile services rendered on the 24th of July 2009 during Cabinet visit |  |
| Provision of ID documents and Birth Certificates | To identify all persons without IDs and birth certificates |  | HOME AFFAIRS |  |  |  | Received 74 applications for IDs and busy processing |  |