## CD POLICY AND PLANNING
OPERATIONAL PLAN 2010/11
PROGRAMME 2 : WOMEN EMPOWERMENT AND GENDER EQUALITY
Chief Directorate: Planning and Policy Implementation on the promotion of WEGE
Measurable Objective | Activity | Indicator | Target Date | Budget
To revise the national policy framework for WEGE in line with new institutional arrangements | Convene three Consultative Meetings | Report on consultative meetings ( Stakeholder contributions, identify key focus areas for policy review | 2010-09-01 | 80000
| Draft Revised Policy | Final Draft Policy | 2010-09-01 | 200000
| Develop implementation guidelines | Guidelines developed | 2010-09-01 | 50000
| Undertake Cabinet Proceccess for approval | Cabinet approved revised policy | 2010-12-01 | 10000
Implementation of review findings and recommendations on the following legislations: Domestic Violence, Sexual Offences and Related Matters Act | 1)Develop Plan of Action for implementing recommendations for each legislation 2)Convene Consultations | Report on impementation of POA in relation to each piece of legislation 2) Report outcomes of consultative meetings | 2011-03-01 | 60000
Consultations on Bills in Parliament that affect women | 1) Convene Consultation with NGM on the following Bills:Prevention and combating of trafficking in Persons, Draft Prostitution,Traditional Courts, Muslim Marriages | 1)Analysis report on each Bill to input on the parliamentary process | 2010-10-01 | 100000
Gender Equality Bill including 50/50 parity | 1)Convene consultations 2) Establish drafting Task Team with SALRC | 1) Report consultations 2) Working Draft equality bill | 2011-03-01 | 100000
To coordinate implementation of 365 Days Action Plan and 16 Day Activism Campaign | Partnership meeting with NPA as implementing lead department on 365 days | MOU developed | 2010-05-01 | 0
| Consultation meetings | Report on consultation meetings | 2010-06-01 | 50000
| Coordinate and plan for implementation of 365 days action plan | 1)Implementation Plan developed 2) Indicators and scorecard developed 3) Two quartely progress reports and comprehensive campaign report | 2010-03-01 | 0
| Develop concept document on 16 days campaign | Concept document approved | 2010-05-01 | 0
| Coordination of meetings of National Coordination committee | Report on consultations meetings ( 4 monthly meetings and weekely meetings in August and September | 2010-11-01 | 50000
| Media launch | 1)Communication strategy developed 2) Draft Programme | 2010-09-01 | 30000
| Opening Ceremony | Project plan implemented | 2010-11-01 | 100000
| Closing Ceremony | Project plan implemented | 2010-11-01 | 100000
| Develop and coordinate plan for implementation of recommendations of impact assesment of 16 days activism campaign | implementation report | 2011-03-01 | 0
To coordinate planning and implementation with GPF's and provincial coordinators | Planning meetings with GFP's at national and provincial levels | 1) Four meetings per quarter, reports developed 2) quarterly annual assesment report developed | 2011-03-01 | 70000
To coordinate planning and implementation with the NGM | Develop NGM Plan of Action | 1) Two strategic planning session 2) Annual Plan of Action developed and implementation report developed | 2011-03-01 | 50000
To raise awareness on WEGE issues through a public-wide advocacy process | Commemorate National Women's Day with a focus on maternal mortality | Project plan implemented | 2010-08-01 | 300000
| Commemorate international women's day | Project plan implemented | 2011-03-01 | 30000
TOTAL |  |  |  | 1380000

## CD MAINSTREAMING AND CAPACITY
OPERATIONAL PLAN 2010/11
PROGRAMME 2 : WOMEN EMPOWERMENT AND GENDER EQUALITY
Chief Directorate: Mainstreaming and Capacity Development on the promotion of WEGE
Measurable Objective | Activity | Indicator | Target Date | Budget
Facilitate Mainstreaming of WEGE equity measures into national priorities with specific focus on work of lead departments | Develop a three year strategic framework and implementation plan for mainstreaming equity measures for each governmnet cluster/lead department | 1) Report of meetings with individual departments, target of 37 departments and 9 provinces) 2) Three year strategic plan developed 3)target and indicators developed an agreed with lead departments 4) Quartely reports compiled | 2012-03-01 | 800000
Facilitate mainstreaming of WEGE considerations into identified targeted projects of governmnet with a special focus on economic empowerment of womenL using empowermnet funds, women owned cooperatives and stokvels savings projects undertaken by lead departments | Compile a comprehensive directory of all empowerment funds available to women in both governmnet and private sector | 1) Research report on available empowermnet funds 2) Directory of services available printed 3) analysis on existing gaps compiled | 2011-02-01 | 800000
facilitate the increase in representation of women in political and decision making levels and in decent employment | 1)Collaborate with DPSA to accelerate 50/50 parity in sms positions 2)Foster the implementation by governmnet of the 8 HOD's principle plan on WEGE and Women Manager's Week 3) report quarterly on progress | 1) MOU with DPSA 2) Quartely reports | 2011-03-01 | 250000
| Facilitate employment equity targets and 50/50 parity at trade union level | 1) Consultation meetings with Trade Union Federations (x3) and trade unions (10) held 2) Annual progress report compiled | 2011-03-01 | 200000
| Initiate an intersectoral collaborative campaign on 50/50 parity in private sector | 1)Consultation meetings with private sector organsiations (x3) 2) Annual progress report compiled | 2011-02-01 | 250000
TOTAL |  |  |  | 2300000

## CD M&E
OPERATIONAL PLAN 2010/11
PROGRAMME 2 : WOMEN EMPOWERMENT AND GENDER EQUALITY
Chief Directorate: Monitoring and Evaluation,Research and Development on the promotion of WEGE
Measurable Objective | Activity | Indicator | Target Date | Budget
Establishment and implementation of WEGE perfomance tracking, verification and perfomance evaluation including comprehensive reporting systems | Develop M&E system with the production of sex and disaregated data using gender-responsive indicators to inform planning | 1)M&E tracking system 2) Gender responsive indicators and scorecard 3) quarterly reports from each department compiled 4) prelimenary database established 5) Annual oversight report on progress | 2011-03-01 | 400000
| Undertake periodic national gender audit | One audit report( gap identification and recomendatons) | Feburay 2011 | 400000
Compliance with sub-regional, continental and international obligations | Ratification of SADC protocol on Gender and Development | 1)Protocol submitted to national parliament for ratification 2) Domestication through national policy | 2011-05-01 | 40000
| Presentation to CEDAW committee | 1)Task team established 2) Consultation meetings convened 3) Responses to committee's questions prepared an submitted 4) national delegation established | 2010-12-01 | 200000
| Commonwealth Mid-Term review Report on POA for WEGE (2010) 9WAMM preparations | 1)Response to questionnaire 2) Macroeconomic paper drafted 3) National delegation to 9WAMM established | 2010-05-01 | 120000
| Development of AU report | 1) Draft report developed 2) cabinet approved report 3) Report submitted to AU | 2010-06-01 | 10000
| UNCSW report back | 1)Report drafted 2) Report back meeting convened 3) Plan of action for implementation of recommendations developed | 2010-05-01 | 75000
| UNCSW 55th Session preprations | 1) Consultation meeting convened 2) Country position paper developed 3) National delegation established 4) National delegation participation report developed | 2011-03-01 | 200000
TOTAL |  |  |  | 1445000
ANNUAL BRANCH TOTAL |  |  |  | 5125000
Note: Total allocation for the Branch minus compensation is: 5, 142,000.00