NATIONAL DEPARTMENT OF PUBLIC

WORKS

SERVICE DELIVERY STANDARDS

TABLE OF CONTENTS

|  |  | PAGE |
| --- | --- | --- |
| 1. | Glossary of terms | 3 |
| 2. | Introduction | 4 |
| 3. | Service Delivery Standards | 5 |
| 4. | User Planning for Immovable Assets | 7 |
| 5. | Custodian Planning or Immovable Assets | 8 |
| 6. | Submission of approved needs assessments and budget | 9 |
| 7. | Leasing – new | 10 |
| 8. | Managing of leasing contracts expiring | 11 |
| 9. | Execution of Implementation Programmes | 12 |
| 10. | Day to day maintenance | 17 |

1.	GLOSSARY OF TERMS:

In this Service Delivery Standards, unless the context otherwise indicates –

“AIM” means the Asset Investment Management branch within NDPW;

“C-AMP” means the Custodian Asset Management Plan;

“CB” means the Customer Billing unit within NDPW;

“CWIP” means Capital Works Implementation Programme;

“CIDB” means Contractor Industry Development Board;

“GIAMA” means the Government Immovable Asset Management Act, 2007 (Act No. 19 of 2007);

“HO” means Head Office;

“KAM” means the Key Account Management unit within NDPW;

“LIP” means Leasing Implementation Programme;

“MTEC” means Medium Term Expenditure Committee;

“NDPW” means the National Department of Public Works;

“PA” means the Portfolio Analysis unit within NDPW;

“PDIR” means Pre-design Information Request;

“PI” means Procurement Instruction;

“PM” means Property Management;

“PMBC” means Planned Maintenance Budget Committee;

“PMIP” means Planned Maintenance Implementation Plan;

“PPM” means the Portfolio Performance and Monitoring unit within NDPW;

“PS” means Professional Services;

“RO” means Regional Office;

“TP’ means the Town Planning unit within NDPW;

“TMC” means Top Management Committee;

“U-AMP” means the User Asset Management Plan;

2.	INTRODUCTION:

The Department provides land and accommodation to national government departments and institutions, manages such land and accommodation, is the custodian of national immovable assets, provides strategic leadership to the Construction and Property Industries, and coordinates the implementation of the Expanded Public Works Programme.

GOVERNMENT-WIDE IMMOVABLE ASSET MANAGEMENT ACT (GIAMA):

The management of public immovable assets is fragmented and their utilisation is not optimised.  A need exists to enhance and consolidate the Department’s custodial function and ensure that all three spheres of government and state-owned enterprises implement a best practice government-wide immovable asset management approach.  The Department has therefore developed the GIAMA, which contains the following principles:

- Requires government bodies to utilise immovable asset management (IAM) techniques.  It sets out minimum management standards for the four asset management processes of strategic planning, acquisition, maintenance and management, and disposal.

- It stipulates minimum diligent analytical methods for these four processes, including assessment of the possibility of non-asset solutions.

- Covers all forms of immovable assets.

- Applies to all spheres of government and to public entities.

- Sets requirements for the content of AIM plans, with the aim of establishing minimum norms and standards for AIM.

3.	SERVICE DELIVERY STANDARDS – NATIONAL DEPARTMENT OF PUBLIC WORKS:

The National Department of Public Works (NDPW) has developed Service Delivery Standards (SDS) as a fore-runner to the Service Level Agreement (SLA) with a view to ensuring that client expectations are met in an achievable manner.  The SDS document further seeks to:

- Enhance the relationship between clients and NDPW as the accommodation service provider.

- Determine the standard of service and timeframe for delivery.

- Ensure that areas of dissatisfaction are reduced.

- Eliminate unrealistic expectations.

- Introduce annual review of standards to effect improvements in consultation with clients.

The services listed are generic and the listing is not a definitive itemisation of the various activities/business processes NDPW performs to achieve the stated deliverables.

The reaction times provided are negotiated deliverables with existing internal units and capture the existing conditions.

There is a concerted effort by the Director-General to provide additional resources and capacity to ensure shortened delivery time-frames, especially in planning and executing of infrastructure related projects.  NDPW will make every effort to meet stated timeframes.  NDPW’s ability to meet timeframes as captured in the SDS is governed by factors that are beyond NDPW control, including ensuring that planning, U-AMP requirements, needs assessments, budgets, project scope and changes requested by clients impact on accommodation deliverables.

The SDS is compiled in alignment with the asset management life-cycle.

SDS will be reviewed on a quarterly basis to improve and enhance delivery timeframes.

NDPW has set out the following minimum operational standards:

4.	USER PLANNING FOR IMMOVABLE ASSETS (GIAMA);

U-AMP (3 years in advance)

| Deliverable | Expected time-frames | Actioning component and stakeholder |
| --- | --- | --- |
| U-AMP Completion of templates and plan | Jan - June | User Department NDPW (AIM) |
| Match user requirements to Custodian Plan | July – August | NDPW (AIM) |
| Conduct options analysis | Sept – Dec | NDPW (AIM) |
| Submit to User costed projects/U-AMP to User Department | Jan – Feb | NDPW (AIM) |
| Draft and submit Implementation Programmes to User Departments | Nov- Jan | NDPW (AIM and Finance) |
| Revision of Implementation Programmes | April/May June/July | NDPW (AIM and Finance) User Department |

5.	CUSTODIAN PLANNING FOR IMMOVABLE ASSETS (GIAMA):

| Deliverable | Expected time-frames | Actioning component and stakeholder |
| --- | --- | --- |
| Compilation of C-AMP with inputs from U-AMP and NDPW portfolio information | Jan- June | NDPW (AIM) |
| Conduct option analysis Investment and disinvestment decisions | Jul – Oct | NDPW (AIM) |
| Analyse and prioritise user accommodation requirements in C-AMP | Nov – Mar | NDPW (AIM) |
| Submission to National Treasury (MTEC) to fund proposals | Apr – Sept | NDPW (AIM) |
| Reprioritise C-AMP in accordance with budget | Oct – Nov | NDPW (AIM and Finance) |
| Finalised Implementation Plans Capital Maintenance | Dec – Jan | NDPW (AIM) |
| Revision of Implementation Plans | June/July | NDPW (AIM and Finance) |

6.	SUBMISSION OF APPROVED NEEDS ASSESSMENTS AND BUDGET:

| Deliverable | Expected time-frames | Actioning component and stakeholder |
| --- | --- | --- |
| Submit needs assessments aligned to CWIP/LIP | Feb – Mar | User Department |
| Application of space and cost norms | Apr – May | NDPW (AIM) |
| Issue PDIR to PS | Apr –May | NDPW (AIM) |
| Issue PI’s to executing units | Apr – May | NDPW (AIM) |

7.	LEASING NEW:

| Deliverable | Expected time-frames | Actioning component and stakeholder |
| --- | --- | --- |
| User Department confirms needs/specialised requirements and budget via KAM HO | 30 days | User Department NDPW (AIM) |
| PI issued by KAM HO to Regional Office | 5 days | NDPW (AIM) |
| Procurement strategy submitted to Bid Committee | 21 days | NDPW |
| Tender and bid evaluation | 60 days | NDPW |
| Budget confirmation by User Department via KAM HO | 10 days | User Department |
| Final approval by Bid Committee | 7 days | NDPW |
| Sign lease agreement/contract | 20 days | NDPW |
| Refurbishment/tenant installation (dependent on extent of user requirements/extent of refurbishment) on new contract and extent and m² | 30 – 180 days | NDPW User Department Lessor |
| Inform User Department | 7 days | NDPW |
| Site handover | 7 days | NDPW |
| Management of leases: Manage terms and conditions of lease | Duration of the lease | NDPW |

8.	MANAGING OF LEASING CONTRACTS EXPIRING:

| Deliverable | Expected time-frames | Actioning component and stakeholder |
| --- | --- | --- |
| User Department and NDPW Regional Offices receive quarterly download of lease expiry report (leases expiring within 18 months) | Quarterly | NDPW (AIM) NDPW (RO) |
| User Department assesses all leases expiring within 18 months | 30 days | User Department |
| User Department to submit | 7 days | User Department |
| PI issued to RO (leasing procurement is initiated – see leasing new) |  | NDPW |

9.	EXECUTION OF IMPLEMENTATION PROGRAMMES:

  - TOWN PLANNING:

a)	Planning and alignment to Implementation Programmes:

| Deliverable | Expected time-frames | Actioning component and stakeholder |
| --- | --- | --- |
| Assess U-AMP/C-AMP to identify suitable sites as per options analysis reports (concurrent process with AIM) | 3 – 6 months | NDPW (AIM and PS) |
| Submit preliminary site investigation reports (possible sites) to AIM for submission to User with high level cost estimates. Execute prioritised TP services (Town Planning Implementation Programme) | 1 month | NDPW (PS) |
| Compile site acquisition plan aligned to CWIP | 1 week | NDPW (PS) |

b)	New sites:

- No restrictions (comply with existing land use and there is no need for development applications to be lodged):

| Deliverable | Expected time-frames | Actioning component and stakeholder |
| --- | --- | --- |
| Assess needs assessment/obtain additional information from User | 10 days | NDPW (PS) |
| Identify stakeholders per purpose | 7 days | NDPW (PS) |
| Locate and collect spatial data information about the site | 14 days | NDPW (PS) |
| Compilation and lodging of development applications, removal of restrictions, sub-divisions and consolidations and township establishments or changed in land use | 14 days | NDPW (PS) |
| Ensure tenure type and options | 7 days | NDPW (PS) |
| Conduct land – use inspections or site visits in respect of the area locally | 14 days | NDPW (PS) |
| Determine and recommend the potential use of a site to the User | 7 days | NDPW (AIM and PS) |
| User confirmation of site | 7 days | User Department |
| Facilitate (via AIM) procurement of site (private site) | 7 days | NDPW (PS) NDPW (AIM) User Department |
| Issue site clearance certificate to confirm compliance with TP laws/requirements | 2 days | NDPW (PS) |

NEW SITES:

- Restrictive conditions or change in land use

- Non-compliance to Town Planning legislation

| Deliverable | Expected time-frames | Actioning component and stakeholder |
| --- | --- | --- |
| Assess site and issue a report on resolving non-compliance with relevant Town Planning requirements | 30 days | NDPW (PS) |
| Identify relevant authorities and stakeholders to grant required approvals | 7 days | NDPW (PS) |
| Identify and determine scope of work, costs and time frames for appointment of service providers | 30 days | NDPW (PS) |
| Appointment of consultants (tendering) | 86 days | NDPW (PS) |
| Investigation of applications for town planning related issues | 180 days | NDPW (PS) |
| Approval of site by User Department | 10 days | User Department |
| Facilitate (via KAM) procurement o site | 14 days | NDPW (AIM) |
| Issue a clearance certificate to confirm compliance with Town Planning laws, requirements and site availabilities | 5 days | NDPW (PS) |
| Update Programme Management Schedules | Monthly | NDPW (PS) NDPW (AIM) |

9.2	ACQUISTION OF LAND (including buying in compliance to Legal and Municipal requirements:

One of these processes may apply to a site:

- Donation that has to be acquired (non-state owned site)

- Expropriation

- Prescription

- Common law	–	negotiated

-	Open tender

-	Quotation

- Exchange

| Deliverable | Expected time-frames | Actioning component and stakeholder |
| --- | --- | --- |
| Donation | 60 days | NDPW |
| Expropriation | 120 days | NDPW |
| Indigenous | 90 days | NDPW |
| Prescription | 90 days | NDPW |
| Common law Negotiated Procedure Open tender Quotation | 30 days 90 days 15 days | NDPW |
| Exchange of property | 90 days | NDPW |

9.3	NEW CONSTRUCT/REFURBISH/ UPGRADE/MAINTAIN:

| Deliverable | Expected time-frames | Actioning component and stakeholder |
| --- | --- | --- |
| PI issued to projects to schedule and appoint project managers | 4 days | NDPW |
| Project Managers: Develop and present procurement strategy including terms of reference for and appointment of consultants: Bids Roster system (limited instance) | 86 days 30 days | NDPW |
| Design and documentation (size and complexity of project) | 30 - 130 days | NDPW |
| User Department approval of sketch plan | 14 days | User Department NDPW |
| Documentation, Bid Committee approval and contractor appointment | 140 days | NDPW |
| Submission of guarantees and site handover | 35 days | NDPW |
| Project and programme management | Duration of project | NDPW |

10.	DAY TO DAY MAINTENANCE:

- Services below R 30 000 (NDPW Data base)

- Services above R 30 000 (CIDB Data base)

- Term contract} 1 – 5 days

- Emergency work

| Deliverable | Expected time-frames | Actioning component and stakeholder |
| --- | --- | --- |
| Receive complaint from User Department via Call Centre | Ad-hoc | User Department |
| NDPW assess the nature of service as per above categories to facilitate implementation |  |  |
| Term/contracts – request contractor to execute | 10 – 30 days | NDPW |
| Services below R 30 000 | 77 days | NDPW |
| Services above R 30 000 | 77 – 136 days | NDPW |
| Emergency work | 1 – 5 days | NDPW |

The above is dependent on the nature of the repair/work and also the complexity in terms of built environment disciplines (mechanical/electrical/structural)

The Department embarking to have FM contracts per portfolio (subject to budget availability)