IPID BILL

IMPLEMENTATION COST OF IPID BILL

Emphasis on staff structure prescribed by the IPID Bill

| No | ACTIVITY | Date of Implementati-on of Activity | Nature of Expenditure | ESTIMATED FUNDING REQUIRED IN THE FINANCIAL YEARS |
| --- | --- | --- | --- | --- |

2010/2011

R`000

2011/12

R’000

2012/13

R`000

2013/14

| R`000 |
| --- |
| INTRODUCTION OF THE NEW ACT AND REGULATIONS |
| 1 | Development of the Bill | 30 August 2010 | Expenditure in respect of department / State Law Advisor fees | 50 | - | - | - |
| 2 | Parliamentary Process/Regulations | 30 August 2010 | Expenditure in respect of travelling and accommodation | 50 | - | - | - |
| 3 | Compile Regulations and amend SOP | 30 September 2010 | SOP Committee and Consultant to meet to develop Regulations and amend SOP | 250 | - | - | - |
| 4 | Development of new Personnel Structure | 30 December 2010 | With the assistance of DPSA develop a personnel structure that would cover the additional work load addressed by the Bill | 10 | - | - | - |
| 5 | - | 30 January 2011 | Gain the assistance of DPSA to evaluate the new posts/ Job Levels to ensure correct salary levels and job contents | 100 | - | - | - |
| 6 | Adoption of Bill | 1 April 2011 |

|  | - | - | - | - |
| --- | --- | --- | --- | --- |
| 7 | Communication | Should the Bill be adopted during January to March 2011 |

Media campaigns and Community Awareness:

| Expenditure iro branding, signage, pamphlets, brochures, stationery, banners and gazebo’s | 100 | 300 | 150 | 100 |
| --- | --- | --- | --- | --- |
| 8 | Media Campaigns | Immediately after commencement of the Act |

Media campaigns and Community Awareness:

| Radio, printed media, internet, press conference | - | 400 | 150 | 200 |
| --- | --- | --- | --- | --- |

| No | ACTIVITY | Date of Implementati-on of Activity |
| --- | --- | --- |

Nature of Expenditure

|  | ESTIMATED FUNDING REQUIRED IN THE FINANCIAL YEARS |
| --- | --- |

2010/2011

R`000

2010/2011

R`000

2010/2011

R`000

2010/2011

| R`000 |
| --- |
| 9 | Launch of new Department in Provinces | 1 April 2011 | Meetings, travelling, accommodation, and venue costs | - | 200 | 50 | 50 |
| 10 | Revised Strategic & Performance Plan, Performance Agreements. | 1 January 2011 | Sign amended Performance Agreement(s) and amend Strategic, Performance Plan during Lekgotla in November 2010 for printing / tabling | 80 | 88 | 95 | 100 |
| 11 | Consultative process. | After 1 April 2011 | Participation of Labour Unions in consultation process regarding changes to be effected in the personnel structure, SOP’s, Work Place, etc. | - | 30 | - | - |
| 12 | Workshop with SAPS and the Secretariat of Police | 1 July 2011 | Hand-over of functions to the SAPS and where appropriate to the Secretariat of Police | - | 1 | 1 | 1 |
|  | TOTAL |
|  | 640 | 1 019 | 446 | 451 |

Bear in mind, by 1 April 2010 funding would have been approved for the ICD as per its current mandate and personnel establishment

A “new” funding request for the IPID will have to be submitted for the Adjustment Budget in October 2011, should the IPID Bill be enacted after 1 April 2011

Should IPID be successful in its request for additional funding during the Adjustment Budget, funds will be available as from December 2011

All newly created posts MUST be Job Evaluated before filling, to ensure correct job level and job contents

| No | ACTIVITY | Date of Implementati-on of Activity | Nature of Expenditure | ESTIMATED FUNDING REQUIRED IN THE FINANCIAL YEARS |
| --- | --- | --- | --- | --- |

2010/2011

R`000

2011/12

R’000

2012/13

R`000

2013/14

R`000

SHOULD FUNDING BE MADE AVAILABLE IN DECEMBER 2011 -

I P I D  - ADDITIONAL PERSONNEL STRUCTURE REQUEST (DEVELOPED FROM  CURRENT ICD STRUCTURE) AS PER THE IPID BILL

PROVINCES

13

PROGRAMME 2

| Implement of the conversion of the existing post levels of 9 Monitors and 29 Case Analysts to Investigators | 1 July 2011 |
| --- | --- |

32 X Case Analysts to be upgraded to Investigators

(Level 5 to level 7)

| 9 X Monitors to be upgraded to Senior Investigators (Level 7 to level 8) | - | 5 645 | 7 694 | 7 783 |
| --- | --- | --- | --- | --- |
| 14 | Upgrading of nine (9) Provincial Heads |

1 July 2011

1 April 2012

Advertise and filling of posts:

9 X Provincial Heads (level 14)

Operational expenditure; and

Furniture/Assets

9 X Personal Assistants

Operational expenditure; and

| Furniture / Assets | - |
| --- | --- |

8 190

1 350

1 215

-

-

-

8 673

1 350

-

1 883

450

1 080

9 151

1 350

-

1 959

450

| - |
| --- |
| 15 | Increase Investigative Teams in the Provincial Offices |

1 July 2011

-

17 359

6 150

4 920

18 783

6 150

19 401

| 6 150 |
| --- |
|  | Gauteng |

4 X Principal Investigators

| 6 X Senior Investigators |
| --- |
|  | KwaZulu-Natal |

2 X Principal Investigators

| 3 X Senior Investigators |
| --- |
|  | Western Cape |

2 X Principal Investigators

| 3 X Senior Investigators |
| --- |
|  | Eastern Cape |

2 X Principal Investigators

| 3 X Senior Investigators |
| --- |
|  | ACTIVITY | Date of Implementati-on of Activity | Nature of Expenditure | ESTIMATED FUNDING REQUIRED IN THE FINANCIAL YEARS |

2010/2011

R`000

2011/12

R’000

2012/13

R`000

2013/14

| R`000 |
| --- |
|  | North West |

1 X Principal Investigator

2 Senior Investigators

| 1X Data Capturer |
| --- |
|  | Limpopo |

1 X Principal Investigator

| 2 X Senior Investigators |
| --- |
|  | Free State |

1 X Principal Investigator

2 X Senior Investigator

| 1X Investigator |
| --- |
|  | Northern Cape |
| 1 Senior Investigators |
|  | Mpumalanga |

1 X Principal Investigator

3 X Senior Investigators

16

Opening up of Four (4) PLUS  Six (6) PLUS Three (3) =13 Satellite Offices over Three years (91 new  staff members to be appointed over three years)

Western Cape

George &

Worcester

Gauteng

Vereeniging

Mpumalanga

KwaMhlanga

|  | 1 July 2011 |
| --- | --- |

Personnel structure per Satellite Office (7):

1 X Assistant Director

1 X Principal Investigator

3 X Senior Investigator

1 X Investigator, and

1 X Administration Clerk

Compensation (4 offices, 28 staff members)

Operational expenditure

Assets / furniture and Equipment

Accommodation

-

11 568

4 200

3 360

300

11 980

4 200

-

332

12 345

4 200

-

364

| NO | ACTIVITY | Date of Implementati-on of Activity | Nature of Expenditure | ESTIMATED FUNDING REQUIRED IN THE FINANCIAL YEARS |
| --- | --- | --- | --- | --- |

2010/2011

R`000

2011/12

R’000

2012/13

R`000

2013/14

R`000

17

Opening up Six (6)

new Satellite Offices

Limpopo

Bela-Bela

Northern Cape

Springbok

KwaZulu-Natal

Ulundi

Eastern Cape

Port Elizabeth

Free State

Kroonstad

North West

| Klerksdorp | 1 April 2012 |
| --- | --- |

Personnel structure per Satellite Office (7):

1 X Assistant Director

1 X Principal Investigator

3 X Senior Investigator

1 X Investigator, and

1 X Administration Clerk

Compensation (4 +) Six offices, (28) 42 staff members)

Operational expenditure

Assets / furniture and Equipment

Accommodation

-

-

17 970

6 300

5 040

498

18 516

6 300

-

546

18

Opening up of Three (3) new Satellite Offices

Eastern Cape

Queenstown

Mpumalanga

Ermelo

KwaZulu-Natal

| Kokstad | 1 April 2013 |
| --- | --- |

Personnel structure per Satellite Office (7):

1 X Assistant Director

1 X Principal Investigator

3 X Senior Investigator

1 X Investigator, and

1 X Administration Clerk

Compensation (10 +)3 offices, (70 +) 21 staff members)

Operational expenditure

Assets / furniture and Equipment

Accommodation

-

-

-

9 258

3 150

2 520

273

| NO | ACTIVITY | Date of Implementati-on of Activity | Nature of Expenditure | ESTIMATED FUNDING REQUIRED IN THE FINANCIAL YEARS |
| --- | --- | --- | --- | --- |

2010/2011

R`000

2011/12

R’000

2012/13

R`000

2013/14

| R`000 |
| --- |
| 19 | Align existing Six Satellite Offices (increase structure) | 1 April 2013 |

1 X Assistant Director
2 X Senior Investigators, for the satellite Offices:

Rustenburg, Mthatha, Bethlehem, Upington, Empangeni & Thohoyandou

Operational expenditure

Assets / furniture

-

-

-

9 167

2 700

| 2 160 |
| --- |
| 20 | Training of Investigative staff | 1 April 2012 |
| - | 100 | 500 | 700 |
| 21 |

PROGRAMME 1

| Strengthening Communication in the nine provincial Offices | 1 April 2013 |
| --- | --- |

1 X Assistant Director (9 Provincial Offices)

Operational expenditure

Assets / furniture

3 130

1 350

| 1 080 |
| --- |
| 22 | Strengthening Support Services, especially in the Provinces | 1 April 2012 |

Provinces:

Strengthen support and segregation of duties.

in Free State, Limpopo and Eastern Cape
(3) Provinces

1 X Assistant Director: Administration (3)

Operational expenditure

Assets / furniture

-

-

1 023

150

360

1 068

150

-

1 April 2013

Provinces:

Strengthen support and segregation of duties.

in Mpumalanga and Northern Cape
(2) Provinces

1 X Assistant Director: Administration (2)

Operational expenditure

Assets / furniture

-

-

-

714

100

240

| NO | ACTIVITY | Date of Implementati-on of Activity | Nature of Expenditure | ESTIMATED FUNDING REQUIRED IN THE FINANCIAL YEARS |
| --- | --- | --- | --- | --- |

2010/2011

R`000

2011/12

R’000

2012/13

R`000

2013/14

R`000

TOTAL                  R

Training

Total (including Training)

Additional Provincial Staff

Additional Satellite Offices

-

64 257

100

64 357

(78)

(4)

93 916

500

94 416

(54)

(6)

125 575

700

126 275

(50)

(3)

| Office | Programme 1 | Programme 2 | Programme 3 | Total |
| --- | --- | --- | --- | --- |
| Current Structure |
| Provinces | 28 | 147 | 18 | 193 |
| National | 72 | 4 | 23 | 99 |
| Total | 100 | 151 | 41 | 292 |
| Additional staff |
| Provinces | 17 | 165 | - | 182 |
| National | 11 | - | 4 | 15 |
| Total | 28 | 165 | 4 | 197 |
| Grand Total | 128 | 316 | 45 | 489 |

| NO | ACTIVITY | Date of Implementati-on of Activity | Nature of Expenditure | ESTIMATED FUNDING REQUIRED IN THE FINANCIAL YEARS |
| --- | --- | --- | --- | --- |

2010/2011

R`000

2011/12

R’000

2012/13

R`000

2013/14

R`000

SHOULD FUNDING BE MADE AVAILABLE IN DECEMBER 2011 -

I P I D  - ADDITIONAL PERSONNEL STRUCTURE REQUEST (DEVELOPED FROM  CURRENT ICD STRUCTURE) AS PER THE IPID BILL

NATIONAL OFFICE

23

PROGRAMME 1

| Improvement of Communication Services | 1 July 2011 |
| --- | --- |

External consultation & community outreach

1 X Director

1 X Deputy Director: Communications.

Operational expenditure

Furniture / assets

-

1 184

445

255

1 257

300

-

1 313

300

-

24

PROGRAMME 3

Establish the “new” Programme 3: Legal Services

Litigation

Policy Development

1 April 2012

1 April 2013

Advertise and filling of posts:

3 X Deputy Director: Legal Service

1 X Director

Compensation

Operational expenditure

Assets / furniture.

-

-

1 257

300

255

2 297

600

375

25

PROGRAMME 1

(Auxiliary Services)

Give support to the line function

(Security Service)

1 April 2012

1 April 2011

1 April 2012

1 April 2013

1 X Deputy Director

1 X SAO

1 X Admin.

Operational Expenditure

Furniture / assets

1 X Deputy Manager

2 X SAO

Operational Expenditure

Furniture / assets

2 X SAO

Operational Expenditure

Furniture / assets

1 X Director

Operational Expenditure

Furniture / assets

-

-

-

-

938

450

375

-

862

150

360

1 189

450

-

750

300

240

903

150

-

1 329

450

-

816

300

828

150

| 135 |
| --- |
| NO | ACTIVITY | Date of Implementati-on of Activity | Nature of Expenditure | ESTIMATED FUNDING REQUIRED IN THE FINANCIAL YEARS |

2010/2011

R`000

2011/12

R’000

2012/13

R`000

2013/14

R`000

Total

TOTAL

(Additional staff)

Introduction of Act and Regulations

Total (Including Introduction)

| R | - |
| --- | --- |

3 647

1 019

4 666

(5)

7 670

446

8 116

(9)

9 946

451

10 397

(2)

Grand Total

GRAND TOTAL (all costs)

(Additional staff)

Training of Investigators

Introduction of Act and Regulations

R

67 904

100

1 019

69 023

(82)

101 586

500

446

102 532

(63)

135 521

700

451

136 672

(52)