ORGANISATIONAL PERFORMANCE REPORT

Q2 REPORT

2010/2011

DEPARTMENT OF AGRICULTURE, FORESTRY AND FISHERIES

TABLE OF CONTENTS

OVERVIEW	3

ADMINISTRATION	4

PROGRAMME PERFORMANCE AGAINST MEASURABLE OBJECTIVES	5

ANALYSIS OF PROGRAMME PERFORMANCE AGAINST MEASURABLE OBJECTIVES	17

CHALLENGES AND RESPONSES TO CHALLENGES	18

RECOMMENDATIONS	22

POLICY, PLANNING AND MONITORING AND EVALUATION	23

PROGRAMME PERFORMANCE AGAINST MEASURABLE OBJECTIVES	24

ANALYSIS OF PROGRAMME PERFORMANCE AGAINST MEASURABLE OBJECTIVES	28

RECOMMENDATIONS	28

ECONOMIC DEVELOPMENT, TRADE AND MARKETING	29

PROGRAMME PERFORMANCE AGAINST MEASURABLE OBJECTIVES	30

ANALYSIS OF PROGRAMME PERFORMANCE AGAINST MEASURABLE OBJECTIVES	34

CHALLENGES AND RESPONSES TO CHALLENGES	34

RECOMMENDATIONS	43

FOOD SECURITY AND AGRARIAN REFORM	44

PROGRAMME PERFORMANCE AGAINST MEASURABLE OBJECTIVES	45

ANALYSIS OF PROGRAMME PERFORMANCE AGAINST MEASURABLE OBJECTIVES	51

CHALLENGES AND RESPONSES TO CHALLENGES	51

RECOMMENDATIONS	56

AGRICULTURE PRODUCTION, HEALTH AND FOOD SAFETY	57

PROGRAMME PERFORMANCE AGAINST MEASURABLE OBJECTIVES	58

ANALYSIS OF PROGRAMME PERFORMANCE AGAINST MEASURABLE OBJECTIVES	73

CHALLENGES AND RESPONSES TO CHALLENGES	74

RECOMMENDATIONS	76

FORESTY AND RESOURCES MANAGEMENT	77

PROGRAMME PERFORMANCE AGAINST MEASURABLE OBJECTIVES	78

ANALYSIS OF PROGRAMME PERFORMANCE AGAINST MEASURABLE OBJECTIVES	88

CHALLENGES AND RESPONSES TO CHALLENGES	88

RECOMMENDATIONS	93

MARINE FISHERIES AND COASTAL MANAGEMENT	94

PROGRAMME PERFORMANCE AGAINST MEASURABLE OBJECTIVES	94

ANALYSIS OF PROGRAMME PERFORMANCE AGAINST MEASURABLE OBJECTIVES	107

CHALLENGES AND RESPONSES TO CHALLENGES	109

RECOMMENDATIONS	115

OVERALL ORGANISATIONAL ANALYSIS	117

RECOMMENDATIONS	117

# OVERVIEW

In this organisational report, the department presents its 2010/11 Quarter 2 performance against the planned deliverables as reflected in Part 5 of its Strategic Plan, this report has been compiled in accordance with Section 195 of the Constitution and other government legislative prescripts that guide performance management in the public sector to display and promote transparency and accountability to stakeholders and the general public concerning matters under their control.  This report also focuses attention on the performance of the department against its service delivery plans (key achievements), and alerts managers to areas where remedial action is required.

After the establishment of the new Department of Agriculture, Forestry and Fisheries (DAFF), some of the services and deliverables, planned initially, had to be reviewed to ensure alignment to the mandate of the new department and the general focus and approach of government. The department’s vision will be achieved through developing and sustaining a sector that contributes and embraces economic growth (and development), job creation, rural development, sustainable use of natural resources and food security.

The department comprises of seven branches/programmes which are: Administration; Policy, Planning and Monitoring and Evaluation; Economic Development, Trade and Marketing; Food Security and Agrarian Reform; Agriculture Production Health and Food Safety; Forestry and Resources Management; and Marine Fisheries and Coastal Management where key achievements will be highlighted in each programme.

# ADMINISTRATION

Purpose:

Provide the necessary human resources capacity, facilities and information and communication technology (ICT) hardware to ensure efficient and effective execution of the mandate of the Department of Agriculture, Forestry and Fisheries (DAFF). The programme is also responsible for the overall administration of DAFF; Stakeholder, Inter-governmental Relations, Communication and Legal Services.

It comprises of the programmes Corporate Services, Chief Financial Officer (CFO) and Stakeholder Relations and Legal Services.

# PROGRAMME PERFORMANCE AGAINST MEASURABLE OBJECTIVES

SUB-PROGRAMME: HUMAN RESOURCE DEVELOPMENT AND MANAGEMENT

| Strategic objective | Strategic outcome | Outcome indicator | Baseline | Target (2010/11) | Actual achievement |
| --- | --- | --- | --- | --- | --- |
| SO 3: To provide effective audit, investigative and legal, human resources and financial risk management SO 3: To provide effective audit, investigative and legal, human resources and financial risk management | Safe, secure, healthy and conducive working environment established Safe, secure, healthy and conducive working environment established | Aligned policies and practices with the operational objectives | Current approved policies and practices | 100% aligned to new legislation and directives | All HRM&D policies are in process of being reviewed and inputs are obtained from the identified role-players. All the reviewed policies will be presented for approval by GOPC. |
|  |  | Percentage (%) reduction in vacancy rate | 17% vacancy rate | 16% vacancy rate | The vacancy rate at the end of Q2 is still 10%. However the restructuring process may impact on the vacancy rate. |
|  |  | Percentage of quality performance agreements (PA’s) for SMS members submitted | 60% of performance agreements submitted | 70% of performance agreements submitted | Only 65% of performance agreements were submitted despite several follow ups. |
|  |  | Percentage (%) of employees trained and developed against specified standards or trained in new competencies | 55 % of targeted staff trained and developed | 50 % of targeted staff trained and developed | *No indication of progress |
|  |  | Percentage reduction in disease burden/incapacity (HIV/AIDS) | 20% strategy implementation and operational plan | 40% implementation and measurement (National Strategic Plan/Monitoring & Evaluation (NSP/M&E) and cost model) | The strategy has been finalised and it’s on the process of implementation. |
| SO 3: To provide effective audit, investigative and legal, human resources and financial risk management | Safe, secure, healthy and conducive working environment established | OHS risk assessment conducted in high-risk areas | 5% risk assessment conducted | 25% risk assessment conducted | *No indication of progress |

SUB-PROGRAMME: CHIEF INFORMATION OFFICER

| Strategic objective | Strategic outcome | Outcome indicator | Baseline | Target (2010/11) | Actual achievement |
| --- | --- | --- | --- | --- | --- |
| SO 5: To provide leadership and manage communication and information | Optimise ICT infrastructure and utilization | Availability of ICT infrastructure | Documented MSP, Information plan, Architecture plan, DRP, SLA and SLM of the three entities | Identify, collect and audit the documents of the three entities | Fisheries User migration is 95 %: Sites that are not done are: Durban 3 users, Port St Johns 9 users and Port Nollorth only 1 user. Server migration: 90 % with challenges. Forestry: User migration 60%, 11 sites outstanding. Server Migration: Infrastructure is procured and installed. |
| SO 5: To provide leadership and manage communication and information | Improved business processes and application | Migration and integration of ICT system processes and technology | Policies and procedures of the three entities | Identify, collect and audit the policies and procedures of the three entities | Collection of Forestry and Fisheries policies is 100% done. DICT had two meetings to discuss the collaboration of all ICT related policies. The collaboration is in progress, and also includes policies identified in the Audit Report. |

SUB-PROGRAMME: FINANCIAL MANAGEMENT

| Strategic objective | Strategic outcome | Outcome indicator | Baseline | Target (2010/11) | Actual achievement |
| --- | --- | --- | --- | --- | --- |
| SO 4: To improve departmental service excellence through implementation of quality standards, Batho Pele principles and general legislative mandate | Effective financial management | Compliance to legislation, prescripts, procedures and guidelines | Unqualified audit report | Unqualified audit report | An Audit Matrix was compiled to monitor progress on 2009/10 Audit Report and Audit Exceptions. |

SUB-PROGRAMME: DEVELOPMENT FINANCE

| Strategic objective | Strategic outcome | Outcome indicator | Baseline | Target (2010/11) | Actual achievement |
| --- | --- | --- | --- | --- | --- |
| SO 1: To increase equity, ownership and participation of Previously Disadvantaged individual (PDIs) | Increased access to development financial services by PDIs | Number of smallholder and subsistence farmers accessing financial services | 26 000 smallholder and subsistence farmers accessing development financial services | 10% | MAFISA: A total of R15, 289, 182 was disbursed to beneficiaries. 410 existing and 122 new. CASP: Q2 of 2010/11 A total of R 474 million was been disbursed to provincial departments, with R146 million spent as at end of August 2010 |
| SO 3: To provide effective audit, investigative and legal, human resources and financial risk management | Effective financial risk management systems | Functional management systems | None | Develop system | The CASP office together with office of CFO, M&E, MAFISA are currently in progress in developing a functional management system that will increase the impact of agricultural services to the community. |

SUB-PROGRAMME: STAKEHOLDER RELATIONS AND COMMUNICATION

| Strategic objective | Strategic outcome | Outcome indicator | Baseline | Target (2010/11) | Actual achievement |
| --- | --- | --- | --- | --- | --- |
| SO 5: To provide leadership and manage communication and information | Well informed internal and external public | 100% understanding of opportunities and support DAFF | Current status | 50% understanding of opportunities and support from DAFF | Information on the DAFF mandate was made available to departmental clients through press statements, external newsletter, advertisements, speeches at events, DAFF website, Thusong Service Centres, GCIS e-portal and exhibitions (Main events being Shanghai Exposition and 2010 FIFA World Cup). The Information Centre has dealt with 3 337 enquiries and issued 73 593 publications (eg. Info. Packs, 2009/10 Annual Report, etc.) of which 421 were sold from the Resource Centre. |
| SO 1: To establish and strengthen cooperative governance and functional relations with local and international stakeholders | Structured and functional relationships with key/strategic local stakeholders and partners | Increased percentage of engagements with all key stakeholders and partners (new) | Current status | Current number of stakeholder relations | The Department of Agriculture, Forestry and Fisheries has gone an extra mile as a new department in acquiring new stakeholders within its new mandate. The sub-programme has been able to consolidate the following statistics of stakeholders on its three core functions: Agriculture, to date the sub programme under the above mentioned function has about 120 stakeholders located within three developmental categories that are commercial, small holding and subsistence. The quantified number reflected above is the true reflection of the 2% increase on the number of stakeholders acquired by the sub programme during the period of quarter 2. Forestry: to date the sub programme under the above mentioned function has been able to consolidate the number of stakeholders categorised as follows commercial 12 , small holding 1200 and subsistence +/- 24 000. The quantified number reflected above is the true reflection of the 3% increase on the number of stakeholders acquired by the sub programme during the period of quarter 2. Fisheries, to date the sub programme under the above mentioned function has been able to consolidate the number of stakeholders categorised as follows commercial 4000 , small holding and subsistence 8 000 and non-consumptive/eco-tourism 300. The quantified number reflected above is the true reflection of the 5% growth increase on the number of stakeholders acquired by the sub programme during the period of quarter 2. |

SUB-PROGRAMME: LEGAL SERVICES

| Strategic objective | Strategic outcome | Outcome indicator | Baseline | Target (2010/11) | Actual achievement |
| --- | --- | --- | --- | --- | --- |
| SO 4: To improve departmental service excellence through implementation of quality standards, Batho Pele principles and general legislative mandate | Well drafted understandable legislation | Information received from internal client/legislative programme | As per legislative programme | Well drafted understandable legislation | The following are six (6) Acts which some of them were referred to state law advisor for consideration, others comments were received from the advisor and whilst others were sent to line function for further inputs : Plant Breeders’ Rights Amend-ment Bill Pounds Bill Proposed amendments to the Veterinary and Para-veterinary Professions Act, 19 of 1982 Agricultural Produce Agent Amendment Bill Marketing of Agricultural Product Amendment Bill Fertilizer and Feeds Bill |
|  | Provide legal support and advisory services | Minimised legal risk |  |  | 22 opinions dealt with. |
|  | Provide litigation support | Minimised queries |  |  | Civil matters (including appeals and claims against DAFF) There are 43 cases existing and 9 new matters. A total of 21 cases still exist (rollovers) for loss of government property. |

# ANALYSIS OF PROGRAMME PERFORMANCE AGAINST MEASURABLE OBJECTIVES

# Overall, the programme performed beyond average for the period under review, however the following are highlighted:

- Development finance – It is imperative again for the sub-programme to elaborate by what percentage they have achieved during the period under review in terms of the number of smallholder and subsistence farmers accessing financial services e.g. MAFISA, CASP etc.

- Where there is no indication of progress by the sub-programme, challenges and corrective measures must be highlighted

# CHALLENGES AND RESPONSES TO CHALLENGES

SUB-PROGRAMME: CHIEF INFORMATION OFFICER

| Strategic objective | Strategic outcome | Outcome indicator | Baseline | Target (2010/11) | Challenges | Corrective measure |
| --- | --- | --- | --- | --- | --- | --- |
| SO 5: To provide leadership and manage communication and information | Optimise ICT infrastructure and utilization | Availability of ICT infrastructure | Documented MSP, Information plan, Architecture plan, DRP, SLA and SLM of the three entities | Identify, collect and audit the documents of the three entities | Fisheries: Oracle financial system infrastructure is currently experiencing hardware problems. Difficult to test the cut-over Forestry: Budget is not available ESRI licensing | Loan equipment will be used for testing and the cut-over. Source funds |

SUB-PROGRAMME: FINANCIAL MANAGEMENT

| Strategic objective | Strategic outcome | Outcome indicator | Baseline | Target (2010/11) | Challenges | Corrective measure |
| --- | --- | --- | --- | --- | --- | --- |
| SO 4: To improve departmental service excellence through implementation of quality standards, Batho Pele principles and general legislative mandate | Effective ﬁnancial management | Compliance to ﬁnancial legislation, prescripts, procedures and guidelines | Unqualiﬁed audit report | Unqualiﬁed audit report | With the transfer of the forestry function from the DWA to DAFF a challenge exist to aliign forestry to uniform financial policies and procedures | Frequent monitoring for compliance, conduct training sessions, centralise control and supervision of forestry financial support staff. A comprehensive checklist was compiled and a overtime project has been approved to verify all payment batches from 1 April 2010. All assets at the Branch Forestry have been verified except the Eastern Cape Province. Once the process is finalised assets will be captured on LOGIS and officially transferred from DWA. Interim Financial Statements will be compiled for the period ending 31 September 2010, which will be audited by the Office of the Auditor General. |

SUB-PROGRAMME: STAKEHOLDER RELATIONS AND COMMUNICATIONS

| Strategic objective | Strategic outcome | Outcome indicator | Baseline | Target (2010/11) | Challenges | Corrective measure |
| --- | --- | --- | --- | --- | --- | --- |
| SO 5: To provide leadership and manage communication and information | Well informed internal and external public | 100% understanding of opportunities and support DAFF | Current status | 50% understanding of opportunities and support from DAFF | The pending of the implementation of the macro structure has an impact on the flow of information. Also lack of capacity , | External Communication strategy still to be approved by DEXCO, |
|  |  |  |  |  | AIS staff is stretched to perform functions for two components - understaffed. | Appointment of additional staff for effective and efficient service delivery |
|  |  |  |  |  | Limited budget allocated to the directorate | Budget made available for advertisements, promotional material to market and enhance the image of the department |

# RECOMMENDATIONS

# Based on the analysis above, the following are recommended:

- Actual achievements must directly talk to the set targets

# POLICY, PLANNING AND MONITORING AND EVALUATION

Purpose:

The programme is responsible for the coordination of policy development, research and technology development and monitoring and evaluation. Furthermore, it will render guidance to the strategic, programme and project planning processes and undertake statistical and economic analysis. This is to ensure a greater impact of the policies and programmes of the DAFF.

The programme comprises Monitoring and Evaluation and Policy Development and Planning.

# PROGRAMME PERFORMANCE AGAINST MEASURABLE OBJECTIVES

SUB-PROGRAMME: MONITORING AND EVALUATION

| Strategic objective | Strategic outcome | Outcome indicator | Baseline | Target (2010/11) | Actual achievement |
| --- | --- | --- | --- | --- | --- |
| SO 2: To strengthen policy, planning, monitoring, evaluation, reporting and sector information | Service delivery Performance contracts | Signed service delivery performance contract | Signed service delivery performance contracts | Service delivery forum established by July 2010 | Delivery agreements are to be signed by 15 October 2010. Work is still continuing to develop clear implementation plans which delivery forums will discuss with cabinet during December 2010. |
|  | Systems for monitoring evaluation and reporting sector M&E systems/ Frameworks | Approved M&E systems/frameworks | Government’s green paper on M&E and operational Knowledge Bank system | Approved and aligned Departmental M&E framework | The Monitoring and Evaluation Reporting (MER) framework has been adopted by DEXCO Status quo for Knowledge Bank still remains: 2010/11 KnowledgeBank (Kberp) software model has been developed and awaiting final structural information for loading in order to be used for reporting. . |
|  | Monitoring, evaluation and reporting system for improved service delivery | Approved M&E plans | Government’s green paper on M&E and operational Knowledge Bank system | Annual M&E Plan | The status quo still remains: The development of M&E plans will be facilitated as soon as the outstanding restructuring issues affecting the Department are finalised. |
|  | Standardised reporting systems | Performance reports | Approved and aligned departmental M&E framework | Quarterly and annual performance reports | Quarter 2 performance report has been compiled and the annual performance report will be compiled in the first quarter of 2011/12 for 2010/11. |
|  | Delivery programmes review/impact assessment Effective implementation of policies | Assessed/reviewed delivery programmes (selected) Existing policies Reviewed | Approved and aligned departmental M&E framework | Cataloguing of all departmental delivery programmes | The alignment of CASP M&E framework to government outcomes is still progressing well and CASP Planning was held on 28 September 2010. MAFISA Framework will be tabled at GOPC on 15 October 2010 for first approval. |

SUB-PROGRAMME: POLICY DEVELOPMENT AND PLANNING

| Strategic objective | Strategic outcome | Outcome indicator | Baseline | Target (2010/11) | Actual achievement |
| --- | --- | --- | --- | --- | --- |
| SO 2: To strengthen policy, planning, monitoring, evaluation, reporting and sector information | Effective implementation of policies | Existing policies reviewed | Approved departmental policy development framework | 3 policies reviewed and approved | This deliverable will be performed under the new unit (Policy Development) established on the departmental structure which awaiting approval. |
|  | Planning systems for improved service delivery | Aligned strategic and implementation plans | Strategic planning framework from National Treasury | All strategic plans concluded by January 2010 | Strategic Operational Planning (SOP) framework Consultation with Fisheries was completed. The document has been prepared for DEXCO to be presented in quarter 3. |
|  | Planning frameworks/systems | Effective planning systems | Green paper on planning | Approved departmental planning framework | Process still on hold pending finalisation of the Outcomes process as requested by provinces |
| SO 4: To provide leadership and support to research in the sector | Increased production enabled by appropriate technologies | Targeted research and technology development programmes to support production | Status report on targeted technology uptake and diffusion in the sector | Monitor and coordinate targeted technology uptake in the sector | Status quo still remains: No major progress has been done during the period under review. |

# ANALYSIS OF PROGRAMME PERFORMANCE AGAINST MEASURABLE OBJECTIVES

The programme has shown a major progress towards achieving its set targets for the period under review. There is still again a possibility that the target set (3 policies reviewed and approved) by the policy development and planning sub-programme might not be achieved due to the awaiting approval of the departmental proposed structure.  It was also difficult to measure performance for the mentioned sub-programme as no major progress was indicated in one of its deliverables.

# RECOMMENDATIONS

The approval and implementation (placements) of the structure will assist this branch to achieve some of its set deliverables.

# ECONOMIC DEVELOPMENT, TRADE AND MARKETING

Purpose:

The programme is key in directing the DAFF’s priority to increase the sector’s overall contribution to national GDP growth through creation of viable and sustainable cooperatives and rural enterprises, product value-addition and increase in exports. The implementation of international relations and trade strategies will be closely connected with marketing to access foreign markets.

The Programme: Economic Development, Trade and Marketing comprises three sub-programmes, which are International Relations and Trade; Cooperatives and Rural Enterprise Development; and Agro-processing and Marketing. International Relations and Trade focuses on SADC and Africa relations; International Trade; and Americas, Australia, Europe and Middle East relations. Co-operatives and Rural Enterprises Development focuses on cooperative development, rural enterprises development and BBBEE charters compliance. Agro-processing and Marketing focuses on domestic marketing, international marketing and agro-processing.

# PROGRAMME PERFORMANCE AGAINST MEASURABLE OBJECTIVES

SUB-PROGRAMME: AGRO-PROCESSING AND MARKETING

| Strategic objective | Strategic outcome | Outcome indicator | Baseline | Target (2010/11) | Actual achievement |
| --- | --- | --- | --- | --- | --- |
| SO 2: To increase the level of public and private investment for agriculture, forestry and fisheries products | Increased access to storage, processing and transportation infrastructure for agricultural, forestry and fisheries products by all categories of producers | Increased share of agricultural, forestry and fisheries products handled through additional investment in storage capacity | 31,8 mt (2008) | 31,8 mt | No indication of progress |
|  |  | Increased share of agricultural, forestry and fisheries products processed through additional investment | 35 mt | 37 mt | No indication of progress |
|  |  | Increased share of agricultural and forestry products transported through rail | 12 mt transported on rail | 15,6 mt transported on rail | Coordinated meetings with the departments of Trade and Industry, Transport, Public Enterprises and Transnet Freight Rail to facilitate the provision of freight logistics to the agricultural sector. |
| SO 3: To increase market access for South African and African agricultural, forestry and fisheries products domestically and internationally | New markets developed and expanded; and existing markets maintained for agricultural, forestry and fisheries products | % increase of agricultural, forestry and fisheries products into new markets | 35 % of agricultural products into new markets | 37 % | Concluded the amendments to the Marketing of Agricultural Products Act No, 47 of 1996 to clarify the role of the Department and the NAMC on the marketing of agricultural products, Concluded amendments to the Agricultural Produce Agents Act, No 12 of 1992 to make provision for broadened regulation of agents and traders facilitating the trade of agricultural products on behalf of farmers. Submitted a feasibility report on the establishment of fresh produce collating facilities to IDC, Landbank, DTI for EU Funding as well as provincial Development Corporations for possible funding. Inputs for negotiations with India were provided to the DTI. To quantify the export growth percentage wise will only be possible about six months after the end of the calendar year when statistics becomes available. |
|  |  | % share in traditional markets maintained for agricultural, forestry and fisheries products | Maintain average exports (65 %) | Maintain average exports (65 %) | Negotiations continued with the European Union on the review of the TDCA to try and obtain additional market access. To quantify the export growth percentage wise will only be possible about six months after the end of the calendar year when statistics becomes available. |

SUB-PROGRAMME: INTERNATIONAL RELATIONS AND TRADE

| Strategic Objective | Strategic Outcome | Outcome Indicator | Baseline | Target (2010/11) | Actual Achievement |
| --- | --- | --- | --- | --- | --- |
| SO 3: To increase market access for South African and African agricultural, forestry and fisheries products domestically and internationally | Facilitated intra-Africa trade on agricultural ,forestry and fisheries products | Increased share of African countries agricultural, forestry and fisheries products in South Africa’s import and export basket. | Imports = 5 % Exports = 35 % | Imports = 7 % Exports = 35 % | Work in progress. An intra Africa trade strategy is being developed to promote regional and continental trade. Current regional agreements of SACU and SADC are in operation A tripartite FTA negotiation with East Africa will start. Non-tariff barriers to trade within SACU and SADC identified and addressed systematically. A meeting of the SACU commission took place where trade issues within SACU as well as on SACU with third parties were discussed. To quantify the export growth percentage wise will only be possible about six months after the end of the calendar year when statistics becomes available. |
|  | Facilitated trade in value-added agricultural ,forestry and fisheries products (diversification of export products) | Increased share of South African value-added agricultural, forestry and fisheries products in total trade basket (domestically and internationally) | 51 % of export were processed products | 52 % of export processed products | A link with dti’s agro-processing unit is being forged to give practical effect to this outcome. It will also be considered within the framework of (elaborate) IPAP II on agro-processing. To quantify the export growth percentage wise will only be possible about six months after the end of the calendar year when statistics becomes available. |
| SO 1: To establish and strengthen co-operative governance and functional relations with local and international stakeholders | Improved cooperative Governance and partnerships | Improved participation of DAFF in the multilateral agencies | DAFF participating in the multilateral agencies (SADC, AU, UN agencies and WTO) | DAFF participating in the multilateral agencies (SADC, AU, UN agencies, etc.) | Participated in the steering committee meeting of RSA/ FAO capacity building project (13 July 2010) The department attended the SADC council and summit on the 11 to 17 August 2010. Facilitated and participated in the following meetings: between the Minister and IFAD President on the (26 July 2010), 7th RSA/EU dialog interdepartmental steering committee on the 4 August 2010, the 3rd SA/EU summit on 28 September 2010. Facilitated the department’s participation on the SADC FANR cluster meeting in Victoria Falls Zimbabwe 13 to 18 July 2010. |
|  |  | New agreements signed and existing MoUs implemented | Agreements not implemented in totality | Facilitate the implementation of active and signed MoUs and resolutions | The following agreements are bound and ready for signing: Congo Brazzaville and Egypt Facilitated and participated the following: JPCC meeting in Botswana 20 to 21 September 2010, State Visit to Russia and ITEC 3 -5 August 2010. Joint Agricultural Committee between RSA/Nigeria was re-established in August 2010. Coordinated and participated in the Joint Management Committee between RSA/Mozambique in July 2010. Joint Management Committee between RSA/Zambia was established in July. Facilitated and participated on the RSA/Lesotho JMC in July 2010, meeting with the German Federal Agriculture and consumer protection to discuss possible projects for collaboration. Facilitated the participation of the following: technical visit to Brazil in September 2010, by technical official from FSQA, the Minister’s participation in the State Visit, the Wine week and Agro-processing seminar in the PRC and Shanghai August 2010 respectively, Minister participation in the world export forum held in Chongqing in September 2010, participated in the SINO Africa Agricultural Forum held in Beijing 11-12 August 2010. Attendance of the first full session of the inter-governmental consultations between South Africa and Kazakhstan, 28 September Facilitated the submission of the project proposal of IBSA fund, the deadline was met in September. |

SUB-PROGRAMME: COOPERATIVES AND RURAL ENTERPRISE DEVELOPMENT

| Strategic Objective | Strategic Outcome | Outcome Indicator | Baseline | Target (2010/11) | Actual Achievement |
| --- | --- | --- | --- | --- | --- |
| SO 1: To increase equity, ownership and participation of PDIs | Increased shareholding of PDIs in the sector | % increase of PDI shares in the sector | Scorecards of the sector charters | As per scorecards of the sector charters | AgriBEE Charter Council met on the 1st September 2010 and all Council members agreed to gazette the current section 12 as section 9 sector code in order to enforce compliance. |
|  |  | Number of sustainable rural cooperatives (agriculture, forestry and fisheries) established and supported as vehicle for LED |  | 3 | 61 Co-operatives established during this quarter. |
| SO 2: To increase the level of public and private investment in the sector | Increased number and value of BEE deals | Number of BEE deals accessed | 20 | 12 | No progress |
|  |  | Value of BEE deals accessed (R/c) | R85 000000 | R 48 610 000 | No progress |

# ANALYSIS OF PROGRAMME PERFORMANCE AGAINST MEASURABLE OBJECTIVES

Based on the information above, the following issues needs to be highlighted:

- Information with regard to targets with percentages will only be available in 2011, due to the process of statistical information gathering and analysis.

- In certain targets the department do not directly increase or decrease exports or imports, but only plays a facilitation role in trying to achieve the target.

Overall it’s difficult to provide an analysis of the programme performance against measurable objectives due to a lack of annual performance plans to which performance can be tracked with. But, in addition based on the information provided, the sub-programmes where difficulties are encountered, are putting in place corrective measures which will ultimately lead to the achievement of their targets.

# CHALLENGES AND RESPONSES TO CHALLENGES

SUB-PROGRAMME: COOPERATIVES AND RURAL ENTERPRISE DEVELOPMENT

| Strategic objective | Strategic outcome | Outcome indicator | Baseline | Target (2010/11) | Challenges | Corrective measures |
| --- | --- | --- | --- | --- | --- | --- |
| SO 1: To increase equity, ownership and participation of PDIs | Increased shareholding of PDIs in the sector | % increase of PDI shares in the sector | Scorecards of the sector charters | As per scorecards of the sector charters | Reliance on the DTI IT Portal to report the implementation of the scorecards in the agricultural sector. The statistics on this portal have not changed since March 2010. | AgriBEE Charter Council is still in a process of finalizing the section 9 sector code that will have its own IT Portal. |
|  |  | Number of sustainable rural cooperatives (agriculture, forestry and fisheries) established and supported as vehicle for LED |  | 3 | Poor coordination of co-operative function among the Department, Provincial Departments of Agriculture and other government agencies which often results in duplication of efforts and resources. Lack of clear agricultural co-operative development strategies from provinces makes it difficult to promote and support co-operatives in the sector for example; it is not clear whether the cooperative development function for extension service or marketing and economic section. Inadequate support from extension services which could be tied up to absence of strategic direction in provinces on the co-operative function. This situation leads to misconception among extension services that the co-operative function is the responsibility of the Economics and Marketing Units which in turn do not have capacity to promote and support agricultural co-operatives. | A proposal to address these issues is being crafted and will be sent to H.O.Ds These issues will be addressed once the concept on cooperation among government spheres has been presented to provinces for discussion |
| SO 2: To increase the level of public and private investment in the sector | Increased number and value of BEE deals | Number of BEE deals accessed | 20 | 12 | The AgriBEE Fund MoA between DAFF and Land Bank has not yet been signed by both parties. | The Directorate met with the Legal Services Units of both DAFF and Land Bank to resolve the pending legal issues in the MoA. The MoA is now ready for signature by both parties. |
|  |  | Value of BEE deals accessed (R/c) | R 85 000 000 | R 48 610 000 | The AgriBEE Fund MoA between DAFF and Land Bank has not yet been signed by both parties. | The Directorate met with the Legal Services Units of both DAFF and Land Bank to resolve the pending legal issues in the MoA. The MoA is now ready for signature by both parties. |

# RECOMMENDATIONS

It can be observed that the sub programmes Agro processing and Marketing, and the International Relations and Trade   still ignores the category that reflects challenges and corrective measures and this does not reflect reality as they also mention that some agreements are not implemented in totality. In future it will be useful to mention the hindrances in implementing the Agreements although it is known that the factor depends on both sides.

The following are recommended:

- The structure of the department needs to be finalized.

- Placements into the new structure to be completed as to identify responsible people who will start reporting on their targets.

- Annual performance plans needs to be finalized as matters of urgency, so as to track the performance of the programme against predetermine milestones.

# FOOD SECURITY AND AGRARIAN REFORM

Purpose:

This programme is meant to develop and facilitate the implementation of appropriate agrarian reform policies and targeted programmes aimed at enhancing the contribution of subsistence and smallholder producers to food security, through education and training, provision of national extension and advisory services and the promotion of transformation imperatives in the agriculture, forestry and fisheries sectors. The programme comprises three sub-programmes which are Food Security, Sector Capacity Development and National Extension Support Services.

Food Security is responsible for subsistence farming, smallholder development and provision of inputs, implements and infrastructure support. Sector Capacity Development focuses on sector education and training, sectoral colleges and sector transformation. National Extension Support Services will develop national extension policies, and provide training and national extension support.

The two will direct and support agricultural education, training, extension and advisory services in support of targeted groups.

# PROGRAMME PERFORMANCE AGAINST MEASURABLE OBJECTIVES

SUB-PROGRAMME: FOOD SECURITY

| Strategic objective | Strategic outcome | Outcome indicator | Baseline | Target (2010/11) | Actual achievement |
| --- | --- | --- | --- | --- | --- |
| SO 2: To coordinate Government food security initiative | Improved support mechanisms for food production at subsistence and smallholder producers’ level | Coordinated support mechanisms for food production at subsistence and smallholder producers’ level | National Poverty Deprivation Index (Stats SA) | Monitor progress and food insecurity status in the country | Food Security Policy development process: Food security policy draft layout has been developed to guide the establishment of the Food Security Policy for South Africa. The scribing schedule was planned to take off from January 2010 and the document is halve complete with only two last parts currently under development [Policy strategic responses and the institutional framework for policy implementation]. Food Insecurity Information Management: As an alternative to FIVIMS which could not be rolled out nationally, the department in partnership with both SADC and FAO is currently implementing IPC, Livelihood Zoning and the formation of the NVAC. HHFPP: to date 810 households have been assisted with veggie-packs. Telefood: since inception in 2007, the department has secured approval of 14 projects to the value of 129 080 US$ |
| SO 5: To promote the use of feedstock by-products for renewable energies | Increased plant production over and above food security requirements | Increase in renewable energy production/ generation from plant products | Limited markets for animal feed impact negatively on development of renewable energies Present level of renewable energies estimated at 0,2 GWh | Coordinate agricultural support for Industrial Bio-fuel Strategy based on licenses approved | No indication of progress* |

SUB-PROGRAMME: SECTOR CAPACITY DEVELOPMENT

| Strategic objective | Strategic outcome | Outcome indicator | Baseline | Target (2010/11) | Actual achievement |
| --- | --- | --- | --- | --- | --- |
| SO4: Comprehensive support towards rural development | Increased access to training by community members | Approved training Programmes for community development | 2010–2014 sector skills plans for primary, secondary, forestry and food and beverage sectors of agriculture | Monitor training support to 10 000 members of communities, including Smallholder farmers and farm workers | Training program terminated due to funding limitations. |
|  |  |  | Training targets of FET and HET in Agriculture |  | Total number of 4 192 students are registered in various Further and Higher Education Institutions of Learning for various study fields in agriculture. |
| SO 4: To improve departmental service excellence through the implementation to quality standards, Batho Pele principles and general legislative mandate | A transformed DAFF and sector (Gender mainstreaming and transformation/sector transformation) | Compliance to transformation legislation | Not aligned | Audit departmental processes and deliverables aimed at vulnerable groups, youth, subsistence and smallholder producers | Policy harmonization workshops were conducted with Management Committees of the different branches of Forestry regions; as well as the Fisheries branch. Advocacy programmes on constitutional values underpinning the 1956 Women’s march conducted in the Fisheries branch (Port Elizabeth, Cape Town) as well as the Forestry branch of Pietermaritzburg. Quarterly survey on Employment equity targets for DAFF is available |

SUB-PROGRAMME: NATIONAL EXTENSION SUPPORT SERVICES

| Strategic objective | Strategic outcome | Outcome indicator | Baseline | Target (2010/11) | Actual achievements |
| --- | --- | --- | --- | --- | --- |
| SO 4: Comprehensive support towards rural development | Increased access to training by community members | Approved training programmes for community development | 1 700 community members receiving training | 1 000 | 390 community members (387 PDI`s) received training in Q2 Total for the year is 928. 1138 community members (708 PDI`s) attended information days Total for year 1646. |
|  |  |  | 3 out of 12 colleges are operating as centres of rural wealth creation | 4 | As a step towards establishing them as centres of rural wealth creation all twelve colleges of Agriculture have been given feedback in terms of identified gaps as mirrored against the norms and standards for ATIs. |
| SO 4: To provide leadership and support to research, training and extension in the sector | Increased production enabled by extension support and appropriate technologies | Approved training programmes for extension support | 438 | Coordinate and monitor the training of 1 000 extension officers in various skills training and qualifications upgrading programmes | 646 extension officers nationally are registered for qualification upgrading in different universities. 2 346 are trained in various short skills programmes. |
|  |  | Research and Technology development programmes to support production | Determination of targeted research and technology development programmes | Monitor the implementation of targeted research and technology development programmes | The initial status reports of three of the 10 signed Service Level Agreements on the targeted and priority research projects have been received and analyzed. |

# ANALYSIS OF PROGRAMME PERFORMANCE AGAINST MEASURABLE OBJECTIVES

Performance for the entire programme is still work in progress but it could not be measured to acceptable standards since targets were too broad and quarterly targets were not known. The target on *coordinating agricultural support for industrial Bio-fuel strategy based on licenses has still not been reported on.  This is mainly because the directorate Food Security is currently not performing such a function and therefore could not report on it.

The sub-programme National Extension Support Services did not report on their progress for quarter 2, only figures and information for the last quarter was included as part of the quarter 2 report.

# CHALLENGES AND RESPONSES TO CHALLENGES

SUB-PROGRAMME: SECTOR CAPACITY DEVELOPMENT

| Strategic objective | Strategic outcome | Outcome indicator | Baseline | Target (2010/11) | Challenges | Corrective measures |
| --- | --- | --- | --- | --- | --- | --- |
| SO 4: Comprehensive support towards rural development | Increased access to training by community members | Approved training Programmes for community development | 2010–2014 sector skills plans for primary, secondary, forestry and food and beverage sectors of agriculture | Monitor training support to 10 000 members of communities, including Smallholder farmers and farm workers | Lack of funding | Several requests for budget reprioritization but unsuccessful up until now. |
|  |  |  | Training targets of FET and HET in Agriculture |  | Only a small portion of youth are registered in scarce and critical study fields | The envisaged Implementation Protocol between DAFF and D:HET will assist in addressing this problem |
| SO 4: To improve departmental service excellence through the implementation to quality standards, Batho Pele principles and general legislative mandate | A transformed DAFF and sector (Gender mainstreaming and transformation/sector transformation) | Compliance to transformation legislation | Not aligned | Audit departmental processes and deliverables aimed at vulnerable groups, youth, subsistence and smallholder producers | Creating an enabling environment for transformation i.t.o Legislation and policies Effective and fully inclusive enabling structures: Women SMS Forum to comply with the transformation legislations and frameworks in the public service. Failure to meeting equity targets in set timeframes, e.g. 50% SMS women representation and across all levels in DAFF Monitor and report on gender equity and equality compliance at Provincial levels of DAFF | Ongoing alignment on mainstreaming cross-cutting issues. Continual strengthening of Sub-transformation Units in DAFF; Formation of the Women SMS Forum in DAFF Submission of report to the DG and the Executive on the percentage towards the targets on a quarterly basis. Participation in shortlisting and interviews of personnel in the different Directorates Departmental input in the Commission on Gender Equality national report on the Millennium Development Goals 2010 |

SUB-PROGRAMME: NATIONAL EXTENSION SUPPORT SERVICES

| Strategic objective | Strategic outcome | Outcome indicator | Baseline | Target (2010/11) | Challenges | Corrective measures |
| --- | --- | --- | --- | --- | --- | --- |
| SO 4: Comprehensive support towards rural development | Increased access to training by community members | Approved training programmes for community development | 1 700 community members receiving training | 1 000 | Most of the farmers found the green book challenging due to their literacy level. | The farmer’s green book has been translated into 7 indigenous languages. |
|  |  |  | 3 out of 12 colleges are operating as centres of rural wealth creation | 4 | The process of developing the ATI Bill is not progressing as planned | DETES has developed a schedule of fortnightly meetings with the appointed service provider to address the challenge |
| SO 4: To provide leadership and support to research, training and extension in the sector | Increased production enabled by extension support and appropriate technologies | Approved training programmes for extension support | 438 | Coordinate and monitor the training of 1 000 extension officers in various skills training and qualifications upgrading programmes | Insufficient funds to increase the extension officers according to their various skills needs | Lobby national treasury to increase allocations for Extension Recovery Plan (ERP) |
|  |  | Research and Technology development programmes to support production | Determination of targeted research and technology development programmes | Monitor the implementation of targeted research and technology development programmes | Lack of funds | Requests for budget reprioritization of funds |

# RECOMMENDATIONS

The Programme: Food Security and Agrarian Reform is advised to take into cognizance the challenges and their corrective measures as early as now to enable effective and efficient service delivery.

# AGRICULTURE PRODUCTION, HEALTH AND FOOD SAFETY

Purpose:

To identify opportunities and develop strategies in order to optimise agricultural productivity and profitability within the agricultural sector. To manage the risks associated with animal diseases, plant pests, genetically modified organisms and registration of products used in the agricultural field.

The Programme: Agriculture Production, Health and Food Safety comprises three sub-programmes, namely Plant Production and Health; Animal Production and Health; and Inspection Services and Food Safety.

Animal Production and Health is responsible for creating an enabling environment for increased and sustainable animal production through the efficient use of genetic resources, manages risks associated with animal diseases through appropriate policies, legislation, norms and standards, technical guidelines and other services.

Plant Production and Health focuses on increasing agricultural productivity with the emphasis on sustainable plant production systems, efficient use of genetic resources, and manages risks associated with plant pests and diseases.

Inspection Services and Food Safety is responsible for food safety and the quality of regulated products and provides for the national inspection service of regulated products intended for local and international markets.

# PROGRAMME PERFORMANCE AGAINST MEASURABLE OBJECTIVES

SUB-PROGRAMME: ANIMAL PRODUCTION AND HEALTH

| Strategic objective | Strategic outcome | Outcome indicator | Baseline | Target (2010/11) | Actual achievement |
| --- | --- | --- | --- | --- | --- |
| SO 4: To provide leadership and support to research, training and extension in the sector | Enhanced capacity for research, training and extension | Increased targeted research, development and training programmes | 10 | 2 | R&D facilities A baseline study on R&D capacity of existing facilities has been initiated; facilities has not been finalised The Gariep aqua training facility should be completed in schedule (Q3). A multi disciplinary workshop was held on site in Q2 to establish terms of reference and R&D priorities Discussions were held between the OIE and Rhodes University in Q2 on the establishment of a facility as collaboration centre. The proposal is now being considered by the OIE This will link to a reference lab at Onderstepoort as this is an established OIE reference lab. Training of animal surveyors (Comprehensive provincial Breed Survey) Training of 16 additional animal surveyors from Free State province was completed successfully in July 2010. The survey was successfully completed in Motheo and Xhariep District Municipalities. A total of 289 farmers were visited in the three Local Municipalities of Motheo. A total of 169 farmers were visited in the three Local Municipalities of Xhariep. |
| SO 1: To promote efficient production, handling and processing of food, fibre and timber | Increased production of productive animals and animal products | Percentage increase in productive animals and animal products | 29% increase | Baseline + 1 % | Kaonofatso ya Dikgomo – There are currently 921 farmer participants in this program. It is an ongoing process and focus has shifted to animal ID and the recording of births as a key priority to be able to have a core accurate assessment of the number of productive animals. Milk production and husbandry 560 farmers trained on milk production and husbandry (Milk recording). The official milk recording coordinator, MBISI is working closely with the Milk Producers organisation to establish study groups within the emergent milk producer sector. A detailed report will be included in Q3 |
| SO 3: To improve production systems anchored in commodities with competitive and comparative advantage in each province | Improved efficiency of farming systems per commodity | Percentage reduction in production costs for animals and animal products | Status report on average production costs per commodity | Reduction by 1 % | Baseline studies continue and commodity groups are providing more details on production costs as far as key commodities are concerned. These include beef, mutton, goat meat, milk, eggs, broilers, pork, wool and mohair. Production costs for producing breeding stock are also being determined. An article on the use of adapted breeds was published in SA Stud breeder and a presentation on using Nguni cattle for cost effective beef production was also made at a farmer’s day in the Western Cape. This presentation will be distributed to all Nguni breeders and will also be published as a scientific paper. |

SUB-PROGRAMME: PLANT PRODUCTION AND HEALTH

| Strategic objective | Strategic outcome | Outcome indicator | Baseline | Target (2010/11) | Actual achievement |
| --- | --- | --- | --- | --- | --- |
| SO 4: To provide leadership and support to research, training and extension in the sector | Increased plant production enabled by extension support based on researched solutions | Enabled extension services in provinces | Researched solutions are not adequately disseminated and transferred to users | All researched solutions completed in year are disseminated and made available to extension services | Research on wheat production & cultivar evaluation: SLAs were signed and reports are awaited from ARC Community Gene Bank Training Programme: Output scheduled for Q4, preparations underway |
| SO 1: To promote efficient production, handling and processing of food, ﬁbre and timber | Adequate volumes of plant production | Increased volumes of plant production and products | South Africa is presently a net exporter of food | Partially implemented agricultural production strategy: support commodity- specific strategies (e.g. grains, fruit and industrial crops) | Review of Cotton and fruit strategies: Good progress had been made in reviewing these two strategies. In case of cotton a steering committee is leading the process. The committee is made up of representatives of all stakeholders across the value chain. A draft strategy is close to finalization. In case of the fruit strategy, areas for amendment had been identified and work is been done in this regard. Advisory services on good production practices rendered to both farmers and extension officers. During the period under review, close to 358 farmers and 105 extension officers had been provided with technical advice on production practices of a wide range of crops. These ranged from site selection, cultivar choice, cultivation practices, and pest control. ) National Policy on Organic Farming. The 6th draft of the policy was tabled at ASRDC/ STC and was recommended for approval. Plant Breeder’s Rights Amendment Bill Written responses provided to the State Law Advisors (on their comments on draft 2)Memorandum of Objects completed and forwarded to Legal Services State law advisers indicated they delayed working on the Bill as they had other major projects |
| SO 3: To improve production systems anchored in commodities with a competitive and comparative advantage in each province | Efficient/effective province-specific commodity (crop) production | Production output comparisons between provinces per commodity | Comparative province-specific production advantage | Aligned spatial planning and support for plant production | A FAnGR survey execution plan meeting was successfully conducted for Lejweleputswa District Municipality. The actual FAnGR for Lejweleputswa was postponed due to financial constraints |
| SO 1: To promote safe food by managing the level of risks associated with food, diseases, pests, natural disasters and trade | Improved access to basic plant health services | Adequate products of good quality | Fragmented and nonexistent plant health services | Finalised MoU between ARC, DAFF and provinces to address primary plant health issues in rural areas | MoU with ARC and PDA’s: The current draft document is being updated for appropriate alignment with the departmental strategic plan and government objectives as well as recent developments on the expression of interest by DAFF in the CABI Plant Wise Clinic concept. |

SUB-PROGRAMME: INSPECTION SERVICES AND FOOD SAFETY

| Strategic objective | Strategic outcome | Outcome indicator | Baseline | Target (201/11) | Actual Achievement |
| --- | --- | --- | --- | --- | --- |
| SO 1: To promote safe food by managing the level of risks associated with food, diseases, pests, natural disasters and trade | Effective regulatory environment | Improved compliance to regulatory measures | Status report on the levels of compliance to regulatory measures | Review, improve and maintain an effective regulatory environment | REVIEW: Amendment Bill for Meat Safety Act: Process still ongoing. Proposed amendments being prepared for vetting by legal services. Amendments to Animal Identification Act .Process still ongoing. Proposed amendments being prepared for vetting by legal services Regulations for wheat and potatoes: regulations have been approved by the Minister in September and will be gazetted in Q3. Pesticides Policy: Submission for approval of Pesticides policy is enroute for Minister’s approval. Regulations relating to the ban of the use of chlorpyrifos: The regulation are implemented and monitored. Final Draft Proposal for Independent Meat Inspection: Approval of the Assignee structure by ITCA (VWG). Submission to the minister being drafted for approval by the minister in Q3 Schemes under Meat Safety Act Game Meat Scheme draft has been vetted by Legal Service twice and a final version was submitted to the Minister. However this version was further vetted by Legal Services and amended. This version must now be approved by Legal Services and further be submitted to the Minister. Abattoir Rating Scheme has been finalised but further comments were received from provinces resulting in a questionnaire being sent to all stake holders for further input before the final version is submitted to the Minister. |
|  |  |  |  |  | IMPROVE& MAINTAIN: Fertilizer and Feed Bill: Fertilizer bill has been incorporated into the feed Bill. The policy is on hold waiting for the appointment of a consultant Workshop was held with stakeholders on the Fertilizer and Feed Bill in the 12th of August 2010 and inputs received are being consolidated Standard Operating Procedure (SOP) for Exporting Rooibos: The SOP was updated and circulated for comments. Liquor Products act: Liquor Products act: Work has started to draft a policy which will precede amendment to the LPA Amendment of the Animal Diseases Act 1984, Act No. 35 of 1984) A memo was written on 13 July 2010 to HLS on Legislation Review process raising concerns by the Directorate Animal Health regarding the Animal Health Act 7 of 2002 particularly on Provincialized Veterinary Services, Delegation of certain functions to provinces, Essential National Standards, Designation of assignees, Compensation, requests for a legal expert to assist DAH on drafting of regulations Animal Health Act 7 of 2002. It was proposed that in the mean time, the Animal Diseases Act 35 of 1984 should be amended to include provisions for restriction on exportation of animals and things, determination of essential national standards that define the norms applicable to any control measures determined by the Director in order to achieve a controlled purpose; and compensation. |

# ANALYSIS OF PROGRAMME PERFORMANCE AGAINST MEASURABLE OBJECTIVES

Based on the information above there is a progress towards the achievement of the strategic outcomes for the programme. Though the following challenges still makes it difficult to give a conclusive verdict on the programme performance for the period under review.

- The absence /lack of information regarding base line. This creates a problem when measuring progress made towards achieving the strategic outcome and if this persists it could result in an audit query. To avoid this programme is urged to indicate the baseline information when reporting.

- Lack of specific time frames: This makes it difficult to measure the progress for the period under review. It is therefore imperative that the APP process be finalized soon to avoid a similar situation in future.

- Inconsistence or /and delayed reporting. Delayed and/or none reporting also makes it difficult to assess actual programme performance and it also delays and affects the finalization of the organizational report. The directorates and Chief Directorates are therefore urged to report as agreed.

Beside the achievements highlighted above, programme also rendered the service to the public such as:

- Inspection at official port of entry

- Register animal identification marks

- Registration of import and export facilities

- Issuing import permits

- Provide Plant Health Diagnostic Services

- Issue import permits for Plants, Plant Products and Other Regulated Articles

- Provide technical advice

- Information Material

- Analytical services

- Etc

# CHALLENGES AND RESPONSES TO CHALLENGES

SUB-PROGRAMME: ANIMAL PRODUCTION AND HEALTH

| Strategic objective | Strategic outcome | Outcome indicator | Baseline | Challenges | Corrective Measure |
| --- | --- | --- | --- | --- | --- |
| SO 1: To promote efficient production, handling and processing of food, fibre and timber | Increased production of productive animals and animal products | Percentage increase in productive animals and animal products | 29% increase | No the funds to do proper baseline studies |  |

SUB-PROGRAMME: PLANT PRODUCTION AND HEALTH

| Strategic objective | Strategic outcome | Outcome indicator | Baseline | Challenges | Corrective Measure |
| --- | --- | --- | --- | --- | --- |
| SO 3: To improve production systems anchored in commodities with a competitive and comparative advantage in each province | Efficient/effective province-specific commodity (crop) production | Production output comparisons between provinces per commodity | Comparative province-specific production advantage | The actual FAnGR for Lejweleputswa was postponed due to financial constraints |  |

SUB-PROGRAMME: INSPECTION SERVICES AND FOOD SAFETY

| Strategic objective | Strategic outcome | Outcome indicator | Baseline | Challenges | Corrective Measure |
| --- | --- | --- | --- | --- | --- |
| SO 1: To promote safe food by managing the level of risks associated with food, diseases, pests, natural disasters and trade | Effective regulatory environment | Improved compliance to regulatory measures | Status report on the levels of compliance to regulatory measures | Constraint is lack of funds for gazetting of regulations for wheat and potatoes |  |
|  |  |  |  | Lack of legal expertise within DAH to draft legislation. Publication of the Animal Diseases Amendment Bill | Engagement of a legal expert to draft legislation. |

# RECOMMENDATIONS

The programme performance for the first half of the2010/11 financial year seems to be satisfactory, as indicated above it is difficult to give conclusive verdict on the actual performance. If the above mentioned challenges are not addressed urgently this could result an audit query.

To minimise the chances of having an audit query

- The programme is urged to indicate the baseline information when reporting.

- Directorates and Chief Directorates are urged to adhere to reporting timeframes

- The APP process be finalized soon

# FORESTY AND RESOURCES MANAGEMENT

Purpose:

Sustainable use and management of natural resources underpins the agricultural, forestry and fisheries sectors. The programme will provide policy advice and coordinate the implementation of programmes aimed at ensuring that forestry production is undertaken sustainably, within the capacity of the landscape and climate. This includes encouraging landowners and managers to maintain and improve the natural resource base on which agricultural production relies—soil, vegetation, water and atmosphere.

The Resources Management part of the programme will contribute to policy and programme development and implementation in the areas of improving water access arrangements for all users and to promote its efficient allocation, use and sustainable management; encouraging sustainable resource access and use through the development of policies to position the agricultural, forestry and fisheries sectors to meet the challenges of achieving sustainable production. It will also provide accurate and reliable information for improved natural resource management, which is essential to the sustainable use of natural resources and policy development and programme implementation.

Resources Management will promote and facilitate greater adoption of sound agriculture, forestry and fisheries natural resource management at primary industries, communities and regions through targeted programmes to improve natural resource management practices and management of the natural resource base; and facilitate the development of agricultural infrastructure and the use of agricultural resources.

Other activities include auditing natural resources, compliance and law enforcement for natural resource management, controlling migratory pests, rehabilitating and protecting agricultural land and running the community-based LandCare Programme. It will furthermore develop mitigation and adaptation measures for risk and climate change.

# PROGRAMME PERFORMANCE AGAINST MEASURABLE OBJECTIVES

SUB-PROGRAMME: FORESTRY OPERATIONS AND FORESTRY MANAGEMENT

| Strategic objective | Strategic outcome | Outcome indicator | Baseline | Target (2010/11) | Actual achievement |
| --- | --- | --- | --- | --- | --- |
| SO 4: To increase contribution to green jobs to improve livelihoods | Increase the contribution of greening, participatory forest management and community forestry to improve livelihoods | Number of green jobs established. | Key issues paper | Forestry livelihoods strategy developed and implemented (150 green jobs established) | Project implementation taking place in KZN and appointment of Implementation Manager by WfW in E Cape underway. Quantity of jobs created to reflect in Quarter 3. |
| SO 1: To increase equity, ownership and participation of PDIs | Effective management of lease agreements | Equity and ownership of PDI’s in leased forestry packages | 1 | Siyaqhubeka agreements with beneficiary communities in place. | Minister still considering lease agreement Lease compliance audits conducted for Singisi and MTO Forestry needs identified for incorporation in the One Stop Shop. |
| SO 1: To increase growth, income and sustainable job opportunities in the value chain | Forestry sector transformed and potential in terms of growth realised. | Forestry 2030 Roadmap targets met. | White paper, NFA forest sector charter; National Forest Programme | 10 targets as reflected in the 2030 Roadmap met. | The road map is the forestry action plan with different strategies for all directorates. Progress with regard to targets reflected in the forestry 2030 roadmap is as follows at the end of Quarter 2: 1) NFP Strategies Draft Sawlog Strategy sent to stakeholders for comments SMME strategy developed and consultation completed Drafted prepared. Currently being consulted with stakeholders 2) Draft Forestry R&D Strategy referred to RDSTC for consideration and recommendation to DEXCO. SADC Forestry Strategy adopted by SADC Council of Ministers of Environment meeting held in Victoria Fall, Zimbabwe, 16 July 2010 (as reported in Q1) Letters written to all neighbouring countries regarding the signing of MoUs on Cross border fires and forestry related issues. Response received from Botswana and a meeting scheduled for 18th October 2010 in Pretoria with representatives of Botswana. Response was also received from Namibia and discussions are underway Preparatory work still underway for the signing of the Swaziland MoU 4) 120ha reforested 5) Still awaiting FSC Board approval of the National Certification Standard Planning in progress 7) Forestry inputs incorporated into the DAFF Education and Training Strategy. 8) Not achieved, awaiting finalisation of DAFF structure |
|  |  | Commercial forest estate expanded. | Afforestation maps; Forestry sector charter | 10 000ha afforested in EC and KZN | Reserve determination for all potential areas for afforestation in KZN has been approved and community mobilization will commence soon |
| SO 4: To provide comprehensive support towards rural development | Optimal use of State assets. | State forest land, not required for forestry land use purposes released for other land use purposes | 3 State forest areas released for other purposes | Land releases finalized within 3 months of Ministerial approval. | Restructuring plan for Injaka Plantation in place, but implementation hindered due to slow progress by Mpumalanga RLCC to finalise claim |
| SO 2: To ensure the sustainable management and efficient use of natural resources | Forestry assets sustainably managed. | National forest resource assessment completed. | Draft proposal for integrated land use resources assessment | Planning phase for assessment completed | Drafting of concept document in progress |
| SO1: To promote safe food by managing the level of risks associated with food, diseases, pests, natural disasters and trade | Increased compliance with and enforcement of the National Forest Act, 1998 and National Veld and Forest Fire Act, 1998. | Reduced incidents of veld, forest and mountain fires through the implementation of National Veld and Forest Fire Act, 1998. | 38 fire protection associations (FPAs) registered | 42 FPAs registered | 7 FPAs registered in the quarter Liaised with CD: Communications of the department of Water to get artworks of previously printed materials to be submitted to DAFF’s Information Services for verification of branding standards MP: Fire awareness material supplied to Lowveld & Escarpment FPA for distribution at schools. Sponsored fire awareness adverts on Radio Jacaranda for 1 month Southern Cape FPA monthly newsletter published Southern Cape FPA website launched 2 Firewise Boards erected on N2, at the Crags Radio talk on Eden FM discussing fire issues in the Southern Cape |
|  |  | NFA regulations published and implemented. | 38 fire protection associations (FPAs) registered | Compliance, monitoring and enforcement of NFA regulations | Draft Service Level Agreement developed for the PSP who will be running the Peace Officers course and submitted to Legal Services for approval. 3 NFA awareness sessions held at 3 local municipalities in Mpumalanga Draft list of spot fines (admission of guilt) compiled for submission to district magistrate in Mpumalanga (MP). W Cape: Court date for Case 176/6/2010 set for 1 October 2010 |

SUB-PROGRAMME: RESOURCES MANAGEMENT

| Strategic objective | Strategic outcome | Outcome indicator | Baseline | Target (2010/11) | Actual achievement |
| --- | --- | --- | --- | --- | --- |
| SO 4: To increase contribution to green jobs to improve livelihoods | Increase the contribution of LandCare and sustainable land management to improve livelihoods | Number of Green Jobs created | 14000 | 25000 | During second quarter, Land Care has created 2219 job opportunities |
| SO 1: To promote environmentally sustainable production systems (best practices) | Minimised environmental degradation | Number of land Users adopting best practices | Suboptimal adoption and implementation of best practices | Assess extent of adoption per farmer category and implement programmes to enhance adoption | 59 Commercial farmers adopted on 16891 ha, 380 Smallholder farmers adopted on 22663.7 ha and 215 Subsistence farmers adopted on 5797.81 ha. |
|  |  | Status of agricultural land retained(limited conversion of Agricultural | Policy and legislation outdated | Review and development of agricultural land protection policy | The Directorate is in the process of developing a policy for both Conservation of Agricultural Resources Act, Act 43 of 1983 (CARA) and Sub division of Agricultural Land Act, Act 70 of 1970 (SALA). The review of the above legislations will be done once the policies have been approved. |
| SO 2: To ensure the sustainable management and efficient use of natural resources | Efficiently managed use of water resources | Support and strengthened institutional arrangements for management of water | Fragmented data | Consolidate data and conduct assessments | The Policy Framework on Irrigation in South Africa was presented at the Free State, Limpopo and Mpumalanga Province Coordination Committees for Agriculture Water (CCAW) meetings. The policy frame-work was also tabled for noting at the Natural Resource Management Working Group Meeting. Additional information was gathered and analysed for the development of norms and standards for revitalisation of irrigation schemes. This includes the following report completed by the WRC: “The Water Use efficiency from Dam wall to root zone”. Attend project reference group meetings at the Water Research Commission. |
| SO 1: To promote safe food / ﬁbre production by managing the level of risks associated with food, diseases, pests, natural disasters and trade | Adopted climate change sector plan | Approved and implemented sector plan | Draft plan | Identify vulnerable areas in the sector | Progress is being made and the directorate received profiles of the identified areas from PDA, Free State Province. The profiles are currently being analysed. |
|  | Improved early warning systems | Reduction of natural related risks | Systems in place | Implement and review | Weather and climate capacity building workshop was conducted in Limpopo during quarter 2.The focus of the workshops including the Limpopo one in quarter 1 was on interpretation, understanding, and usage of weather and climate information to agriculture.The biannual report is available. |

# ANALYSIS OF PROGRAMME PERFORMANCE AGAINST MEASURABLE OBJECTIVES

There is good progress in delivery of planned targets by sub-programme resource management. The target of reviewing and development of agricultural land protection policy seems unlikely to be achieved in a single financial year. Developing policy is a very extensive consultative process and hence to have two policies developed and approved during this financial year and reviewing of two (2) acts can not be practically achieved in the planned period.

Sub-Programme Forestry Operations and Forestry Management is also showing progress on their planned targets. There is however a need to fast track the process of mapping out services rendered; this will assist in separating reporting on services from strategic interventions.

# CHALLENGES AND RESPONSES TO CHALLENGES

SUB-PROGRAMME: FORESTRY OPERATIONS AND FORESTRY MANAGEMENT

| Strategic objective | Strategic outcome | Outcome indicator | Baseline | Target (2010/11) | Challenges | Corrective measure |
| --- | --- | --- | --- | --- | --- | --- |
| SO 1: To increase equity, ownership and participation of PDIs | Effective management of lease agreements | Equity and ownership of PDI’s in leased forestry packages | 1 | Siyaqhubeka agreements with beneficiary communities in place. | Process required prior approval of lease agreement by Minister (not yet signed) |  |
| SO 1: To increase growth, income and sustainable job opportunities in the value chain | Forestry sector transformed and potential in terms of growth realised. | Forestry 2030 Roadmap targets met. Commercial forest estate expanded. | White paper, NFA forest sector charter; National Forest Programme | 10 targets as reflected in the 2030 Roadmap met. | Awaiting Forest Stewardship Council (FSC) Board approval for the National Certification Standard (NCS) | Continue to strengthen the relationship with the Council. |
| SO 4: To provide comprehensive support towards rural development | Optimal use of State assets. | State forest land, not required for forestry land use purposes released for other land use purposes | 3 State forest areas released for other purposes | Land releases finalized within 3 months of Ministerial approval. | Depends on availability of land not required for forestry |  |
| SO 2: To ensure the sustainable management and efficient use of natural resources | Forestry assets sustainably managed. | National forest resource assessment completed. | Draft proposal for integrated land use resources assessment | Planning phase for assessment completed | Invitation with proposed date sent to stakeholders (awaiting responses) | The first stakeholder workshop has since been held on 13 August 2010 and a Discussion Paper is being drawn in preparation for the planned (broader) workshop |
| SO1: To promote safe food by managing the level of risks associated with food, diseases, pests, natural disasters and trade | Increased compliance with and enforcement of the National Forest Act, 1998 and National Veld and Forest Fire Act, 1998. | Reduced incidents of veld, forest and mountain fires through the implementation of National Veld and Forest Fire Act, 1998. NFA regulations published and implemented. | 38 fire protection associations (FPAs) registered | No registration requests have been received from landowners, registration is voluntary | No registration requests have been received from landowners, registration is voluntary |  |

SUB-PROGRAMME: RESOURCES MANAGEMENT

| Strategic objective | Strategic outcome | Outcome indicator | Baseline | Target (2010/11) | Challenges | Corrective measure |
| --- | --- | --- | --- | --- | --- | --- |
| SO 1: To promote environmentally sustainable production systems (best practices) | Minimised environmental degradation | Number of land Users adopting best practices | Suboptimal adoption and implementation of best practices | Assess extent of adoption per farmer category and implement programmes to enhance adoption | Time lack after submission to obtain feedback from National Treasury. | Strengthen liaison with National Treasury |
|  |  | Status of agricultural land retained( limited conversion of Agricultural | Policy and legislation outdated | Review and development of agricultural land protection policy | Long legal process | Engage legal service to fast track the process. |
| SO 4: To increase contribution to green jobs to improve livelihoods | Increase the contribution of LandCare and sustainable land management to improve livelihoods | Number of Green Jobs created | 14000 | 25000 | Provincial reports inadequate to report accurately on number of green jobs established. | Liaise with provincial LandCare project coordinators to ensure reporting on number of green jobs established. |
| SO 2: To ensure the sustainable management and efficient use of natural resources | Efficiently managed use of water resources | Support and strengthened institutional arrangements for management of water | Fragmented data | Consolidate data and conduct assessments | CCAW meetings in the Provinces have not taken place regularly. The Water Use Working Group and the Natural Resource Working Group have merged and DWUID has not been able to table the Irrigation Policy Framework to the NRM Working Group. | Irrigation Policy Framework to be presented to the remaining Provinces by way of CCAW Meetings. Table the following documents at next NRM Working Group Meeting: (1) Irrigation Policy Framework; (2) Report on Efficient Agricultural Water Use Technology; (3) Irrigation Water Quality Guidelines. |
| SO 1: To promote safe food / ﬁbre production by managing the level of risks associated with food, diseases, pests, natural disasters and trade | Adopted climate change sector plan | Approved and implemented sector plan | Draft plan | Identify vulnerable areas in the sector | Delay in response from PDA Lack of resources (personnel and financial). | To setup a follow up meeting with PDA. To request funds for climate change projects. |

# RECOMMENDATIONS

Consistent and regular reporting will surely be the order of the day from now on since the monitoring, evaluation and reporting framework of the department has been approved. This will go a long way in enabling thorough assessment of performance information and improve the capacity to advice management.

# MARINE FISHERIES AND COASTAL MANAGEMENT

Purpose:

The aim of the branch will be to contribute to maintaining and restoring the productive capacity and biodiversity of the marine environment, ensuring the protection of human health, as well as promoting the conservation and sustainable use of marine living resources. The branch further aims to ensure that the degradation of the marine environment from land-based activities is prevented by facilitating the realisation of the duty of the DAFF to preserve and protect the marine environment through the application of respective policies, priorities and resources.

# PROGRAMME PERFORMANCE AGAINST MEASURABLE OBJECTIVES

| Strategic objective | Strategic outcome | Outcome indicator | Baseline | Target (2010/11) | Actual achievement |
| --- | --- | --- | --- | --- | --- |
| SG4;SO 1: To increase equity, ownership and participation of PDIs | Increased marine and coastal economic opportunities and broadened access for PDIs | Implementation of the Transfer of Rights Policy, the allocation of ﬁshing rights and implementation of the Small-scale Fisheries Policy in respect of transformation imperatives | Transfer of Rights Policy and a draft policy on small-scale fisheries | Implementation of policies | Draft Small-scale fisheries Policy gazetted and road shows conducted. Section 21 Application: Received 170,Finalised 26 |
|  | Facilitate affirmative procurement | % expenditure on procurement from BEE and BBBEE enterprises | 35 % expenditure on procurement from BEE and BBBEE enterprises | 40 % expenditure on procurement from BEE and BBBEE enterprises | 37 % expenditure on procurement from BEE and BBBEE enterprises |
| SG5;SO 1: To increase, growth, income and sustainable job opportunities in the value chain | Key recommendations of harbor feasibility study implemented | Livelihood opportunities for coastal communities and improved harbor infrastructure | Harbor feasibility study | 25 % implementation of recommendations | 25% implementation of quick wins recommendations of study achieved Improved the following: Lease Agreement and Property Management Slipway maintenance Communication between stakeholders On site management and security |
| SG2;SO 1: Promote environmentally sustainable production systems | Marine aquaculture monitoring and evaluation framework in place | No M&E framework in place | Monitoring and evaluation plan developed | 70 % M&E of 3 pilot projects | Draft Environmental Management and Monitoring Framework (EMMF) completed and discussed with DEA. EMMF is undergoing peer review at DEA and the submission to outsource the undertaking of an independent environmental legal review is in the office of the Acting DDG: Fisheries and will be forwarded accordingly for DG approval. Saldanha Bay surveys and Land-based Abalone Effluent surveys were conducted and a paper on the first phase of these ongoing surveys is currently being written up. Photographing of macrofauna species from the first phase of Saldanha Bay benthic survey has commenced. Monitoring and surveys will be conducted in other potential zones once those zones have been declared after successful EIA processes currently in progress. |
|  | EU accreditation of shellﬁsh | No EU accreditation of shellﬁsh | Review of EU accreditation criteria and development of a shellfish sanitation programme | Achievement of 50% of EU requirements | About 20% of the Food and Veterinary Office’s (FVO’s) evaluation report recommendations regarding EU requirements have been completed, e.g. the FVO observed deviations from the South African Molluscan Shellfish Monitoring and Control Programme with regard to turn around times for biotoxins, number of samples sizes taken. The Liquid Chromatography Mass Spectrophotometer (LCMS) which will replace the Mouse Bioassay method for testing samples for the presence of marine biotoxins has been delivered and installed. Training of DAFF officials is scheduled for mid November 2010. South African Molluscan Shellfish Monitoring and Control Programme officials will undergo training on Phytoplankton Identification and Enumeration Training in November 2010. The SA molluscan shellfish monitoring and control programme has been reviewed to be inline with international standards |
|  | Number of research projects on feasibility of SA aquaculture species conducted | Research into 2 SA aquaculture species (ﬁnﬁsh and scallops) | Research into 2 SA Aquaculture species (finfish and scallops) | Research into 2 SA aquaculture species (ﬁnﬁsh and scallops) | Spawning of sea urchins currently underway. Spawning and grow out trials scallops in process. |
| SG2;SO 2: Ensure the sustainable management and efficient use of natural resources | Promote the equitable and sustainable management and efficient use of marine living resources | % of commercial ﬁshing right holders per cluster who have had their performance reviewed | Work plan finalised and key performance indicators drafted for fishery performance reviews | 70 % of the ﬁsheries reviewed by cluster | Cluster C and D assessments being finalized. Cluster A and B assessments to commence in Q3. Survey results being analyzed. |
|  |  | 100 % of commercial rights transfer applications processed within speciﬁed service standards | Draft policy on transfer of commercial fishing rights published | Finalise policy on commercial rights transfer and applications processed | Policy gazetted on 31/07/2009 |
|  | Rebuild depleted ﬁsh stocks | Extent of recovery of hake and abalone, West Coast Rock Lobster and lineﬁsh | Strategy in place for abalone and hake | Continuous review of strategy for hake and abalone in respect of research, management and compliance | National Integrated Security Strategy for abalone. Standard operating procedures developed by MCS for the monitoring and inspection of Rock Lobster, Line fish and Squid sectors Analysis is being conducted to determine state of recovery. Hake Resource : The hake resource is managed in term of an Operational Management Procedure (OMP).The most recent OMO(implemented in October 2006) had the objectives of median recovery of the heavily depleted M.paradoxus resource spawning biomass (as then defined)to 20%of pristine over 20 years, a CPUE increase of 50%over the next 10years and changes in the TAC constrained to 10% up or down from one year to the next. An in –depth assessment of the hake resource was conducted during 2009 and the results from this assessment indicated that the status of the hake resource was still within the range applicable to the OMP formulation. It was also noted that the recovery plan for M. paradoxus was working and yielding positive results. Abalone: The Abalone SWG has held numerous deliberations over the course of this year (in the order of around 10 SWG and Task Group meetings) to assess the status of the abalone resource and provide recommendations to management .Abalone industry stakeholders have participated in all/most of these meetings. Many working group documents are produced each year – and are available upon request. In addition to the TAC submissions in January and March for the 2009/10 season, the SWG submitted: recommendation for the sustainable management of the abalone for the 2010/11 season,(in August 2010),as well as recommendation on surveys of the Eastern Cape. The abalone SWG has also prepared inputs towards the plan for the experimental allocations for False Bay and the Eastern Cape – that will be submitted to management by the end of this week. West Coast Rock Lobster : Routine data collection and assessment of the commercial recreational and interim Relief sectors of the West Coast Rock lobster fishery, using the “OMP 2007 recast” adopted in 2008, resulted in a reduction in the recommended TAC by 4.5% for the 2010/11 season. This is to enable recovery of the resource by 20%from 1996 to 2016. LineFish Linefish recovery is threatened exceeding of TAE, non- compliance and by –catch in other fisheries. No alignment with DEA in terms of Marine Protected Ares expansion. No alignment of management regimes in case of overlapping stocks (ie LineFish –Demersal Trawl).Failure to extent observer programme. |
|  | Compliance with and enforcement of marine and coastal legislation | % of ﬁsh processing establishments inspected | Rudimentary operational data | 40 % of ﬁsh processing establishments inspected | Registered FPE’ s =74 No of Inspections 615 On average FPE’s was inspected 8,3 times each, during the reporting period >100% |
|  |  | % of rights holders investigated in 5 key ﬁsheries sectors |  | 10 % of rights holders in the 5 key ﬁsheries investigated | 10% of right holders in the 5 key fisheries investigated. West Coast Rock Lobster Section rights holder found guilty and fined R100 000. Land Based Hake Trawl: 374 inspections of 478 vessels that landed (72%) Hake longline:100% of 176 vessels West Rock Lobster 100% of 2110 Vessels that landed Squid: 35 Inspections of 43 Vessels (80%) Sea Based: Abalone 3 Hake Trawel 23 West Coast Rock Lobster 8 Linefish 29 Squid 21-162 7.5 %of vessels inspected in the 5 keys fisheries sectors. |
|  |  | % of vessels inspected in the 5 key ﬁsheries |  | 15 % of vessels inspected in the 5 key ﬁsheries sectors | 10% vessels inspected at sea |
|  |  | Percentage of cases and tip-offs investigated according to service standards | Limited investigation capacity and no service standards in place | 75 % of cases and tip-offs investigated according to services standards | 85% of cases and tip offs investigated according to Services Standards. A total of 102077 unit of abalone with a value of R11960 000 retrieved and 1 syndicate related cases concluded as guilty (R60 000) |
|  |  | Number of joint partnerships with law enforcement and conservation agencies established | 5 partnerships | Maintain and strengthen 5 partnerships | 337 Joint Operations with SAPS, SANDF, and SARS, SANAPARKS and Nature Conservation. |

# ANALYSIS OF PROGRAMME PERFORMANCE AGAINST MEASURABLE OBJECTIVES

The programme’s performance based on reported outputs is satisfactory however more emphasis need to be put on reporting against the targets. The programme has improved on reporting against targets which are expressed in percentages by reporting on milestones achieved; however there is still room for improvement.

26% of the programme’s planned deliverables were transferred to DEA.  There is also a need for the programme to improve stating challenges and corrective measures as they relate to the targets

# CHALLENGES AND RESPONSES TO CHALLENGES

| Strategic objective | Strategic outcome | Outcome indicator | Baseline | Target (2010/11) | Challenges | Corrective measures |
| --- | --- | --- | --- | --- | --- | --- |
| SG4;SO 1: To increase equity, ownership and participation of PDIs | Increased marine and coastal economic opportunities and broadened access for PDIs | Implementation of the Transfer of Rights Policy, the allocation of ﬁshing rights and implementation of the Small-scale Fisheries Policy in respect of transformation imperatives | Transfer of Rights Policy and a draft policy on small-scale fisheries | Implementation of policies | Time frame for finalization of policy. Implementation of policy | Consultation with Stakeholders |
|  | Facilitate affirmative procurement | % expenditure on procurement from BEE and BBBEE enterprises | 35 % expenditure on procurement from BEE and BBBEE enterprises | 40 % expenditure on procurement from BEE and BBBEE enterprises | The Vessel Management contract brings BEE spending down by at least 13% basis point in the financial period ending 30 September 2010.Also the branch has existing contracts with companies that don not have strong BEE ownership. | We will insist on greater participation of HDI suppliers when the vessels management contract is awarded from 01 April 2011.Also when the existing contracts cease, we will insist of greater HDI participation from our suppliers. |
| SG5;SO 1: To increase, growth, income and sustainable job opportunities in the value chain | Key recommendations of harbor feasibility study implemented | Livelihood opportunities for coastal communities and improved harbor infrastructure | Harbor feasibility study | 25 % implementation of recommendations | Final approval for principles. Funding. Rollout of road show to release study. | Ministerial approval (DAFF & DPW) Submissions prepared for two Ministers Funding and road shows dependant on outcomes of discussions between Ministers |
| SG2;SO 1: Promote environmentally sustainable production systems | Marine aquaculture monitoring and evaluation framework in place | No M&E framework in place | Monitoring and evaluation plan developed | 70 % M&E of 3 pilot projects | Supply Chain Management processes. | OCFO to provide training. |
|  | EU accreditation of shellﬁsh | No EU accreditation of shellﬁsh | Review of EU accreditation criteria and development of a shellfish sanitation programme | Achievement of 50% of EU requirements | Capacity (HR), equipment, and coordination with other government departments. | Employ and train personnel, source funding and MoU’s in place. |
|  | Number of research projects on feasibility of SA aquaculture species conducted | Research into 2 SA aquaculture species (ﬁnﬁsh and scallops) | Research into 2 SA Aquaculture species (finfish and scallops) | Research into 2 SA aquaculture species (ﬁnﬁsh and scallops) | Inadequate capacity | Partnership with Universities. |
| SG2;SO 2: Ensure the sustainable management and efficient use of natural resources | Promote the equitable and sustainable management and efficient use of marine living resources | % of commercial ﬁshing right holders per cluster who have had their performance reviewed | Work plan finalised and key performance indicators drafted for fishery performance reviews | 70 % of the ﬁsheries reviewed by cluster | Time frame for finalization of project. Additional costs involved. | DG approval |
|  |  | 100 % of commercial rights transfer applications processed within speciﬁed service standards | Draft policy on transfer of commercial fishing rights published | Finalise policy on commercial rights transfer and applications processed | Implementation of the policy. Limited capacity | Employ more skilled personnel. |
|  | Rebuild depleted ﬁsh stocks | Extent of recovery of hake and abalone, West Coast Rock Lobster and lineﬁsh | Strategy in place for abalone and hake | Continuous review of strategy for hake and abalone in respect of research, management and compliance | Cross cutting activities. | Commitment required from partners in respect of the National Integrated Security Strategy( NISS) for the abalone and the approval of the Standard operating procedures. Partners in terms of the NISS were engaged and Standard Operating Procedures (SOP’s) updated. Monitoring Control and Surveillance should champion the target. |
|  | Compliance with and enforcement of marine and coastal legislation | % of ﬁsh processing establishments inspected | Rudimentary operational data | 40 % of ﬁsh processing establishments inspected | Internal communication | The definition of Fish processing Establishments under the MLRFA and the increase of human capacity. The legal definition of FPE’s is being addressed. Capacity is addressed by the appointment of external services providers. Provide more training to staff in harbors. Improve facilities |
|  |  | % of rights holders investigated in 5 key ﬁsheries sectors |  | 10 % of rights holders in the 5 key ﬁsheries investigated | Investigation and registering of cases | Investigative Capacity. Regional offices extended to the Eastern Cape. Successful prosecution and implementation. |
|  |  | % of vessels inspected in the 5 key ﬁsheries |  | 15 % of vessels inspected in the 5 key ﬁsheries sectors | The monitoring of line fish vessels and the record keeping at slipways of the number of line fishing vessels. | Budgetary constraints and adverse weather has had an impact on inspections at sea in the 5 keys fisheries sectors. OCFO is engaging Treasury for vessels operating |
|  |  | Percentage of cases and tip-offs investigated according to service standards | Limited investigation capacity and no service standards in place | 75 % of cases and tip-offs investigated according to services standards | Cases pending in court and further operations | Challenges include the extensive period for finalizing criminal cases budgetary constraints and the deployment of technological investigative instruments. Responses include sensitizing cases, forfeiting gear and Vessels. Successful prosecution. |
|  |  | Number of joint partnerships with law enforcement and conservation agencies established | 5 partnerships | Maintain and strengthen 5 partnerships | Engagements | Commitment from stakeholders and partners on operational and administrative levels. Actions taken include sensitizing and engaging stakeholders and partners. Continuous engagements |

# RECOMMENDATIONS

The following are recommended based on the report:

- The programme has to make a formal submission to the Directorate: Strategic Planning regarding deliverables that were transferred to DEA for them to follow due processes of amending to strategic plan. This will prevent  audit queries

- Detailed reporting on milestones achieved per deliverable advised. Reports should be based on the targets.

- It is important to highlight challenges and corrective measures where there is under performance.

- Any deviation from the strategic plan be it under performance of performance above target should be explained.

# OVERALL ORGANISATIONAL ANALYSIS

# Based on the information above, progress has been made towards the achievement of the strategic outcomes for the various programmes as compared to the previous quarter. However the following must be highlighted:

# The current DAFF structure in operation is not aligned to Part four and five of the 2010/11 strategic plan and this is still causing some confusion.

# The unavailability of performance information by certain sub-programmes still persists and we would need to work on this.

# It is difficult to confirm the actual performance due to a lack of supporting evidence to validate and substantiate the actual performance reported by programmes therefore.

# There are difficulties experienced in tracking the progress made due to a lack of specific time frame.

# The confirmation of the annual performance plans by various directorates is currently on going and will be finalised before the end of the third quarter, and that will make it easier to track the performance of the programme against its predetermined milestones. Reporting against annual performance plans will be reported on the next quarter.

# RECOMMENDATIONS

- The structure of the department needs to be finalized.

- Placements into the new structure to be completed as to identify responsible people who will start reporting on their targets.