SOUTH AFRICAN COUNCIL FOR EDUCATORS

OPERATIONAL PLAN

2011/12

THE SOUTH AFRICAN COUNCIL FOR EDUCATORS

STRATEGIC OVERVIEW

The South African Council for Educators (SACE) is a professional council that has been established in terms of the SACE Act no.31 of 2000. In addition, the National Policy Framework on Teacher Education and Development (2007) mandate SACE to manage and implement the Continuing Professional Teacher Development (CPTD) system. SACE’s goals are first to regulate the teaching profession by developing and maintaining standards of entry into the profession; managing a register of professionally qualified teachers; and managing the code of professional ethics, complaints and discipline within the profession. Furthermore it develops the profession through managing and implementing the CPTD system, identifying needs of the teaching profession, promoting teaching as a profession, setting and monitoring standards of teacher education and development, and advising the Ministers of Education. In realising its mandate and goals it needs to work collaboratively with the Ministry of Basic Education and other Education stakeholder in achieving government’s outcome number one – Quality Basic Education.

2011/2012 DIVISIONAL OPERATIONAL PLAN

# Programme 1:		Registration (R1,200,000)

| Sub-Programme: Registration of Educators |  |  |
| --- | --- | --- |
| Strategic Objectives | Performance Measures and Targets | Activities | Responsibility | Timeframes / Target Date | Performance Indicators | Budget |
| To facilitate the registration of all practicing and non-practicing educators | Report on cleaned register is available. |  | Registration |  | The main register is current and has professionally qualified practicing and non-practicing educators | R320 000 |
|  | 100% of the practicing educators are registered. |  | Registration with the support of Communication. |  | All unregistered practicing educators are identified and registered | R480 000 |
|  | Sub registers concept paper available and approved. |  | Registration with the support of Policy and Research Coordination. |  | The new sub-registers are introduced to the profession and included in the SACE Act amendment processes |  |
|  | Quarterly reports on registration six weeks turn around time are produced. |  | Registration with the support of Corporate Services and Finance. |  | Registration applications received by SACE are processed and certificated posted within six weeks |  |
|  | Reviewed registration criteria available and approved. |  | Registration with the support of Policy and Research Coordination. |  | Revised registration criteria and procedures that provides clear guidance to the registration of South African and foreign educators, and registration of educators in the new sub-registers. |  |
|  | Annual Registration statistical document available and approved. |  | Registration with the support of Policy and Research Coordination. |  | Annual Registration Statistical Report produced in terms of various variables . |  |
| Sub-Programme: Sectoral Registration |
|  | Performance Measures and Targets | Activities | Responsibility | Timeframes / Target Date | Performance Indicators | Budget |
|  | Review of current Sectoral registration types and proposals for new types submitted for discussion and implementation. Concept paper Approval Pilot Implement | Discussions into the industry changes and research into future impact with SACE operations and criteria. Analysis into current structure and changes required for amended Sectoral registrations. | Registration Manager | 30 MARCH 2011 First quarter report to REGCO for 2011/12 financial year | Review of current industry trends and demands as well as support of the evaluations framework and Research Division. |  |
|  | Target future registration mandates for increasing scope of SACE Mandates and industry responsibilities Based. | Research the needs of the industry as well as allow for external recommendations to broaden SACE scope and allow for further registration types to be introduced. Full assistance and approval required from REGCO | Registration Manager | 30 MARCH 2011 First quarter report to REGCO for 2011/12 financial year | Recommendations to REGCO for review, approval of piloting and implementation programme. Concept paper drafted. |  |
| Sub-Programme: Electronic Registration |  |
|  | Performance Measures and Targets | Activities | Responsibility | Timeframes / Target Date | Performance Indicators | Budget |
|  | Implement review of current objectives and demands for implementation of Online Registration project. | Discussions and research into implementation of the Electronic Registration system and logistics involved including costs. Concept paper required. | Registration | 30 MARCH 2011 Discussions and investigations into implementation and costs conducted with all parties input. | Report presented to Council for approval and clear project for assessment, piloting and research, and implementation. | R400 000 |
| Sub-Programme: Standards of Entry into the Profession |
|  | Performance Measures and Targets | Activities | Responsibility | Timeframes / Target Date | Performance Indicators | Budget |
|  | Review of current Minimum registration requirements and industry demands as well as standard entry level for employment within industry. | Discussions into the industry changes and research into future impact with SACE operations and criteria. Analysis into current structure and changes required for amended minimum entry levels for registrations. | Registration Manager | 30 MARCH 2012 Begin meetings and discussions for review paper and draft possible timeframes. | The new minimum entry level of industry standards reviewed and implemented, and introduced to the profession and included in the SACE Act amendment processes | 0 |

# Programme 2: Professional Development

| Sub-Programme: CPTD System |  |  |
| --- | --- | --- |
| Strategic Objectives | Performance Measures and Targets | Activities | Responsibility | Timeframes / Target Date | Performance Indicators | Budget |
| To enhance the quality of the practicing educators through the management of the CPTD System | The CPTD System pilot is implemented effectively in 144 schools across the 9 provinces. Evaluation and Endorsement processes are tested | Implementation of the CPTD Pilot Finalisation of policy documents and relevant forms Regular CPTD Task team meetings.(10 meetings per annum) Update and support to pilot structures and pilot schools Monitoring of Provinces (PPCC’s) activities.(once a month) Regular Endorsement committee meetings(6 meetings pre annum) Evaluation and Endorsement of activities(100 activities) | CPTD Unit in collaboration with Provincial Education departments, CPTD Task Team and the support of Policy and Research Coordination | March 2011 Ongoing | Pilot report is available with recommendations Minutes of the Endorsement committee meetings, and records of endorsed activities after every EC meeting | R800 000 |
| Operationalisation of CPTD Information System | CPTD Information System is live and used by pilot schools effectively. | Correct the bugs/inefficiencies on the CPTD IS- system The CPTD ICT System goes live. Conduct and invite educators in the pilot schools to sign-up (electronically and manually) Capture on 6000 educators and their record of PD points, Manage queries Keep up to date database of 250 endorsed CPTD activities and 150 Providers | CPTD Unit in collaboration with Provincial Education departments, CPTD Task Team and the support of Policy and Research Coordination | December 2010 Ongoing |  | R255 000.00 |
| Re-establishment of the Provider/ Endorsement Support Unit |  |  |  |  |  |  |
|  | Pilot monitoring and Evaluation report available | Develop an instrument for: Monitoring and evaluation of the pilot. Conduct monitoring of a sample of pilot schools Assign evaluators to Conduct site visits. Provider support to pilot schools | CPTD Unit in collaboration with Policy and Research Coordination | July 2011 | Pilot monitoring and Evaluation report available | R70 000 |
| Sub-Programme: Educator Professional Assistance Facility |  |
| Strategic Objectives | Performance Measures and Targets | Activities | Responsibility | Timeframes / Target Date | Performance Indicators | Budget |
| Sub-Programme: Induction and Professional Designation |  |  |  |
| Strategic Objectives | Performance Measures and Targets | Activities | Responsibility | Timeframes / Target Date | Performance Indicators | Budget |
| To develop programmes to improve and maintain the status and image of the teaching profession | Professional Designation and Induction concept document developed | .Develop concept document on Induction. Develop concept document on Professional Designation. Develop concept document on Full Registration. Advocacy to stakeholders and presentation to Council. | CPTD Unit with the support of Policy and Research Coordination | April 2011 | Induction, Professional Designation, and full registration concept approved by Council and stakeholders in the teaching profession | R90 000 R70 000 R90 000 |
| Sub-Programme : Teacher Recruitment and Retention |  |  |
| Strategic Objectives | Performance Measures and Targets | Activities | Responsibility | Timeframes / Target Date | Performance Indicators | Budget |
| To promote teaching as a career of first choice | Teacher recruitment and retention programme and campaign are approved | Development of the teacher recruitment and retention programme and campaign | Professional Development with the support of Policy Planning and Research Coordination and Communications and Advocacy | March 2011 | More young people join the teaching profession and teachers remain in the profession | R45 000 |
| Sub-Programme: Professional Practice and Development Standards |  |  |
| Strategic Objectives | Performance Measures and Targets | Activities | Responsibility | Timeframes / Target Date | Performance Indicators | Budget |
| To facilitate processes of ensuring that more and better teachers join the teaching profession | Professional practice and Professional development standards document developed and approved by Council. | Develop Professional development and practice standards document. Consult with all relevant Stakeholders. | Professional Development with the support of Policy Planning and Research Coordination | March 2011 | Consultation process on the standards takes place with all the relevant stakeholders | R70 000 R60 000 |
| Sub-Programme: Celebration of Teachers and the Profession |  |  |  |  |  |  |
| Strategic Objectives | Performance Measures and Targets | Activities | Responsibility | Timeframes / Target Date | Performance Indicators | Budget |
| To ensure that effective programmes and strategies of celebrating teachers and the profession are in place. | Two Programmes of celebrating teachers and the profession is in place. Focus on the month of October as a recognised Teachers month. | Organize a National event celebrating and honouring about 1200 teachers( on behalf of all teachers) Develop brochures and flyers to publicize the message of honoring teachers | Professional development | March 2011 | The profession is celebrated on an ongoing basis with special focus on the month of October | R600 000.00 |

# Programme 3: Policy Planning and Research Coordination (R1,200,000)

| Sub-Programme: Policy Matters |  |  |
| --- | --- | --- |
| Strategic Objectives | Performance Measures and Targets | Activities | Responsibility | Timeframes / Target Date | Performance Indicators | Budget |
| To coordinate SACE policy matters and contribute to the national policy debates and legislation | Reviewed and Updated SACE policies available | Assist the SACE Divisions and Council in developing and reviewing internal policies on an ongoing basis | Policy Planning and Research Coordination in collaboration with Divisions | Ongoing | SACE has well developed and updated policies that guide the implementation of programmes, projects, and interventions | R10 000,00 |
|  | Minimum of three policy submissions (per annum) on various professional matters are available and presented to Council and the relevant sub-structures | Make ongoing written and verbal SACE policy submissions to the Departments of Education, and other relevant bodies and structures on various professional matters | Policy Planning and Research Coordination | Ongoing | SACE is visible in influencing and / or informing national policy issues. | R0 000,00 |
|  | Ongoing policy advice provided to the Ministers of Education, Council, SACE Divisions, and the Profession . | Provide policy advice services to SACE Divisions, Council, and Ministers of Education. | Policy Planning and Research Coordination. | Ongoing | Minimum of three policy advices are done per annum. | R50 000,00 |
|  | Report on SACE participation in national policy making and implementation structures and bodies. | Participate in various educational policy making and implementation structures at various levels in order to act as the voice of the profession. | Policy Planning and Research Coordination. | Ongoing | SACE is visible in informing national policy making and implementation processes through int participation in various policy structures. | R10 000,00 |
| SUB-TOTAL |  |  |  |  |  | R70 000,00 |
| Sub-Programme: Planning |
| Strategic Objectives | Performance Measures and Targets | Activities | Responsibility | Timeframes / Target Date | Performance Indicators | Budget |
| To ensure that SACE engages in medium and long-term planning that is informed by sound research and information | Reviewed document on SACE’s roles, scope and functions document. | Review SACE’s redefined role, scope, and functions document. | Policy Planning and Research Coordination. | November 2011 | The redefined roles, scope, and functions document provides direction in terms of governance and administrative implementation matters. | R0 000,00 |
|  | 2012/2013 Annual Performance Plans developed and in place. | Develop draft strategic plan, present it to Council for inputs and approval. | Policy Planning and Research Coordination. | January 2012 | The three year strategic plan provides direction in managing, implementing, and periodically monitoring the strategic issues against the plan’s targets. | R20 000,00 |
|  | The 2012/2013 Divisional operational plans are developed and approved. | Assist the Divisions in developing operational plans for presentation to sub-committees and Council | Policy Planning and Research Coordination with the support of all Divisions. | January 2012 | Divisional Programmes are implemented and monitored periodically in line with the developed operational plans’ performance targets. | R20 000,00 |
|  | SACE annual statistics document is publicized. | Coordinate statistical data from registration, ethics, and CPTD-IS to develop and distribute the SACE statistics Annual Publication | Policy Planning and Research Coordination with the support of Registration, Professional Development, and Ethics. | March 2012 | The publicized statistics document is used to inform SACE planning and Council decisions, and advice the Ministers of Education, Council and the profession. | R300 000,00 |
| SUB-TOTAL |  |  |  |  |  | R340 000,00 |
| Sub-Programme: Research Coordination |
| Strategic Objectives | Performance Measures and Targets | Activities | Responsibility | Timeframes / Target Date | Performance Indicators | Budget |
| To promote and undertake research on professional matters for purposes of informing and advising the Ministers of Education, Council, SACE Divisions, and the teaching profession | Research policy and plan implemented | Develop the research plan for 2011/2012 | Policy Planning and Research Coordination | April 2011 | Research projects and programmes implemented in line with the research policy and plan | R0 000,00 |
|  | Research partnerships and networks are in place | Establish national and international research partnerships and networks | Policy Planning and Research Coordination | Ongoing | SACE collaborates with other national and international bodies / organizations on professional matters and research | R10 000,00 |
|  | Research Reports available and findings presented to Council | Conduct research on three focus areas in line with SACE research priorities | Policy Planning and Research Coordination | Ongoing | Research findings publicized | R300 000,00 |
|  | Research advisory services provided to the Ministers of Education, Council, SACE Divisions, and the profession | Use the research findings for advisory purposes | Policy Planning and Research Coordination | Ongoing | Research findings used to inform and advice Council, SACE Divisions, Education Ministers, and the profession | R30 000,00 |
|  | Concept paper on practitioner-based research is available and approved | Develop practitioner – based research concept | Policy Planning and Research Coordination | March 2011 | Practitioner – based research programme developed in line with the approved concept paper | R30 000,00 |
| SUB-TOTAL |  |  |  |  |  | R370 000,00 |
| Sub-Programme : Monitoring and Evaluation |
| Strategic Objectives | Performance Measures and Targets | Activities | Responsibility | Timeframes / Target Date | Performance Indicators | Budget |
| To promote and undertake the monitoring and evaluation of SACE programmes and strategic issues. | The Monitoring and evaluation framework and instruments are available and approved. | Engage in a process of developing the monitoring and evaluation framework for the purpose of monitoring and evaluating the planning and implementation of SACE programmes and projects on an ongoing basis. | Policy Planning and Research Coordination. | July 2011 | Programmes and projects are monitored and evaluated on an ongoing basis using the monitoring and evaluation framework and instruments. | R30 000,00 |
|  | Programmes and Projects Monitoring and Evaluation reports are available and presented to sub-structures and Council. | Engage in an ongoing process of monitoring and evaluating SACE. | Policy Planning and Research Coordination. | Ongoing | Programmes and projects are monitored and evaluated on an ongoing basis and the reports are used to improve and adjust implementation processes. | R30 000,00 |
| SUB-TOTAL |  |  |  |  |  | R60 000,00 |
| Sub-Programme: Research Reports and Publications |  |  |  |  |  |  |
| Strategic Objectives | Performance Measures and Targets | Activities | Responsibility | Timeframes / Target Date | Performance Indicators | Budget |
| To communicate and disseminate research findings and produce publications on professional matters. | Strategy and plans to publicise and disseminate research findings are in place. | Develop research publicity and dissemination strategy and plans. | Policy Planning and Research Coordination with the support of Communication. | June 2011 | Strategy and plans are implemented and guide the dissemination of research findings. | R45 000,00 |
|  | Professional Magazine is developed and disseminated to teachers. | Coordinate the writing, editing and distribution of articles for the professional magazine. | Policy Planning and Research Coordination with the support of Communication. | August 2011 | 30 000 schools and educational institutions receive the magazine and are informed of topical professional matters through the professional magazine. | R300 00,00 |
| SUB-TOTAL |  |  |  |  |  | R345 000,00 |
| Sub-Programme: Resource Centre |  |
| Strategic Objectives | Performance Measures and Targets | Activities | Responsibility | Timeframes / Target Date | Performance Indicators | Budget |
| To conceptualize and implement the resource centre services | Resource Centre Concept and Policy are available and approved. | Develop the Resource Centre concept paper and policy . | Policy Planning and Research Coordination. | August 2011 | The Resource Centre operates according to the approved concept paper and policy | R20 000,00 |
|  | Report on the ordered and classified material is available. | Order and subscribe to various material and equipments for the Resource Centre. | Policy Planning and Research Coordination. | October 2011 | Resource Centre material is classified accordingly | R80 000,00 |
| SUB-TOTAL |  |  |  |  |  | R100 000,00 |

Programme 4: Ethics

| Sub-Programme: Standards of Professional Ethics |
| --- |
| Strategic Objective | Performance Measures and Targets | Activities | Responsibility | Timeframes / Target Date | Performance Indicators | Budget |
| To set, promote, maintain and instill good ethical values and standards among educators. | Interaction with educators, learners, parents, social services, CPU, SAPS and other stakeholders. 2011/2012 ensure that at least 30% of educators have been taken through workshops regarding the code. Development of skills for the Panelists; Investigators; Prosecutors and Chairpersons. Counseling for the Victims; Panelists; Prosecutors and Chairpersons | Conduct workshops, seminars, meetings, Imbizos and trainings | Ethics | Quarterly reports submitted | Evaluation forms, Attendance register and questionnaires | R370 000.00 |
| Sub-Programme: Managing Cases |
| Strategic Objectives | Performance Measures and Targets | Activities | Responsibility | Timeframes / Target Date | Performance Indicators | Budget |
| Investigation of complaints and mediation. | Conduct offsite recorded telephonic investigation and on site investigations. Ensure that 70% of on and offsite investigations are conducted and finalised by 30 March 2012 | Open a file within 48 hours of receipt of a complaint Acknowledge receipt of complaint within 48 hours Send out an audi letter calling for a response within 7days If a response is received, prepare recommendation If no response after 7days, prepare recommendation Refer recommendations to ETHCOM for consideration and instruction Forward advise to Council for noting and ratification Execution of the ETHCOM instruction | Ethics Ethics Ethics Ethics Ethics Ethics Ethics Ethics | Ongoing with monthly reports. | Complaint File Communication letters to parties Recommendations to ETHCOM Investigation reports for ETHCOM Instructions from ETHCOM | R245 000.00 |
| Conduct of Disciplinary Hearings | Ensure that 60% of disciplinary hearings have been conducted and finalized by 30 March 2012 | Identify a venue for the hearing Issue summons against an accused educator Subpoena witnesses to testify Appoint a disciplinary panel Conduct the hearing Adjudication of Appeals | Ethics | Ongoing with monthly reports | Conduct at least 12 hearings per month | R785 000.00 |
| Sub-Programme: Educator and School Support | Performance Measures and Targets | Activities | Responsibility | Timeframes/Target Date | Performance Indicators | Budget |
| Review of the Code and Ethics | Ensure that the code of professional ethics and disciplinary procedures are reviewed on an annual basis | Ensure that 100% of teachers sanctioned by Council attend to programmes recommended by Council and submitted proof to Council | Ethics | Ongoing with monthly reports | Ensure that all educators sanctioned to attend courses or programmes attend the programmes, complete them and submit proof of attendance Ensure prompt attendance to the school making requests for workshops on the Code of Conduct. | NIL |

Programme 5: Communication (R1,900,000)

SUB-PROGRAMME 1

NATIONAL AND INTERNATIONAL RELATIONS

| Strategic Objectives | Performance Measures and Targets | Activity | Responsibility | Timeframes / Target Date | Performance Indicators | Budget |
| --- | --- | --- | --- | --- | --- | --- |
| Network and on-going relations with National and International stakeholders, professional Councils and other relevant organization are established | Develop national stakeholder plan and strategy | The Strategy and Plan developed and finalized. | Communications | April 2011 | National strategy and plan developed and implemented. | - |
|  | Develop international stakeholder plan and strategy | Develop international stakeholder plan and strategy | Communications | April 2011 | International strategy and plan developed and implemented | - |
|  |  | Hosting of the International conference: Conference peparations, losgistics, identifying of venue, develop confrence porogramme. Media plan. | Communications | July 2011 | IFTRA Conference hosted | R 650 000 |
|  | Meeting with national Union leaders. | At least hold two meetings with each union in a financial year. | Communications | May 2011 February 2012 | Develop a needs analysis stakeholder report on a quarterly basis | R 100 000 |
|  |  | Publish SACE e-news bulletin for unions. | Communications | June 2011 September 2011 December 2011 March 2012 | E-news bulletin is published and distributed (quarterly) | - |
|  | Showcase the services and work of SACE to stakeholders. | Conduct 18 exhibitions at regional/provincial teacher union conferences | Communications | May 2011- October 2011 | Report on impact of this on the SACE brand | R 110-000 |

SUB-PROGRAMME 2

MEDIA RELATIONS

| Strategic Objectives | Performance Measures and Targets | Activity | Responsibility | Timeframes / Target Date | Performance Indicators | Budget |
| --- | --- | --- | --- | --- | --- | --- |
| Restore brand credibility and build image of trust and confidence. | Establish a strong relationship with media houses. | Hold one-on-one meetings with journalists from the following newspapers: Sowetan Star Beeld City Press | Communications | June/July 2011 | Improve good working relations with the media. | R 20 000 |
|  |  | Publlicise SACE programmes, services | Communications | April 2011 June 2011 September 2011 March 2012 | Issue 8 media statements | - |
|  |  |  |  | April 2011 | Compilation of quarterly media monitoring report and visibility of SACE in the media | R220 000 |

SUBPROGRAMME 3   MEDIA PRODUCTION AND PUBLICATIONS

| Strategic Objectives | Performance Measures and Targets | Activity | Responsibility | Timeframes / Target Date | Performance Indicators | Budget |
| --- | --- | --- | --- | --- | --- | --- |
| Production of publications. | Develop educational and informative materials (publications) about SACE | Produce at least 3 publications on SACE External Newsletter PFMA Annual Report | Communications | April 2011 May 2011 August 2011 | All publications are produced and distributed | R 280 000 R 120 000 |

SUB-PROGRAMME 4

WEBSITE MANAGEMENT

| Strategic Objectives | Performance Measures and Targets | Activity | Responsibility | Timeframes / Target Date | Performance Indicators | Budget |
| --- | --- | --- | --- | --- | --- | --- |
| To Update and improve the website.. | Re- design a user friendly website that offers comprehensive information. | Appointment of a dedicated webmaster. | Communications | April 2011 | User-friendly website is developed. | R 1 20 000 |
|  |  | Place information on the website. Respond to website queries on a daily basis | Communications Communications | Monthly Ongoing | Record and give reports on monthly hits to determine the most needed information and trends | - - |

SUB-PROGRAMME 5  CALL CENTRE MANAGEMENT

| Strategic Objectives | Performance Measures and Targets | Activity | Responsibility | Timeframes / Target Date | Performance Indicators | Budget |
| --- | --- | --- | --- | --- | --- | --- |
| Report on inflow of calls and educator’s feedback | Ensure that call centre is run efficiently. | Review call centre systems to ensure ease of access for customers. | Communications | April | SACE offices are easily accessible – increased number of incoming calls. | R100 000 |
|  |  | Closely monitor performance at the call centre to ensure adherence to customer service standards | Communications | June 2011 September 2011 December 2011 March 2012 | Reduced number of complaints by callers reports on the number of queries kept | - |

SUB-PROGRAMME 6 INTERNAL COMMUNICATION

| Strategic Objectives | Performance Measures and Targets | Activity | Responsibility | Timeframes / Target Date | Performance Indicators | Budget |
| --- | --- | --- | --- | --- | --- | --- |
| Regular communication with staff through e-mails, news letters and memos. | Inform and update staff on all developments and initiatives. | Four (4) internal newsletters produced quarterly. Disseminate corporate messages (at least 2 messages on a monthly basis) | Communications | June 2011 September 2011 December 2011 March 2012 Ongoing | Staff members are informed about the SACE | - |

SUBPROGRAMME 7 MARKETING AND ADVERTISING

| Strategic Objectives | Performance Measures and Targets | Activity | Responsibility | Timeframes / Target Date | Performance Indicators | Budget |
| --- | --- | --- | --- | --- | --- | --- |
| Improving the image and maximising the SACE brand | Develop marketing strategy of SACE by April 2011 | Develop marketing strategy of SACE. | Communications | April 2011 | Strategy developed and implemented | - |
|  | Viral advertising Producing SACE Promotional materials | The use of viral messages as a strip on all staff and councilors’ E-mails. Procurement of the following items : SACE diary | Communications Communication | August 2011 January 2012 September/October 2011 | World Teacher’s Day is publicised through virall advertising. Identified promotional materials procured and distributed. | - R 80 000 |

Programme 6: Corporate Services

| Sub-Programme: Human Resource Management and Development |  |
| --- | --- |
| Strategic Objectives | Performance Measures and Targets | Activities | Responsibility | Timeframes / Target Date | Performance Indicators | Budget |
| To provide and Strengthen the management and development of the SACE human capital | Achieve a 100% identification of skills gaps through the use of a performance development plan. | Assess the prior year’s performance assessment from managers | Corporate services | End of April 2011 | Skills gap identified | Not applicable |
|  | Implement at least 80% of training and development interventions in line with the SACE needs. | Implement the prior year’s performance assessment recommendations from managers | Corporate services | End of June 2011 | Trained staff in line with SACE needs | R 280 000 |
|  | Monitor at least 90% of the performance development system assessment to ensure that personnel meet targets. | Monitor quarterly performance reports from divisional managers | Corporate services | Quarterly | Personnel development targets met | Not applicable |
|  | Resolve all grievances raised by staff. | Ensure that mediation processes are attended on a quarterly basis. | Corporate services | On going | Resolved grievances | Not applicable |
|  | Revise all policies and procedures in line with HR best practices. | Review and update the human resource policy and procedure | Corporate services | On going | Revised policies and procedure manual. | Not applicable |
|  | Ensure that all managers consistently apply and follow up on the individual development action plan | Monitor the staff development plan | Corporate services | On going | Developed staff in line with the plan | Not applicable |
|  | Recruit and appoint skilled personnel to fill vacancies | Recruit and appoint in line with Council mandates | Corporate services | On going | Appointed skilled staff | Not applicable |
| Sub-Programme: Secretariat Services, Registry and Postal services |  |
| Strategic Objectives | Performance Measures and Targets | Activities | Responsibility | Timeframes / Target Date | Performance Indicators | Budget |
| To Ensure effective and efficient administration systems and processes | Setting up a registry and archives. | Develop registry and archives policy. Establishing the registry and archives section | Corporate services | End of May 2011 | Developed policy | Not applicable |
|  | Development of meeting procedures document. | Development of policy and procedure manual for council | Corporate services | End of June 2011 | Developed procedure | Not applicable |
| Sub-Programme: Procurement Services |  |
| Strategic Objectives | Performance Measures and Targets |  | Responsibility | Timeframes / Target Date | Performance Indicators | Budget |
| To provide transparent ;cost effective and efficient procurement services | Reviewal of procurement policies and procedures. | Review and update the Supply chain and procurement policy | Corporate services | End of June 2011 | Reviewed policy | Not applicable |
|  | Ensure unqualified audit report on compliance to policies and procedures | Implement and comply with the policies and procedures | Corporate services | On going | Unqualified report | Not applicable |
|  | Compile annual procurement plan. | Consolidate divisional procurement plan | Corporate services | End of April 2011 | Compiled plan | Not applicable |
|  | Ensure that SACE assets are secured and operational. | Review insurance policies Review and update the asset register Develop internal control procedure manual | Corporate services | On going | Reviewed insurance policy Updated asset register Internal control document | R 460 000 |
| Sub-Programme: Information and Communication Technology |  |
| Strategic Objectives | Performance Measures and Targets |  | Responsibility | Timeframes / Target Date | Performance Indicators | Budget |
| To ensure reliable; up to date and stable IT environment | Provision of a reliable accessible and stable technology environment. | Continuously update the information technology environment | Corporate services | On going | Stable and accessible information technology environment | R 600 000 |
|  | Review and update IT policies | Review and update IT policies | Corporate services | End of June 2011 | Reviewed policy | Not applicable |
|  | Completion of SACE Integrated IT solution. | Review and update the Integrated IT solution and enhancements | Corporate services | End of September 2011 | Integrated IT solution | Not applicable |
|  | Monitor security system on monthly basis to ensure that the security provide a safe environment for IT systems. | Monthly monitoring of security systems | Corporate services | On going | Safe IT environment | Not applicable |
|  | Review and update the IT architectural framework annually to ensure strategic alignment to SACE’s mission and objectives. | Review and update the IT architectural framework annually to ensure strategic alignment to SACE’s mission and objectives. | Corporate services | On going | Reviewed IT architectural framework | Not applicable |
| Sub-Programme: Council office accomodation |  |
| Strategic Objectives | Performance Measures and Targets |  | Responsibility | Timeframes / Target Date | Performance Indicators | Budget |
| To ensure acquisition of an equitable and accessible permanent building for Sace | Office building | Planning and construction of the building | Corporate services and finance | On going | Completed office building | R 13 104 000 |
| Sub-Programme: Financial Administration |  |
| Strategic Objectives | Performance Measures and Targets | Activities | Responsibility | Timeframes / Target Date | Performance Indicators | Budget |
| To ensure effective and efficient Financial Administration of council | Prepare a three year budget for strategic plan | Timely preparation of three year budget for strategic plan | Finance and Research | Before 31 August | Prepared three year budget and budget approval by the Minister of basic education | Not applicable |
|  | Review of financial policies and procedures | Annual review of financial policies and procedure manual Follow-up on audit findings regarding policy gaps Align financial policies with PFMA, Accounting Standards changes and SARS changes | Finance | First quarter of the financial year ending 30-04-11 July 2011 First quarter of the financial year ending 30-04-11 | Council approval of the financial policies and procedure manual Aligned policies to the statutory changes | Not applicable |
|  | Maintain a positive cash flow at all times | Preparation of monthly cash flow projections | Finance | Monthly | Prepared cash flow projections | Not applicable |
|  | Produce monthly and quarterly accurate financial report | Preparation of monthly financial reports to management Preparation of monthly budget report to management Preparation of quarterly financial report to FINCO, Council and DoBE | Finance | Ten days after month end Ten days after month end Fifteen days after the end of the quarter | Monthly financial report submitted to management Actual expenditure VS budget statement submitted to management Income and Expenditure VS Budget statement submitted to FINCO and Council Financial reports submitted to FINCO, Council and DoBE | Not applicable |
|  | Secure additional funding for specific projects | Revise the funding strategy | Finance and communication division | Before end of June 2011 | Revised funding strategy submitted to FINCO | Not applicable |
|  | Receive an unqualified audit report | Timely preparation of audit packs Ensuring that performance information is available | Executive, CFO, Finance | Before the 30th April 2012 Before the 30th April 2012 | Audit packs submitted to Auditors before the 30th April 2012. Performance information submitted to the Auditors before 30th April 2012. | Not applicable |