STATUS REPORT AND OUTCOMES OF THE 2011 TRADE AND INDUSTRY WORKPLAN

| Issue | Completed | Not Completed |
| --- | --- | --- |
| Legislation: Bills referred in 2010 Intellectual Property Laws A/B | The Intellectual Property Laws A/B was redrafted and the Committee’s process was finalised by in September 2011. The report of the Committee was only adopted in October 2011. This is currently being processed by the National Council of Provinces. |  |
| Expected Legislation 2011/12 Cooperatives Amendment Bill (June 2011) Estate Agents Amendment Bill (introduction date pending consultation between Ministers of Human Settlements and Trade and Industry) National Credit Amendment Bill (September 2011) Broad-based Black Economic Empowerment (BBBEE) Amendment Bill (September 2011) Lotteries Amendment Bill (August 2011) Final Regulations for Companies and Consumer Protection Acts (April 2011) Regulations for Public Preferential Procurement Framework Act (PPPFA) | The Companies and Consumer Protection Regulations were tabled in Parliament. The Committee received a briefing from the Consumer and Corporate Regulation Division in this regard. The Committee noted that the amendments to the Preferential Public Procurement Framework Act’s regulations have been finalised and gazetted to align these with Broad-based Black Economic Empowerment (BBBEE) imperatives. | None of the expected amendment legislation has been tabled in Parliament as yet. |
| Oversight visit to Northern Cape and Gauteng | The Committee conducted its oversight visit in July 2011. It performed oversight over the newly established National Consumer Commission and Companies and Intellectual Property Commission. Furthermore, it undertook visits to ArcelorMittal South Africa and Kumba Iron Ore Ltd. | The Committee had planned to do a second oversight visit. However, due to legislative pressures, it may not be able to meet this objective. |
| Budget Vote and Strategic Plan | The Committee held briefings on the DTI’s strategic plan and its budget vote. It had also requested the DTI to submit an annual business plan to assist more accurate monitoring and evaluation of the DTI’s quarterly financial and non-financial performance. The Committee adopted its Budget Vote Report on 14 April 2011. |  |
| Budget Review and Recommendation Report (BRRR) and Annual Report | The Committee completed its BRRR. As part of this process, it considered the Department of Trade and Industry’s annual report, as well as the South African Bureau of Standards and the National Regulator of Compulsory Specifications’ annual reports. Furthermore, it focused on challenges experienced by the National Consumer Commission and the National Credit Regulator. | However, there is a need to monitor the DTI’s and possibly selected entities’ quarterly performance. |
| Industrial Policy Action Plan (IPAP2) | Finalisation of Steel Report: The Steel Report was finalised and adopted by the Committee on 24 September 2011, after the oversight visit to ArcelorMittal SA and Kumba Iron Ore in July 2011. Banking sector’s role in providing access to finance: The Committee undertook public hearings in the Sedibeng District Municipality during its July oversight visit to Gauteng on the financing of business to promote industrial and small business development. The Committee had engagements with the Banking Association of South Africa, the Industrial Development Corporation, National Empowerment Fund and Khula Enterprise Finance on their contributions. | Two Progress Reports: The Committee has received the annual report for progress report on IPAP2 as part of its Budget Review and Recommendation Process. However, it has not had an in-depth briefing on the matter since 22 March 2011. Inter-departmental report on steel: The Committee is awaiting this report. Update on status of the National Industrial Participation Programme (NIPP) commitments and alignment with IPAP2: The Committee had received an overview of the status of NIPP during the briefing on the DTI’s Annual Report. However, a more detailed report was requested. |
| International Trade and Regional Integration | Regional Integration: The Minister briefed the Committee on recent developments of the COMESA-EAC-SADC Tri-partite Free Trade Agreement in June 2011. Two Members of the Committee attended the SACU Regional Conference held in Gauteng in July 2011. International Trade Relations: The DDG of ITED briefed the Committee on relations with IBSA, BRICS and the European Union in April 2011. | Bilateral Investment Treaties: No progress was made in this regard. |
| Incentive Schemes | The Committee has engaged with The Enterprise Organisation during its Northern Cape visit, and for follow-up meetings in October and November 2011. |  |
| Gambling |  | The Gambling Review Commission’s Report has been tabled in Parliament. The Committee has established a working group to guide the Committee on the issues arising from this report. A call for public submissions was made and subsequently public hearings were held from 28 October and public engagement is on-going. |
| Broad-based Black Economic Empowerment |  | The Committee has planned to assess the development, implementation and impact of BEE Charters during the 2011/12 financial year. in addition, it had intended for the Empowerment and Economic Development Division to present training on the Codes of Good Practice |
| New generation trade issues |  | The Committee has only had a briefing on the impact of climate change on trade relations in November 2011 from the International Trade and Economic Development Division. |
| Issues that remain unresolved since the 2010/11 financial year |
| Cooperatives |  | Awaiting the Cooperatives A/B. |
| Financial Crisis Interventions: The Committee had requested an analysis of the impact of the financial crisis and the proposed financial crisis interventions from three economists. |  | No, the Committee needs to engage the relevant lead department(s) and entities for an update on the implementation of the proposed industrial and trade policy measures within the framework. However, the matter may be relatively outdated. |
| Reviewing and promoting rural development initiatives |  | No. |
| Strategy for agro-processing industries |  | No, due to the Committees other commitments, it has been unable to encourage a consultative approach between the relevant Departments and parliamentary committees in developing this strategy as envisaged in its annual Oversight Strategy. |