## BRANCH: CURRICULUM POLICY, SUPPORT AND MONITORING

CONDITIONAL GRANT –

CONSOLIDATED DRAFT REPORT FOR THE TECHNICAL SECONDARY SCHOOLS RECAPITALISATION

2011/12

Compiler: Enoch Mchiza

Extension: X4194

Date: 25 May 2012 v5

CONSOLIDATED PRELIMINARY REPORT ON THE TECHNICAL SECONDARY SCHOOLS RECAPITALISATION GRANT – APRIL 2011-MARCH 2012

1.	AIM OF THE REPORT

The aim of this preliminary report is to provide details of the performance of the grant during second implementation period (2011/12). Further assessments and verification of the performance data will be provided through the annual evaluation report, which will be available in July 2012.

The data in this report is sourced from expenditure reports from CFO’s office and other reports collected from provincial coordinators. The provincial data is collected using a template developed by the project management office and has not been verified or audited by any third party.

2.	PURPOSE OF THE RECAPITALISATION OF TECHNICAL SCHOOLS

The purpose of the recapitalization of technical schools is to improve conditions of technical schools  and modernize them to meet the teaching requirements of learners in the technical subject fields and increase the number of suitably qualified and technically skilled graduates from these schools.

2.1	Purpose of the Technology Subjects

The four technology subjects of the curriculum (Civil Technology, Electrical Technology, Mechanical Technology and Engineering Graphics and Design) are intended to offer learners elementary engineering and technological skills, which are suitable for (1)  the world of work, (2)  higher and or further education and training and  (3) self employment.

2.2	Delivery of Technology Subjects within the Education Landscape

According to the Education Management Information System (EMIS) database of 2010, there are 960 public secondary schools offering one or more technology subjects. The grant has identified 200 of the 960 schools for recapitalisation during the period 2010/11 - 2014/15.

2.3	Relevance of the Grant to the Department’s Goals

The Conditional Grant aims to contribute to the achievement of the following goals and outputs of the Action Plan 2014:

Teachers

- Goal 16: 	Improve the professionalism, teaching skills, subject knowledge and computer literacy of teachers throughout their entire careers. (GRANT OUTPUT 4).

Learner resources

- Goal 20: 	Increase access amongst learners to a wide range of 	media, including computers, which enrich their education. (GRANT OUTPUT 3).

School infrastructure and support services

- Goal 24: 	Ensure that the physical infrastructure and environment of every school inspires learners to want to come to school and learn, and teachers to teach. 			(GRANT OUTPUT 1 & 2)

3.	THE ALLOCATION OF RESOURCES FOR THE RECAPITALISATION GRANT

The Department of Basic Education (the Department) was initially allocated R80 million (2010/11), R200 million (2011/12), R210 million (2012/13 to implement the grant through provinces respectively. During the budget review period of 2011/12 the financial allocations were revised as follows: R210 million: 2011/12, R209 million: 2012/13, R221 million: 2013/14 and R233 million: 2014/15.

4.	GRANT OUTPUTS

The business planning process for the period 2011/12 indicated the following outputs for the grant: 32 new workshops to be built, 147 old workshops to be refurbished, 191 workshops to receive equipment, tools and machinery and 578 teachers to be trained.

After careful analysis of the provincial business plans, it was revealed that the total outputs as projected by the provinces are different from the projections indicated in the grant framework. The following targets were indicated: 44 new workshops to be built, 226 old workshops to be refurbished, 214 workshops to receive equipment, tools and machinery and 588 teachers to be trained.

The differences meant that the deviations between the grant framework and the business plans have to be reconciled at the end of the financial period because the framework could not be revised during the period. A detailed reconciliation of the outputs has been provided in page 13 of this document.

5.	BACKGROUND TO THE PERFORMANCE CYCLE FOR THE YEAR (2011/12)

The requirement to submit business plans and schools operational plans was communicated to all provinces at the beginning of the year (January 2011). Provinces complied with the requirement to submit provincial business plans with the exception of KwaZulu-Natal, which submitted the plan in August 2011, and again the compilation and submission of schools operational was not met by all provinces.

The schools operational plans are critical because they are an indication that the province has planned for the allocation of funds according to the specific needs at each school in the list.

The issue of indicating unrealistic targets was resolved during the business planning process except in the Eastern Cape. However, communication and interdepartmental planning at provincial level has not yet been instituted.

This therefore creates challenges in the case of infrastructure projects, which are implemented by other departments.

Expenditure and outputs trends have improved considerably at most provinces and although a number of provinces continue to struggle in terms of completing projects and recording expenditure according to the correct departmental codes and Limpopo, Gauteng and North West have recorded poor expenditure and output performance for the first time in the grant for latter two provinces.

In comparison with the previous financial period the operational systems at provincial level have improved at most provinces especially those that transfer funds to schools and those that implement infrastructure projects on their own.

5.1	Summary of performance information

The grant’s performance for 2011/12 in a nutshell:

- The financial expenditure has declined by 3% compared to the previous period (R60 million of R80 million, 75% in 2010/11 and R151 million of R210 million 72% in 2011/12).

- The output’s performance has increased by 16% from 71% to 87%. The number of outputs completed this period is 949 of 1092 compared to 516 of 731 in the previous period. The outputs refer to building of new workshops, refurbishing old workshops, supplying new equipment and training teachers.

- The overall expenditure (when financial commitments are taken into consideration) is 92%, which is similar to the previous period.

- An amount of R16 million may be surrendered to the National Revenue Fund because it was not committed at the close of financial books (March 2011/12).

  - The most completed output is teacher training, followed by supply of equipment, followed by refurbishment of workshops and the least being the building of new workshops.

- Provinces that performed well in terms of expenditure and outputs are Free State, Mpumalanga, Northern Cape, and Western Cape. The performance for KwaZulu-Natal and Eastern Cape requires verification before confirmation.

- Limpopo has recorded the highest completion of outputs with the lowest expenditure. This may be due to the capital expenditure paid for by the Infrastructure department instead of education.

- The Eastern Cape has recorded the highest expenditure with the lowest outputs. This is due to the high charge or cost of building new workshops, which are currently under construction.

- The following provinces recorded over-expenditure (MP: 1% and NC: 2%). These deviations will be dealt with by provincial treasuries and provincial equitable shares will also be considered to supplement where necessary.

- Financial commitments for incomplete projects or unpaid invoices (accruals) amounted to R42 million.

The evaluation of the grant, which is planned for April – June 2012 will provide more information related to the output performance recorded in this report.

The following tables provide detailed breakdown of the funds allocated, transferred, and spent during the year and it also indicates the completed outputs according to the business plans’ projections:

| Table 1: Consolidated (R’000) |
| --- |
| Conditional Grant | Total Allocation | Amount Transferred | Total Expenditure (Excl. Commitments) | % Spent on Total Allocation |
| Technical Secondary Schools Recapitalisation | 210,518 | 210,518 | 151,769 | 72% |
| Total | 210,518 | 210,518 | 151,769 | 72% |

| Table 2 | 2010/11 |  | 2011/12 |  | Variance |
| --- | --- | --- | --- | --- | --- |
| Province | Annual Allocation/Adjusted Budget | Amount Transferred | Amount Spent (Excluding Commitments) | % Spent on total Allocations |  | Annual Allocation/Adjusted Budget | Amount Transferred | Amount Spent (Excluding Commitments) | % Spent on total Allocations |  | % Change |
| EC | 9,549 | 3,342 | 6,030 | 63% |  | 40,272 | 40,272 | 34,492 | 86% |  | 22% |
| FS | 7,477 | 7,477 | 6,758 | 90% |  | 14,428 | 14,428 | 14,428 | 100% |  | 10% |
| GP | 17,944 | 17,944 | 14,247 | 79% |  | 30,596 | 30,596 | 10,649 | 35% |  | -45% |
| KZN | 15,275 | 15,275 | 15,038 | 98% |  | 38,563 | 38,563 | 35,276 | 91% |  | -7% |
| LP | 8,479 | 2,968 | 2,500 | 29% |  | 31,894 | 31,894 | 11,043 | 35% |  | 5% |
| MP | 5,869 | 2,054 | 1,738 | 30% |  | 21,464 | 21,464 | 21,780 | 101% |  | 72% |
| NC | 3,423 | 3,423 | 2,689 | 79% |  | 7,667 | 7,667 | 7,829 | 102% |  | 24% |
| NW | 8,696 | 8,697 | 7,595 | 87% |  | 17,015 | 17,015 | 7,662 | 45% |  | -42% |
| WC | 3,288 | 3,288 | 3,103 | 94% |  | 8,619 | 8,619 | 8,610 | 100% |  | 6% |
| TOTAL | 80,000 | 64,468 | 59,698 | 75% |  | 210,518 | 210,518 | 151,769 | 72% |  | -3% |

| Table 3: Detailed Financial Data (R’000) |
| --- |
| Province | Annual Allocation | Amount Transferred | Amount Spent per Province | Amount Committed to Goods and Services | Total Amount Spent (incl Commitments) | % Spent on Actual Payments/Allocation | % Total Spent on Transfers (Incl. Comms) | Total Amount Withheld to date | Total Amount Retained/Unspent Under/Over-expenditure |
| EC | 40,272 | 40,272 | 34,492 | 8,750 | 43,242 | 86% | 107% | 0 | -2,970 |
| FS | 14,428 | 14,428 | 14,428 | 0 | 14,428 | 100% | 100% | 0 | 0 |
| GP | 30,596 | 30,596 | 10,649 | 19,947 | 30,596 | 35% | 100% | 0 | 0 |
| KZN | 38,563 | 38,563 | 35,276 | 3,832 | 39,108 | 91% | 101% | 0 | -545 |
| LP | 31,894 | 31,894 | 11,043 | 9,400 | 20,443 | 35% | 64% | 0 | 11,451 |
| MP | 21,464 | 21,464 | 21,780 | 0 | 21,780 | 101% | 101% | 0 | -316 |
| NC | 7,667 | 7,667 | 7,829 | 0 | 7,829 | 102% | 102% | 0 | -162 |
| NW | 17,015 | 17,015 | 7,662 | 765 | 8,427 | 45% | 50% | 0 | 8,588 |
| WC | 8,619 | 8,619 | 8,610 | 9 | 8,619 | 100% | 100% | 0 | 0 |
| TOTAL | 210,518 | 210,518 | 151,769 | 42,703 | 194,472 | 72% | 92% | 0 | 16,046 |
| Table 4: Performance Outputs Projected and Completed for the period (2011/12) |
| Performance Output | EC | FS | GP | KZN | LP | MP | NC | NW | WC | TOTAL |
|  | Projected | Actual | Projected | Actual | Projected | Actual | Projected | Actual | Projected | Actual | Projected | Actual | Projected | Actual | Projected | Actual | Projected | Actual | Projected | Actual |
| Target Output 1: New Workshops | 2 | 0 | 14 | 14 | 0 | 0 | 8 | 0 | 6 | 0 | 8 | 8 | 0 | 0 | 3 | 0 | 1 | 1 | 42 | 23 |
| Target Output 2: Refurbishment of Workshops | 8 | 2 | 64 | 64 | 24 | 4 | 43 | 25 | 7 | 3 | 16 | 16 | 56 | 56 | 1 | 0 | 28 | 28 | 247 | 198 |
| Target Output 3: New Equipment | 21 | 21 | 4 | 4 | 28 | 0 | 36 | 10 | 24 | 23 | 15 | 15 | 56 | 56 | 3 | 17 | 28 | 28 | 215 | 174 |
| Target Output 4: Teacher Training | 31 | 31 | 55 | 55 | 28 | 28 | 50 | 59 | 140 | 140 | 120 | 120 | 48 | 48 | 100 | 55 | 16 | 18 | 588 | 554 |
| Total Targets Projected and Completed | 62 | 54 | 137 | 137 | 80 | 32 | 137 | 94 | 177 | 166 | 159 | 159 | 160 | 160 | 107 | 72 | 73 | 75 | 1,092 | 949 |
| % Completed (Targets) | 87% | 100% | 40% | 69% | 94% | 100% | 100% | 67% | 103% | 87% |
| Table 5: Summary Comparison of Non-Financial Performance for the periods 2010/11 - 2011/12 |
| ELEMENT | EC | FS | GP | KZN | LP | MP | NC | NW | WC | TOTALS |
| Total Targets Projected | 62 | 137 | 80 | 137 | 177 | 159 | 160 | 107 | 73 | 1,092 |
| Total Targets Completed (2011/12) | 54 | 137 | 32 | 94 | 166 | 159 | 160 | 72 | 75 | 949 |
| % Completed (Targets) 2011/12 | 87% | 100% | 40% | 69% | 94% | 100% | 100% | 67% | 103% | 87% |
| Total Targets Projected (2010/11) | 151 | 52 | 15 | 167 | 174 | 67 | 10 | 53 | 42 | 731 |
| Total Targets Completed (2010/11) | 95 | 52 | 14 | 167 | 89 | 9 | 10 | 47 | 33 | 516 |
| % Completed (Targets) 2010/11 | 63% | 100% | 93% | 100% | 51% | 13% | 100% | 89% | 79% | 71% |
| Variance in Targets Projected (2011/12-2010/11) | -89 | 85 | 65 | -30 | 3 | 92 | 150 | 54 | 31 | 361 |
| Variance in Targets Completed (2011/12-2010/11) | -41 | 85 | 18 | -73 | 77 | 150 | 150 | 25 | 42 | 433 |
| % Increase/Decrease in Performance | 24% | 0% | -53% | -31% | 43% | 87% | 0% | -21% | 24% | 16% |
| Table 6: Detailed Comparison of Financial Performance between quarters of 2010 and 2011 |
| Period | 2010/11 | 2011/12 | Variance (2011-2010) | % Change | 2010/11 | 2011/12 | Variance (2011-2010) | % Change | 2010/11 | 2011/12 | Variance (2011-2010) | % Change | 2010/11 | 2011/12 | Variance (2011-2010) | % Change |
|  | Quarter 1 |  |  | Quarter 2 |  |  | Quarter 3 |  |  | Quarter 4 |  |  |
| Annual Allocation | 80,000 | 200,000 | 120,000 | 150% | 80,000 | 200,000 | 120,000 | 150% | 80,000 | 210,518 | 130,518 | 163% | 80,000 | 210,518 | 130,518 | 163% |
| Transfer per quarter | 12,000 | 16,144 | 4,144 | 35% | 16,000 | 60,000 | 44,000 | 275% | 30,725 | 91,755 | 61,030 | 199% | 64,468 | 210,518 | 146,050 | 227% |
| Expenditure for the Quarter | 1,200 | 31,312 | 30,112 | 2509% | 17,707 | 19,158 | 1,451 | 8% | 17,191 | 45,128 | 27,937 | 163% | 35,954 | 57,622 | 21,668 | 60% |
| Balance | 78,800 | 167,940 | 89,140 | 113% | 74,345 | 180,842 | 106,497 | 143% | 62,809 | 161,191 | 98,382 | 157% | 44,046 | 152,896 | 108,850 | 247% |
| % Exp to Allocation | 1.50% | 15.66% | 14.16% | 943.73% | 22.13% | 9.58% | -12.55% | -56.72% | 21.49% | 21.44% | -0.05% | -0.24% | 44.94% | 27.37% | -17.57% | -39.10% |
| % Exp to Transfer | 10.00% | 193.95% | 183.95% | 1839.54% | 110.67% | 31.93% | -78.74% | -71.15% | 55.95% | 49.18% | -6.77% | -12.10% | 55.77% | 27.37% | -28.40% | -50.92% |
| NB: 2011/12 Annual Allocation revised from R200 million to R210,518 million due to approval of roll-over of R10,518 million. |

| Table 7: Comparison of Financial Performance between two financial periods - 2010/11 and 2011/12 |
| --- |
| Period | 2010/11 | 2011/12 | Variance (2011-2010) | % Change |
| Annual Allocation | 80,000 | 210,518 | 130,518 | 163% |
| Transfer per quarter | 64,468 | 210,518 | 146,050 | 227% |
| Expenditure for the Period | 60,000 | 151,769 | 91,769 | 153% |
| Balance | 20,000 | 58,749 | 38,749 | 194% |
| % Expenditure to Allocation | 75.00% | 72.09% | -2.91% | -3.88% |
| % Expenditure to Transfer | 93.07% | 72.09% | -20.98% | -22.54% |
| NB: 2011/12 Annual Allocation revised from R200 million to R210,518 million due to approval of roll-over of R10,518 million. |

| Table 8: Financial Performance | 2010/11 | 2010/11 |  | 2011/12 | 2011/12 |  | To date |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Allocated | Spent |  | Alloc ated | Spent |  | Total Spent | Total Allocated | Deviations/Shortfall |
| TSSR Conditional Grant | 80,000 | 60,000 |  | 210,518 | 151,769 |  | 211,769 | 290,518 | 78,749 |
| % Totals | 75% |  | 72% |  | 73% | 27% |

| Table 9: Performance Outputs | Baseline | 2010/11 | 2010/11 |  | 2011/12 | 2011/12 |  | To date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Baseline Targets | Projected | Actual |  | Projected | Actual |  | Total Target/Projection | Total Achieved | Deviation for period |  | Balance for the project life |
| Target Output 1: New Workshops |  | 118 | 26 | 10 |  | 42 | 23 |  | 68 | 33 | 35 |  | 85 |
| Target Output 2: Refurbishment of Workshops |  | 266 | 144 | 106 |  | 247 | 198 |  | 391 | 304 | 87 |  | -38 |
| Target Output 3: New Equipment |  | 663 | 87 | 36 |  | 215 | 174 |  | 302 | 210 | 92 |  | 453 |
| Target Output 4: Teacher Training |  | 2749 | 474 | 364 |  | 588 | 554 |  | 1062 | 918 | 144 |  | 1831 |
| Total Targets Projected and Completed |  | 3796 | 731 | 516 |  | 1092 | 949 |  | 1823 | 1465 | 358 |  | 2331 |
| % Completed (Targets) per annum |  |  | 71% |  | 87% |  | 80% | 20% |  | 61% |
| % Achieved of targets for project life cycle | 14% |  | 25% |  | 39% |  |  |

NB: The above table indicates the baseline targets for all the outputs (3796), the projections and achievements for the past two years and the total for both years. It can be noted that the grant achieved an average *0% for both years and missed around 20% of its outputs for the two years.

If importance is the achievement of 39%, which is the sum of the two years achievements on a year to year basis. Year one is 15% and year 2 is 25%. This is good because the grant is expected to achieve 20% each year until 2014/15 in order to complete its outputs of 3976. There is 61% which is still left to be completed by the grant in its last 3 years.

6.	DETAIL ANALYSIS OF THE PERFORMANCE INFORMATION

The above tables indicate the following with regards to the performance of the grant during the 2011/12 financial period:

Financial Performance

- The adjusted allocation of R210 million (100%) was transferred to all provinces after a once off withholding for under-spending in January 2012.

- Of the R210 million R152 million was spent by all provinces excluding the financial commitments made at the end of the financial period. This represents 72% of the total transfers to provinces.

- When the commitments are taken into consideration, the aggregate expenditure becomes R194 million, which represents 92% of the total allocation.

- The over-expenditure has been recorded by the Eastern Cape (R8,7 million commitment), Mpumalanga (R316,000, actual expenditure), KwaZulu-Natal (R545,000, commitment) and Northern Cape (R162,000, actual payment). These deviations will be covered by the provincial equitable share allocations as indicated by the provincial treasuries.

- There is R58,7 million, which has been retained as a balance to cover the commitments for the following provinces: Eastern Cape (R8,7 million), Gauteng (R19 million), KwaZulu-Natal (R3,8 million, Limpopo (R9,4 million), North West (R765,000) and Western Cape (R9,000). The request for roll-overs will be done by provinces through their treasuries in accordance with the relevant regulations.

- The following provinces have recorded expenditure lower than the national average of 70%: Gauteng (35%), (Limpopo (35%), and North West (45%).

- Limpopo was also part of the under-performing provinces in the previous period.

- The following provinces recorded the highest expenditure: Eastern Cape (86%), Free State (100%), KwaZulu-Natal (91%), Mpumalanga (101%), Northern Cape (102%) and Western Cape (100%). It should be noted that three of the six provinces transfer funds directly to schools for implementation.

- It has to be noted that Limpopo indicates the highest number of outputs completed (102%) with the lowest expenditure (35%). It is reported that this is due to the inaccurate allocation of capital expenditure by the departments of education and infrastructure.

- An estimated R16 million may be surrendered to the National Revenue Fund for not being expended or committed at the end of the financial period.

Overall Performance Outputs (targets)

- 23 of 42 new workshops built to support the technical subject offerings;

- 247 of 198 existing workshops refurbished, upgraded and re-designed to comply with safety laws and regulations and minimum industry standards;

- Equipment, machinery and tools bought, delivered and installed at 174 of 215 projected workshops;

- 554 of 558 Technical schools teachers trained in subject content delivery and new practical teaching methodologies;

- The building of new workshops also improved especially at Mpumalanga and it was also boosted by the efficiencies of the Free State.

- The failure by Gauteng, Limpopo and North West to complete their targets had a negative impact on the performance of the grant.

- The fact that the under-performing provinces have all projected the building of new workshops and failed to complete most of their targets is an indication of the level of difficulty in completing this output, the time required in planning for its delivery and the coordination required between the Department and the implementing agency (Public Works etc).

- The following provinces recorded the most completed outputs for the period: (Free State (100%), KwaZulu-Natal (77%), Mpumalanga (100%), Northern Cape (100%), and Western Cape (103%)).

  - The total projected outputs were 1,092 and 949 were completed by all

Provinces, which represents 87% and.

- In financial terms, the performance has declined by 3% to the previous period (2010/11) at 72% expenditure, however, in non-financial terms, the output performance has significantly improved from 71% to 87% achievement of targets.

Additional Notes: Reconciliation of the performance targets

| Table 10: Performance targets per province per output item with the reconciliation between PDE and DBE targets |
| --- |
| Province | EC | FS | GP | KZN | LP | MP | NC | NW | WC | TOTAL | % Complete | Reconciliation of Performance Targets |
| Output Item |  |  |  |  |  |  |  |  |  |  |  | DBE Targets | Outcome-DBE | Variance | DBE-PDE | PDE-Result |
| New Workshops | 0 | 14 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 23 | 55% | 32 | -9 | -10 | 19 | 0 |
| Refurbishments | 2 | 64 | 4 | 25 | 3 | 16 | 56 | 0 | 28 | 198 | 80% | 147 | 51 | -100 | 49 | 2 |
| Equipment | 21 | 4 | 0 | 10 | 23 | 15 | 56 | 17 | 28 | 174 | 81% | 191 | -17 | -24 | 41 | 21 |
| Training | 31 | 55 | 28 | 59 | 140 | 120 | 48 | 55 | 18 | 554 | 94% | 578 | -24 | -10 | 34 | 31 |
| Totals | 54 | 137 | 32 | 94 | 166 | 159 | 160 | 72 | 75 | 949 | 87% | 948 | 1 | -144 | 143 | 54 |

As indicated in paragraph 6 of this document that the performance targets are different between the provincial plans and the departmental plans. The following information describes the reconciliation of the differences/deviations:

- The aggregate departmental target for the grant is 948 outputs;

- The aggregate provincial target is 1092 outputs for the period;

- The difference between the two outputs is 144;

- The aggregate targets achieved during the period is 949;

- If the departmental targets are considered, the grant has exceeded its targets by 1 output;

- If the provincial targets are considered, the grant has under-achieved by 143 outputs.

- The above deviations have no significant effect on the allocated budget for the grant. This is due to the timing difference between the development of the grant framework and business plans for each year.

6.2	Academic Performance (Learner Participation and Success

| Table 11 | Civil Technology | Electrical Technology | Engineering Graphics and Design | Mechanical Technology |
| --- | --- | --- | --- | --- |
| Province | Total Wrote | Total Passs | % Pass | Total Wrote | Total Passs | % Pass | Total Wrote | Total Passs | % Pass | Total Wrote | Total Passs | % Pass |
| EASTERN CAPE | 632 | 592 | 94 | 484 | 383 | 79 | 1897 | 1701 | 90 | 527 | 481 | 91 |
| FREE STATE | 725 | 714 | 98 | 377 | 360 | 95 | 1609 | 1579 | 98 | 485 | 475 | 98 |
| GAUTENG | 2184 | 2102 | 96 | 1286 | 1153 | 90 | 6799 | 6370 | 94 | 1729 | 1590 | 92 |
| KWAZULU-NATAL | 1303 | 1272 | 98 | 1198 | 1091 | 91 | 5999 | 5691 | 95 | 1287 | 1216 | 94 |
| LIMPOPO | 402 | 397 | 99 | 397 | 356 | 90 | 1475 | 1445 | 98 | 254 | 247 | 97 |
| MPUMALANGA | 449 | 446 | 99 | 331 | 317 | 96 | 1453 | 1407 | 97 | 362 | 346 | 96 |
| NORTH WEST | 672 | 655 | 97 | 352 | 334 | 95 | 1647 | 1593 | 97 | 501 | 484 | 97 |
| NORTHERN CAPE | 157 | 153 | 97 | 132 | 121 | 92 | 445 | 436 | 98 | 158 | 157 | 99 |
| WESTERN CAPE | 1703 | 1638 | 96 | 279 | 247 | 89 | 2500 | 2461 | 98 | 528 | 512 | 97 |
| Total | 8227 | 7969 | 97 | 4836 | 4362 | 90 | 23824 | 22683 | 95 | 5831 | 5508 | 94 |

The four technology subjects pass rate is satisfactory averaged at 90% but the major concern is the decline in learner numbers over the years for all provinces in all the four subjects, which is not illustrated in the table.

6.3	Interventions to Improve Learner Participation and Success

Table 12:

| REASONS FOR DECLINE OF ENROLMENTS | IMPROVEMENT STRATEGY |
| --- | --- |
| The NCS curriculum has combined 18 subjects into four (4) subjects taking away the specialization component as a result most learners cannot cope with the demand of the subjects; Lack of specialisation does not offer learners sufficient skills for employment; Some learners might have gone to the FET college sector. Negative perceptions around attending vocational school. Most technology teachers leaving the schooling system because they have only specialised in one or two subjects and cannot cope with the demand of the subjects. The design of the subject in the GET phase does not prepare learners for the Technology subjects in FET. | The current review of CAPS to introduce specialisation in the technical/technology subjects will have a positive effect in the content and delivery of the three subjects; The proposal to introduce technical mathematics and technical science will attract more learners into the technical stream while bringing direct relevance between the content of mathematics and physical science and the technology subjects. The impact of the ongoing recapitalisation process will provide resources, facilities and assist teachers in the practical teaching methodologies of the subjects; this will further improve the pass rate while attracting more learners into the stream. The development of a clear articulation model/policy between technical schools and FET colleges will also assist in retaining the learners within the system |

7.	CHALLENGES FACING THE ACHIEVEMENT OF OUTPUTS FOR THE FINANCIAL PERIOD 2011/12;

Although the operating systems for the grant at provincial and school level are maturing, there are still ongoing implementation and planning challenges experienced during the period. Amongst other challenges, the most prominent can be outlined below as:

- Internal departmental administrative delays in the development and approval of tender specifications for building and refurbishment of workshops resulted in the annual targets not being met for Gauteng, Eastern Cape, KwaZulu-Natal, Limpopo and North West;

- Irregular monitoring, collection of data and reporting resulted in the absence of information to detect early warning signals for underperformance especially for Limpopo and Eastern Cape;

- The late approval of provincial and schools’ business plans delayed the implementation of the grant for KwaZulu-Natal;

- Unrealistic projections in the business plans and the lack of skills to coordinate the project resulted in the province not meeting its performance targets for the Eastern Cape; and

- The failure to consult other departments and directorates such as Public Works and Infrastructure continue to delay the implementation of building of workshops by the other Departments in Eastern Cape, North West and Gauteng.

| Table 13: CHALLENGES AND MITIGATING FACTORS |
| --- |
| Challenge | Affected Provinces | Mitigating Strategy |
| Delays in the development and approval of tender specifications for building and refurbishment of workshops resulted in the annual targets not being met | Gauteng, Eastern Cape, KwaZulu-Natal, Limpopo and North West | Standard templates for procurement and uniform architectural plans for buildings have been developed |
| Irregular monitoring, collection of data and reporting resulted in the absence of information to detect early warning signals for underperformance especially | Limpopo and Eastern Cape | Monthly visits are being undertaken Implementing agencies (COEGA for EC have dual reporting) Schools also report on a monthly basis to the project manager where necessary |
| The late development of provincial and schools’ business plans delayed the implementation of the grant | KwaZulu-Natal | Business planning process improved to be completed earlier than previous periods |
| Unrealistic projections in the business plans and the lack of skills to coordinate the project resulted in the province not meeting its performance targets | Eastern Cape | Business plans reviewed in partnership with provincial departments such treasury and public works |
| The failure to consult other departments and directorates such as Public Works and Infrastructure continue to delay the implementation of building of workshops by the other Departments | Eastern Cape, North West and Gauteng | Business plans reviewed in consultation with provincial departments such as public works and infrastructure directorates |

8.	COMPLIANCE WITH THE CONDITIONS OF THE DIVISION OF REVENUE ACT

In terms of section 10(5) of the DoRA, 2011, as amended, the duties of the transferring national officer include submitting monthly reports to National Treasury, in the format determined by National Treasury, not later than 20 days after the end of each month. Compliance with this obligation was met.

In terms of section 12(2) of the DoRA, 2011, as amended, the duties of the receiving officer include submitting monthly reports to the relevant provincial treasury and to the transferring national officer on amounts received, funds withheld, and the actual expenditure of the province. Provinces continue to fail in comply with this requirement because only four of the nine provinces (Free State, KwaZulu-Natal, Northern Cape and Western Cape) managed to submit their monthly reports.

With regards to quarterly reports, all provinces managed to submit their quarterly reports within thirty days after the end of the quarter.

However most reports were not signed by the Heads of Departments as required, therefore a data verification process had to be made in this regard.

The failure to submit the monthly reports made it difficult for the Department to report to National Treasury on a monthly basis. The Department relied on the provincial treasuries to source expenditure data on a monthly basis.

8.1	Withholding of funds due to under-expenditure

The continuous underperformance especially under-spending during the first two quarters led to the Department withholding the transfer of funds to all provinces in accordance with Section (16)(1)(c) of the Division of Revenue Act, 2011, as amended.

The third quarter of the financial period saw an improvement in the implementation and expenditure of the grant and all funds were transferred to the provinces in January 2012.

9.	APPROVAL OF BUSINESS PLANS

Due to the late submission of the business plans, the payment schedule was revised. All business plans were approved after March 2011 with the exception of KwaZulu-Natal, which was received in August 2011. The compliance certificates were compiled and submitted to the National Treasury as part of the approval process.

10.	PERFORMANCE EVALUATION OF THE CONDITIONAL GRANT

In terms of Section 10(6) of the Division of Revenue Act 2011, as amended, the transferring national officer must evaluate the performance of programmes funded or partially funded by the allocation and submit such evaluation to the National Treasury within four months after the end of the financial year.

The technical secondary schools conditional grant being a new grant was evaluated for the first time during the first quarter of 2011/12. The Department plans to conduct another annual performance evaluation of the grant in all nine provinces in accordance with the process outlined in Practice Note 12, issued by National Treasury for this purpose. The evaluation process and the report must be completed in July 2012.

11.	PERFORMANCE OF THE DEPARTMENT WITH REGARDS TO ADMINISTRATION, MONITORING AND SUPPORT FOR THE GRANT

The Department of Basic Education is required to administer, manage all processes related to the grant, develop guidelines that will assist provinces in implementing the grant, monitor performance and provide continuous support to provinces.

The Department allocated R949,000 as a budget to implement the activities indicated in the above paragraph. The expenditure for the Department stood at R492,000,000, (52%) at the end of the financial period.

Thirty (30) schools in eight provinces were visited by the project manager as part of the monitoring and support process during the period under review (KwaZulu-Natal has not been visited).

The under-expenditure is due to the fact that the parallel activities such as the curriculum review process or CAPS training, requires the same project coordinators therefore monitoring, reporting, supporting the implementers or service providers may not be conducted to allow the coordinators to focus on the other activities. This occurrence requires revisions of the activities of the grant in order to accommodate the finalisation of other activities such as the CAPS activities.

12.	IMPROVEMENT OF THE GRANT IMPLEMENTATION FOR THE 2012/13 PERIOD AND BEYOND

As a response to the ongoing challenges of underperformance, the grant framework was revised to strengthen the implementation and improve efficiencies at provincial and school level. These revisions have made differences in those provinces that have adopted them. These have also made a difference at school level where capacity is being built through this project. The Department will continue to use the framework as one of the tools to effect change and improve performance of the grant.

The planning processes have also improved, however an added effort is required with regards to the relationship between different departments. The department will be reconstituting the recapitalisation teams at provincial level, which must include representative of different stakeholders. These teams will become standing committees that will oversee and be accountable for the delivery of the grant for the duration of the project. The grant requires the involvement of other personnel to undertake activities such as collection, analysis and reporting of information. There is a lack of information at all levels which, is vital to decision making and the current personnel are unable to provide this based on their core activities.

The Department is also in a process of intensifying its monitoring and support efforts by establishing a special or dedicated unit that will provide ongoing support and guidance to provinces and intervene urgently in cases of severe underperformance at all levels.

13.	CONCLUSION

The gradual increase in funding between the previous period had a positive effect in the increase of the projected outputs. It is acknowledged that the overall expenditure has declined by 3% compared to the previous period, but the increase in the outputs achieved is a sign that operational systems at provincial and school level are maturing and significant improvements in coordination can now be identified.  It is therefore an opportune time for provinces to complete the project within the set timeframe.

The fact that the same number of provinces (three out of nine) (Limpopo, Gauteng and North West in 2011/12) continue to underperform is a cause for concern and urgent interventions are required such as the appointment of an external service provider, which will deliver the implementation on behalf of the department in the case where a department lacks the capacity to deliver especially in infrastructure projects.

The utilization of the subject advisors as the project coordinators/managers also poses a challenge especially when there are other major projects that require their attention such as the ongoing CAPS process.

In cases where the grant is performing, the funds are transferred to the school and the subject advisor/project coordinator is therefore relived of the responsibility of managing the day-to day of the grant.

It has to be emphasised again that the grant requires the involvement of other personnel to undertake activities such as collection, analysis and reporting of information.

There is a lack of information at all levels which, is vital to decision making and the current personnel are unable to provide this based on their core activities. The reporting systems are currently inefficient and this negatively affects the decision making process.

The grant continues to have a positive impact at school and community levels where it has been delivered efficiently. The ongoing review of the technology subjects’ curriculum and the effect of specialisation will also contribute positively to the delivery of the grant by identifying the correct schools and the areas of specialisation with an aim of allocating the resources adequately.

Considering the current available human resources and the type of outputs to be produced by the grant within the set timeframes, the grant has performed well but more efficiencies are required to improve its financial and output performance to 100% in the next financial period.

The implementation of a short-term project such as this grant requires the strengthening of planning as a main feature for timely service delivery. Focused planning ensures better and quicker implementation especially in meeting the tight deadlines set up for the project. Planning alone may not improve the implementation of the grant, but dedicated and efficient administrative, financial and procurement processes and systems, resources and management commitment are also required from all role-players.

## BRANCH: CURRICULUM POLICY, SUPPORT AND MONITORING

CONSOLIDATED DRAFT REPORT FOR THE TECHNICAL SECONDARY SCHOOLS RECAPITALISATION CONDITIONAL GRANT

2011/12

Compiler: Mr Enoch Mchiza: Project Manager

Technical Secondary Schools Recapitalisation

(012) 357-4194 (Tel)

(012) 328-9828 (Fax)

mchiza.e@dbe.gov.za

222 Struben Street

Sol Plaatje House

Pretoria

0001

Private Bag X895

Pretoria

0001