| # | Hospitals/ Projects on HRP | Start date | Anticipated completion date - in 2012/13 PIP | Revised completion date | Allocated budget (As per appointment letter) | Allocated budget (2012/13) | Expenditure to date (since inception to August 2012) | Balance | Reasons for delay if any and contractor challenges |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Letaba Hospital |  |  |  |  |  |  |  |  |
|  | B3Construction of new administration buildings, patient admission buildings, transport control centre, entrance Complex, paved parking and access road and renovations to existing administration and gateway clinic; including professional fees | 6/3/2008 | 1/10/2010 |  | R 40,600,083 | R 6,403,000 | R 34,194,540 | R 6,405,543 | The project is completed and occupied in 2012. The remaining funds are for final accounts and mechanical work (airconditioners that were installed but were not functioning properly). The contractor is currently on site and anticipated to fininsh by end of 3rd Quarter. |
|  | A 2: Construction Gynaecology, walkways, Orthotic & Prosthetic Workshop, Extension to Nursing School, Renovations to Staff accommodation, workshop including professional fees | 1/9/2009 | 08/27/09 |  | R 40,709,788 | R 1,912,000 | R 32,625,387 | R 8,084,401 | Slow performance by the contractor. |
|  | New Maternity and Victim empowerment Centre and roads, including Professional fees. | 11/22/2011 | 5/12/2012 | Revised dates currently being discussed with Implementing Agents | R 50,800,000 | R 41,598,000 | R 12,400,000 | R 38,400,000 | The project started in Novenber 2011, just before administration in December of the same year and was affected by unavilability of funds at that time. Implementing Agent to submit extension of time. |
|  | TOTAL - LETABA |  |  |  | R 132,109,871 | R 49,913,000 | R 79,219,927 | R 52,889,944 |  |
| 2 | Maphutha Malatji |  |  |  |  |  |  |  |  |
|  | Demolition of existing buildings and construction of new stores including professional fees | 3/30/2011 | 3/30/2012 | Revised dates currently being discussed with Implementing Agents | R 12,095,543 | R 407,000 | R 9,300,000 | R 2,795,543 | The remaining amount in for payment of final accounts and variation order. The stores building is completed and occupied. |
|  | Final account for Construction of Administration, Gateway Clinic and external works including professional fees. | 1-Aug-08 | 3/1/2012 | Revised dates currently being discussed with Implementing Agents | R 26,518,400 | R 1,715,000 | R 28,498,611 | R 1,980,211 | Overspending due to variation order due to price escallation on steel structure for gateway clinic. The building is completed and occupied. |
|  | Construction of Transport Control, Workshop, Recreational facility, Kitchen upgrade, linen store including professional fees. | 1-Oct-08 | 12/31/2011 | Revised dates currently being discussed with Implementing Agents | R 18,838,221 | R 3,665,000 | R 24,192,238 | R 5,354,017 | All buildings are completed and occupied except linen store. The overspending is due to variation order on the kitchen. |
|  | TOTAL |  |  |  | R 57,452,164 | R 5,787,000 | R 61,990,849 | R 4,538,685 |  |
| 3 | Thabamoopo |  |  |  |  |  |  |  |  |
|  | Female Acute, Sub-Acute and Chronic Ward including professional fees. | 9/10/2009 | 4/10/2010 | 3/23/2012 | R 9,038,384 | R 1,000,000 | R 7,732,054 | R 1,306,330 | Completed and occupied |
|  | Male Security Ward including professional fees. | 9/10/2009 | 7/14/2010 |  | R 3,086,088 | R 182,000 | R 2,904,424 | R 181,664 | Completed and occupied |
|  | Completion of Substance Abuse Ward including professional fees. | 6/1/2011 | 13-Dec-11 | 30-Oct-12 | R 5,205,501 | R 1,347,000 | R 3,887,277 | R 1,318,224 | Slow performance by the contractor. |
|  | Hostel, Flats,Bachelor's Flats, Halfway House, Pharmacy and Shelter including professional fees. | 9/10/2009 | 11/15/2010 |  | R 1,147,032 | R 361,000 | R 786,274 | R 360,758 | Completed and occupied |
|  | Kitchen, Staff Dining and Bulk Stores including professional fees. | 3/31/2009 | 7/31/2010 |  | R 17,940,394 | R 1,311,000 | R 17,231,138 | R 709,256 | Completed and occupied |
|  | Male Acute, Sub-Acute and Chronic Wards including professional fees. | 3/31/2009 | 5/31/2010 |  | R 17,065,502 | R 1,523,000 | R 15,788,885 | R 1,276,617 | Completed and occupied |
|  | Medical and Gaeriatics Ward including professional fees. | 9/9/2009 | 1/8/2011 |  | R 16,250,786 | R 1,280,000 | R 13,670,947 | R 2,579,839 | Slow performance by the contractor. |
|  | Health Support Complex including professional fees. | 7/25/2012 | 7/30/2013 |  | R 9,260,786 | R 4,000,000 | R 0 | R 9,260,786 |  |
|  | Civil Works (Phase 2) including professional fees. | 9/22/2008 | 2009/11/30 |  | R 9,717,103 | R 329,000 | R 9,793,991 | R 76,888 | Completed |
|  | TOTAL CONSTRUCTION COSTS |  |  |  | R 88,711,576 | R 11,333,000 | R 71,794,990 | R 16,916,586 |  |
| 4 | Thabazimbi |  |  |  |  |  |  |  |  |
|  | OPD, Casualty, X-ray, Pharmacy and ARV Clinic and administration block including professional fees. | 2011/06/20 | 2012/09/20 |  | R 64,991,536 | R 11,225,000 | R 49,500,000 | R 15,491,536 | All projects are on schedule. |
|  | Construction of staff accommodation including professional fees. | 2012/01/13 | 2012/09/12 |  | R 13,412,537 | R 11,410,000 | R 5,240,000 | R 8,172,537 |  |
|  | Construction of maternity, wards and theatre, linen bank ,kitchen, medical waste and ring road including professional fees. | 2012/01/13 | 2013/09/13 |  | R 184,836,755 | R 60,372,000 | R 33,900,000 | R 150,936,755 |  |
|  | TOTAL |  |  |  | R 263,240,828 | R 83,007,000 | R 88,640,000 | R 174,600,828 |  |
| 6 | Jane Furse |  |  |  |  |  |  |  |  |
|  | Construction of Gateway Clinic, Linen store and corrective work to OPD,Casualty , maternity male and female wards including professional fees. | 5/16/2011 | 3/25/2012 | Revised dates currently being discussed with Implementing Agents | R 19,912,913 | R 8,746,000 | R 5,440,000 | R 14,472,913 | The contractor was affected by shortage of funds during end of previous financial year resulting in the contractor abandoning site. |
|  | TOTAL |  |  |  | R 19,912,913 | R 8,746,000 | R 5,440,000 | R 14,472,913 |  |
|  | OVERALL TOTAL |  |  |  | R 561,427,352 | R 158,786,000 | R 307,085,766 | R 254,341,586 |  |
| Balances in red indicate overspending |  |  |  |  |  |  |
|  | ENABLING PROJECTS |  |  |  |  |  |  |  |  |
|  | Name of Institution | Project Details | Start date | Completion date | Allocated Budget | Expenditure to Date | Balance | Project Status (Retention/ Construction) |  |
| 1 | Elim Hospital | Theatre |  |  | R 1,283,000 | R 1,327,020 | R 44,020 | Retention |  |
| 2 | George Masebe Hospital | Maternity & Theatre | 2011/07/14 | 2012/07/13 | R 11,788,000 | R 5,709,252 | R 6,078,748 | Construction |  |
| 3 | Voortrekker Hospital | OPD, X-Ray, Casualty & Pharmacy | 2011/04/12 | 2012/08/11 | R 13,962,000 | R 4,153,970 | R 9,808,030 | Construction |  |
| 4 | Mecklenburg Hospital | OPD, X-Ray, Casualty & Pharmacy | 2011/04/14 | 2012/08/13 | R 7,648,000 | R 10,691,215 | R 3,043,215 | Construction |  |
| 5 | Mokopane Hospital | Theatre Complex | 2011/04/12 | 2012/07/11 | R 603,000 | R 4,808,593 | R 4,205,593 | Construction |  |
| 6 | WF Knobel Hospital | Theatre Complex | 2011/04/20 | 2012/07/20 | R 11,158,000 | R 3,115,147 | R 8,042,853 | Construction |  |
| 7 | St Ritas Hospital | Pharmacy Upgrade | 2011/06/21 | 2012/04/20 | R 6,191,000 | R 5,606,142 | R 584,858 | Construction |  |
| 8 | Dr CN Phatudi Hospital | OPD, X-Ray & Pharmacy | 2011/07/15 | 2012/07/14 | R 7,540,000 | R 2,466,668 | R 5,073,332 | Construction |  |
| 9 | Matlala Hospital | OPD, X-Ray, Casualty & Pharmacy | 2011/06/01 | 2012/06/06 | R 8,292,000 | R 1,250,223 | R 7,041,777 | Construction |  |
| 10 | Philadelphia Hospital | OPD, X-Ray, Casualty | 2011/04/15 | 2012/07/16 | R 11,624,000 | R 7,763,438 | R 3,860,562 | Construction |  |
|  | TOTAL |  |  |  | R 80,089,000 | R 46,891,668 | R 33,197,332 |  |  |
|  | HOSPITAL STAFF ACCOMMODATION |  |  |  |  |  |  |  |  |
|  | Name of Institution | Project Details | No. of Projects | Start date | Completion date | Allocated Budget | Expenditure to Date | Balance | Project Status (Retention/ Construction) |
| 1 | Zebediela Hospital | 10 bedded single rooms | 1 | 2011/09/26 | 2012/03/26 | R 2,624,000 | R 2,042,000 | R 582,000 | Construction |
| 2 | George Masebe Hospital | 10 bedded single rooms | 1 | 2011/09/19 | 2012/03/19 | R 786,000 | R 895,000 | R 109,000 | Completed |
| 3 | Malamulele Hospital | 10 bedded single rooms | 1 | 2011/09/01 | 2012/03/01 | R 3,115,000 | R 1,040,000 | R 2,075,000 | Construction |
| 4 | Louis Trichardt Hospital | 10 bedded single rooms | 1 | 2011/09/01 | 2012/03/01 | R 3,574,000 | R 608,000 | R 2,966,000 | Construction |
| 5 | Donald Fraser Hospital | 10 bedded single rooms | 1 | 2011/09/01 | 2012/03/01 | R 2,139,000 | R 662,000 | R 1,477,000 | Construction |
| 6 | Kgapane Hospital | 10 bedded single rooms | 1 | 2011/09/01 | 2012/03/01 | R 3,664,000 | R 1,043,000 | R 2,621,000 | Construction |
| 7 | Old Nkhensani Hospital | 10 bedded single rooms | 1 | 2011/09/01 | 2012/03/01 | R 2,845,000 | R 968,000 | R 1,877,000 | Construction |
| 8 | Letaba Hospital | 10 bedded single rooms | 1 | 2011/10/01 | 2012/04/01 | R 3,739,000 | R 316,000 | R 3,423,000 | Construction |
| 9 | Dilokong Hospital | 10 bedded single rooms | 1 | 2011/10/01 | 2012/04/01 | R 4,034,000 | R 599,000 | R 3,435,000 | Construction |
| 10 | Jane Furse Hospital | 10 bedded single rooms | 1 | 2011/06/12 | 2012/07/09 | R 4,014,000 | R 1,117,000 | R 2,897,000 | Construction |
| 11 | Philadelphia Hospital | 10 bedded single rooms | 1 | 2011/09/20 | 2012/03/20 | R 4,123,000 | R 780,000 | R 3,343,000 | Construction |
| 12 | Matlala Hospital | 6* Bachelor; 4* 2Bedroom | 1 | 5/13/2010 | 2011/02/12 | R 1,148,000 | R 908,000 | R 240,000 | Construction |
| 13 | Mecklenberg Hospital | 4* Bachelor | 1 | 5/13/2010 | 2011/02/12 | R 1,148,000 | R 1,108,000 | R 40,000 | Construction |
|  | TOTAL |  | 13 |  |  | R 36,953,000 | R 12,086,000 | R 24,867,000 |  |
|  | Overall Budget: HRP Infrastructure Total (2012/13) |  |  |  |  | R 275,828,000 | (Less Limpopo Acamemic =R2,835,000 & Messina = 2,000,000) as there is no construction currently |