ACTION LOG

| Action Plan |
| --- |
| Objective | Scope | Activities | Allocated person | Deadline |
| Statistics | Template | Source copies of statistics templates from all provinces | Bonnie / Dawn / Nolitha / Geo / Andrea / Hanise | 31/01/13 Done |
|  |  | Source National template from Anthea Van Der Byl. | Luvuyo | 31/01/13 Done |
|  |  | Develop a detailed statistic form | All Task Team members | 31/01/13 Done |
|  |  | Drafted version of statistics form to be sent to IT to develop an integrated system | Aaron | 8/02/13 |
|  |  | Integrated system to be presented to NOMM | Aaron | TBD |
|  |  | Once NOMM accepts the form to be presented to DPP management | All Task Team members | TBD |
|  | Collation Process | Directive / Circular to be sent out: That Prosecutors’ must keep statistics on Human Trafficking matters on a monthly basis and forward them to the nodal points at DPP Office. That the nodal point at the DPP Office must report back on Human Trafficking matters in the Q report and to person responsible for collation. | Aaron | TBD |
|  |  | Ascertain who is the responsible person for collation of Human Trafficking statistics at a National level. | Aaron | 31/03/13 |
| Training material review | Identify training topics include case studies) | Social context | Bonnie | 31/03/13 |
|  |  | Chapter 1 What is trafficking in persons? The three phases of trafficking. Child Trafficking Identification of victims of trafficking – indicators Who are the traffickers? Traffickers – how do they control victims? The causes – push and pull factors The element of organised crime Trafficking of person – violation of human rights Impact of Human Trafficking Differentiate between migrant smuggling and trafficking in persons | Geo / Pakanyiswa | 31/03/13 |
|  |  | Chapter 3 International legal framework The Bill Other relevant legislation | Luvuyo, Andrea and Patamedi | 31/03/13 |
|  |  | Chapter 4 Extraditions and MLA | LAD / Aaron | 31/03/13 |
|  |  | Chapter 5 Victim’s rights (add compensation referred to in the Bill / look at Ch4) | Annah / Nolitha Johannes | 31/03/13 |
|  |  | Chapter 6 Procedural guidelines) – incorporate chapter 2 / sentencing / competent verdicts | Patamedi / Daphney / Zelda | 31/03/13 |
|  |  | Updated Case Law / scenarios | Siphiwo to source and collate | 31/03/13 |
|  |  | Case studies | Geo / Adina | 31/03/13 |
|  |  | SAPS National Instructions | Dawn | 31/03/13 |
|  |  | DSD norm and standards | Patamedi will follow up on availability | 14/02/13 |
|  |  | National Policy Framework | Patamedi to follow up on availability. | 14/02/13 |
|  |  | Process (DSD / WP / Drugs / Health issues) cooperation and coordination / Tip | Dawn / Geo | 31/03/13 |
|  |  | Interviewing process | Dawn / Zelda (consult George / Val) | 31/03/13 |
|  |  | AFU | Aaron to ask for Kamini Reddy to be co-opted and advise her of request for training material. | 8/02/13 |
|  |  | Pre assessment / Post assessment / evaluation of course material | Daphney / Johannes | 31/03/13 |
|  | Source available training materials and disseminate to task team members | Disseminate list of persons who have been trained as trainers | Daphney | 31/01/13 Done |
|  |  | Ascertain what training material they have and disseminate | Daphney | 14/02/13 |
|  |  | Disseminate current training manual for Prosecutors | Bonnie | 31/01/13 |
|  |  | Ascertain from other Departments whether they have training manuals available and disseminate | Patamedi / Luvuyo | 14/02/13 |
|  | Allocate training topics to be developed to individual task team members | Discuss and allocate training topics to be developed in a meeting. | Task Team members | 31/01/13 Done |
|  | Interrogate current training material | Interrogate current training manual for Prosecutors and other sourced training materials sent to individual Task team members | Task Team members | 31/03/13 |
|  | Distribute developed training material for comment to all task team members | once material has been developed all material to be sent to Kim to be distributed to all task team members for comment | Kim | 3/04/13 |
|  | Collate training manual | Meeting to assess and finalise training material | All task team members | 29 – 30 April 2013 |
|  | Develop power point presentations | Develop power point presentations | All Task Team members | 20/05/13 |
|  |  | Meeting to finalise power point presentations | All task team members | 20 -23 May 2013 |
| Training Implementation Plan | Enhance the training capacity of task team members by training other presenters in the Provinces. | List of trained trainers in Provinces to be disseminated. | Daphney | 31/01/13 Done |
|  |  | Identify committed trainers in Provinces and send through recommendations to Kim to disseminate | All Task Team members | 31/03/13 |
|  | Look at current training programme (2013 / 2014) of NPA and dates | Identify potential dates for training (during July) | Aaron / Daphney | 8/02/13 |
|  | Indentify suitable dates for training. | Disseminate dates to task team members | Aaron / Daphney | 8/02/13 |
|  |  | Meet with regional training forums and advise them of training dates | All Task Team members | TBD |
|  | Develop a training schedule. | Draft training schedule | All Task Team members | 29 – 30 April 2013 |
|  | Develop programme for the training | Draft programme for training | All Task Team members | 29 – 30 April 2013 |
|  | Allocate training topics to trainers | Training topics allocated for development of power point presentations | All task Team members | 29 – 30 April 2013 |
|  | Look into the training outcomes | The application form for the training must contain a clause that if you attend you will obliged to take matters to Courts. | Daphney | 31/03/13 |
| Annexures | Identify the offences contained in the Bill | Email draft annexures | Patamedi | 31/01/13 Done |
|  | Draft annexures | Draft annexures for charges contained in the Bill. | Patamedi / Daphney / Zelda | 31/03/13 |
|  | Distribute for comment to all task team members | Distribute draft annexures to all task team members for comment | Kim | 3/04/13 |
|  | Collate comments | Meeting to assess and finalise annexures | All task team members | 29 – 30 April 2013 |
| Policy Directives | Identify clauses to be included in the policy directives in line with clause 44(8). | Develop a draft inclusive of clauses | Luvuyo | 31/03/13 |
|  |  | Disseminate to all task team members | Kim | 3/04/13 |
|  | Identify other clauses that must be included in directives. | Meeting to identify clauses | All Task Team members | 29-30 April 2013 |
|  | Draft directives | Meeting to finalise directives | All Task Team members | 20-23 May 2013 |
|  | Submit to Bradley Smith for compliance check. | Compliance check to be done | Aaron | TBD |
| Regulations | Obtain draft regulations from the Law Reform Commission. | Disseminate draft regulations | Luvuyo | 31/01/13 Done |
|  | Identify issues that should be included in regulations. | Inputs on draft regulations to be sent to Luvuyo | All Task Team members | 1/03/13 |
|  | Submit to the Law Reform Commission. | Send inputs to Law Reform Commission | Luvuyo | TBD |