| DAFF Organisational Non-Financial Performance Report | Q3 of 2012/13 |
| --- | --- |
|  | 01 October – 31 December 2012 |

Table of Contents

ACRONYMS	4

OVERVIEW	8

ADMINISTRATION	10

PERFORMANCE AGAINST MEASURABLE OBJECTIVES	11

Human Resources Management	11

Chief Information Office	13

Development Finance	15

Financial Management	18

Monitoring and Evaluation	19

Policy Development and Planning	21

Stakeholder Relations/Fisheries Partnership Management	24

AGRICULTURAL PRODUCTION, HEALTH AND FOOD SAFETY	26

PERFORMANCE AGAINST MEASURABLE OBJECTIVES	27

Animal Production and Health	27

Plant Production and Health	29

Inspection and Laboratory Services	31

FOOD SECURITY AND AGRARIAN REFORM	32

PERFORMANCE AGAINST MEASURABLE OBJECTIVES	33

Food Security	33

Sector Capacity Development	37

National Support Services	38

ECONOMIC DEVELOPMENT, TRADE AND MARKETING	40

PERFORMANCE AGAINST MEASURABLE OBJECTIVES	41

Agro-Processing and Marketing	41

Cooperatives and Rural Enterprise Development	42

International Relations and Trade	45

FORESTRY AND NATURAL RESOURCES MANAGEMENT	48

PERFORMANCE AGAINST MEASURABLE OBJECTIVES	49

Forestry Development and Regulations	49

Forestry Operations	51

Natural Resources Management	53

FISHERIES MANAGEMENT	56

PERFORMANCE AGAINST MEASURABLE OBJECTIVES	57

Aquaculture and Economic Development	57

Fisheries Research and Development	61

Marine Resources Management	63

Monitoring, Control and Surveillance	66

CONCLUSION	68

# ACRONYMS

ABET 		Adult Basic Education and Training

ABP 		Annual Business Plan

ACP 		Aquaculture Certification Plan

ADF 		Agricultural Development Finance

ADZ 		Aquaculture Development Zone

AGIS 	Agricultural Geo-referenced Information System

AgriBEE	Agricultural Broad-Based Black Economic Empowerment

AIDA	Animal Identification Act

APA 		Agricultural Produce Agents

API 		Agricultural Production Input

APP 		Annual Performance Plan

ARC		Agricultural Research Council

ATF 		Agricultural Trade Forum

ATI 		Agricultural Training Institute

ATPR	Agricultural Trade Progress Report

BCC		Benguela Current Commission

BEE		Black Economic Empowerment

CAADP 	Comprehensive African Agricultural Development Programme

CAF		Consultative Advisory Forum

CASP 	Comprehensive Agricultural Support Programme

CC 		Climate Change

CCS 		Compulsory Community Service

CD 		Chief Director

CMDB 	Configuration Management Database

COMESA 	Common Market for Eastern and Southern Africa

CPI 		Consumer Price Index

CRDP 	Comprehensive Rural Development Programme

DAFF 		Department of Agriculture, Forestry and Fisheries

DBSA 	Development Bank of Southern Africa

DDG 		Deputy Director-General

DEA 	Department of Environmental Affairs

DEXCO	Departmental Executive Management Committee

DFQF 		Duty Free and Quota Free

DG		Director-General

DHET 	Department of Higher Education and Training

DPSA 	Department of Public Service and Administration

DPW 		Department of Public Works

DRDLR 	Department of Rural Development and Land Reform

DRP 		Disaster Recovery Plan

EAC		East African Cooperation

EAF 	Ecosystems Approach to Fisheries

EAF 	Ecological Approach to Fisheries

EAP 	Employee Assistance Programme

EC		European Countries

EE		Employment Equity

EFTA 	European Free Trade Association

EH&W 		Employee Health and Wellness

EPA 	Economic Partnership Agreement

EPDM	Employee Performance Development Management

EPWP	Expanded Public Works Programme

ERA 		Ecological Risk Assessment

ERP 		Enterprise Resource Planning

EU		European Union

FAnGR		Farm Animal Genetic Resources

FARM	Framework for Aquaculture Research Management

FAO	Food and Agriculture Organization

FET 		Further Education and Training

FMD 		Foot-and-Mouth Disease

FMP 		Fisheries Management Plan

FPE		Fish Processing Establishment

FS 		Food Security

FTE		Full-Time Equivalent

GADI 	Grootfontein Agricultural Development Institute

GDP 		Gross Domestic Product

GEP 		Gauteng Enterprise Propeller

GFI 		Gross Farm Sector Income

GHG 		Greenhouse Gases

GMO		Genetically Modified Organism

HE		Higher Education

HIV 		Human Immunodeficiency Virus

HoD 		Head of Department

HR 		Human Resources

HRD 	Human Resources Development

HRM		Human Resources Management

IBSA 		India, Brazil and South Africa

ICT 	Information and Communication Technology

IFSNP 	Integrated Food Security and Nutrition Programme

IFSS 	Integrated Fisheries Security Strategy

IGDP 	Integrated Growth and Development Plan

ILM		Industry Liaison Meeting

IPAP 		Industrial Policy Action Plan

IT 		Information Technology

ITC		International Trade Centre

ITCAFF 	Intergovernmental Technical Committee for Agriculture, Forestry and Fisheries

ITSC	International Trade and Security Cluster

KIM		Knowledge and Information Management

LR 		Labour Relations

LTRAMP 	Long-term Rights Allocation Management Process

Mafisa 	Micro-agricultural Financial Institutions of South Africa

MAP 	Marketing of Agricultural Products

MAST 		Marine Administration System

MCM	Marine and Coastal Management

MCS	Monitoring, Control and Surveillance

MDG 		Millennium Development Goals

M&E		Monitoring and Evaluation

MER	Monitoring, Evaluation and Reporting

MERCOSUR	Mercado Commún del Sur

MIS 		Marketing Information System

MLRA 		Marine Living Resources Act

MoA 		Memorandum of Agreement

MoU 		Memorandum of Understanding

MSP 		Master Systems Plan

MTEF 	Medium Term Expenditure Framework

MTSF 	Medium Term Strategic Framework

MWG 		Management Working Group

NAC	National Agro-meteorological Committee

NAFU		National African Farmers’ Union

NAMC		National Agricultural Marketing Council

NARMCO	National Agricultural Risk Management Committee

NAS 		National Aquaculture Strategy

NDTT 		National Disaster Task Team

NERPO	National Emergent Red Meat Producers’ Organisation

NFA 		National Forests Act

NFI 		Net Farm Sector Income

NGP 		New Growth Path

NPoA 		National Programme of Action

OD 		Organisational Development

OHS 		Occupational Health and Safety

PBR		Plant Breeders’ Rights

PDA 	Provincial Department of Agriculture

PDI 	Previously Disadvantaged Individual

PFMA 		Public Finance Management Act

PGRFA 	Plant Genetic Resources for Food and Agriculture

PMDS 	Performance Management and Development System

QPR		Quarterly Performance Report

R&D 		Research and Development

RSA 		Republic of South Africa

SACU		Southern African Customs Union

SADC	Southern African Development Community

SALA 	Subdivision of Agricultural Land Act

SAQA 	South African Qualifications Authority

SASSA 	South African Social Security Agency

SDIP 	Service Delivery Improvement Plan

SEDA 	Small Enterprise Development Agency

SETA 	Sector Education and Training Authority

SMME	Small, Medium and Micro Enterprises

SMS 		Senior Management Service

SOE		State-Owned Entities

SPS 		Sanitary and Phytosanitary

SRPP 	Social Responsibility Programmes and Projects

TAC		Total Allowable Catch

TAE		Total Allowable Estimate

dti 	Department of Trade and Industry

TIDCA 	Trade, Investment and Development Cooperation Agreement

ToR		Terms of Reference

UN 		United Nations

US 		United States

VE		Value Engineering

VMW 		Virtual Machine Ware

VOIP 		Voice Over Internet Protocol

WCRL 		West Coast Rock Lobster

WFFP 	Working for Fisheries Programme

WSCD 		White Shark Cage Diving

WSP 		Work Skills Programme

WTO		World Trade Organization

# OVERVIEW

This report focuses on the performance of departmental programmes for the third quarter of the 2012/13 financial year. The Department comprises of six programmes, which share a total of 253 annual planned deliverables shown in (Table 1) and 32 deliverables were targeted for Quarter 3. This report presents the performance of the Department for the last quarter before the compilation of the Annual Report. Therefore, the emphasis has been placed on the submission of admissible evidence. Deliverables are only recognised as in progress or completed if supported by authentic and admissible evidence.

The decision by the departmental management to have one monthly executive committee meeting focusing on strategic performance management is already paying dividends judging by the vast improvement in the quality of reporting and introduction of corrective measures in time in cases of bottlenecks. The departmental mid-term performance report has been submitted to the Auditor-General team for assessment before compilation of the Annual Report. A meeting is pending with the AG team to get guidance and advice on ways to better present the departmental state of performance in the Annual Report.

The pages that follow give the details of the performance status as reported by the programmes.

Table 1: 2012/13 DAFF Planned Deliverables

| Programmes | Planned | Planned | Planned | Planned | Planned |
| --- | --- | --- | --- | --- | --- |
|  | Annual | Q1 | Q2 | Q3 | Q4 |
| Administration | 57 (*58) | 9 | 8 | 7 | 33 |
| Agricultural Production, Health and Food Safety | 28 | 1 | 2 | 5 | 20 |
| Food Security and Agrarian Reform | 22 | 0 | 0 | 0 | 22 |
| Economic Development, Trade and Marketing | 43 | 4 | 4 | 6 | 29 |
| Forestry and Natural Resources Management | 40 | 1 | 2 | 1 | 36 |
| Fisheries Management | 61 | 9 | 11 | 13 | 28 |
| DAFF | 251 (*252) | 24 | 28 | 32 | 169 |

* Indicates an inclusion of a deliverable that was not assigned to any quarter due to the date being set by the National Treasury; see page 65 of the Strategic Plan 2012/13 – 2016/17.

# ADMINISTRATION

Purpose

Provide strategic leadership, management and support services to the Department. The aim of the programme is to lead, support and promote agricultural, forestry and fisheries resources management through policies, strategies and programmes to enhance sustainable use, and to achieve economic growth, job creation, food security, rural development and transformation.

Corporate Services: To render sound human resources management and development, security and information management.

Chief Financial Officer: To provide the Department with sound financial services.

Policy Planning, Monitoring and Evaluation: To direct the provision of policy analysis, formulation, planning and monitoring and evaluation in order to facilitate the improvement of the Department’s performance.

Stakeholder Relations, Communication and Legal Services: To provide the Department with legal and communication services and promote intergovernmental and stakeholder relations.

## PERFORMANCE AGAINST MEASURABLE OBJECTIVES

### Human Resources Management

| Sub-programme: Human Resources Management |
| --- |
| Strategic goal | Strategic objective | Indicator | Actual performance against target | Challenges | Corrective Measures |
|  |  |  | Target | Actual |  |  |
| SG 6: Effective and efficient governance | SO 3: Provide effective audit, investigative and legal, human resources and financial risk management | Improved compliance to performance management and development system | 80% adherence to performance management and development systems | Total of 80% first bi-annual assessments have been submitted. There are still Directorates which are not adhering to the Employee Performance Management and Development System policy timelines. | Non-adherence to the EPMDS policy timelines. | Enforce disciplinary measures. |
|  |  | Vacancy rate reduced | 11% | Filling of vacancies has decreased to 12,8% during Quarter 3. |  |  |
|  |  | Improved HRD | HRD Strategy implemented | The HRD Strategy was implemented through bursary awards to various field of study, ABET, various skills programmes and induction. |  |  |
| SG 6 : Effective and efficient governance | SO 3: Provide effective audit, investigative and legal, human resources and financial risk management | Improved Health and Wellness of personnel | Health and Wellness programmes implemented | The following campaigns and ceremonies were held during Quarter 3: Cancer awareness; Blood Donation; and Long Service Ceremony, etc. |  |  |

### Chief Information Office

| Sub-programme: Chief Information Office |
| --- |
| Strategic goal | Strategic objective | Indicator | Actual performance against target | Challenges | Corrective Measure |
|  |  |  | Target | Actual |  |  |
| SG 6: Effective and efficient governance | SO 5: Provide leadership and manage communication and information | MSP implemented | Approved MSP | First draft of MSP received end July 2012. 84% of DAFF directorates interviewed and information collected. SITA and DAFF ICT to workshop and augment MSP when all directorates have been interviewed. |  |  |
|  |  | Knowledge and Information Management Strategy implemented | KIM Strategy | Compilation and finalization of KIM Strategy is still ongoing. A feasibility study on the development of an on and off storage facility is currently being conducted. |  |  |

### Development Finance

| Sub-programme: Development Finance |
| --- |
| Strategic Goal | Strategic Objective | Indicator | Actual performance against target | Challenges | Corrective Measures |
|  |  |  | Target | Actual |  |  |
| SG 4: A transformed and united sector | SO 1: Increase equity, ownership and participation of previously disadvantaged individuals (PDIs) | Comprehensive funding facility implemented | Implement Insurance and savings programmes | 509 smallholder farmers participated in the savings programme. 433 smallholder farmers were covered with insurance. | Most clients appreciate the concept of a savings programme, but have little or nothing to save. Affordable insurance products, DAFF depends on the intermediaries and other stakeholders to offer insurance products. | Constant motivation Speed up the process of developing affordable products. |
|  |  | Improved access to financial support services | 5 000 smallholder producers supported through Mafisa. | 407 smallholders producers have been assisted with loans for Quarter 3, which brings the cumulative achievement to 3 473 against the planned 5 000. | The number of intermediaries has declined from 9 to 6. | Accredit additional institutions to increase the numbers. |
|  |  |  | 15 000 smallholder producers supported through CASP | 38 130 beneficiaries supported through CASP. A cumulative total of 63 088 beneficiaries supported for the financial year. |  |  |
| SG 4: A transformed and united sector | SO 1: Increase equity, ownership and participation of previously disadvantaged individuals (PDIs) | Improved access to financial support services | 30 000 subsistence producers (Ilima) | 43 464 beneficiaries supported through Ilima. A cumulative total of 59 641 beneficiaries supported for the financial year. |  |  |

### Financial Management

| Sub-programme: Financial Management |
| --- |
| Strategic Goal | Strategic Objective | Indicator | Actual performance against target | Challenges | Corrective Measures |
|  |  |  | Target | Actual |  |  |
| SG 6: Effective and efficient governance | SO 4: Improve departmental service excellence through implementation of quality standards, Batho Pele principles and general legislative mandate | Compliance to legislation, prescripts, procedures and guidelines | Unqualified audit report on financial statements. | Unqualified audit report for 2011/2012 was achieved. Audit Matrix was developed to address the 2011/12 audit findings and was submitted to National Treasury on 28 September 2012. |  |  |

### Monitoring and Evaluation

| Sub-programme: Monitoring and Evaluation |
| --- |
| Strategic Goal | Strategic Objective | Indicator | Actual performance against target | Challenges | Corrective Measure |
|  |  |  | Target | Actual |  |  |
| SG 6: Effective and efficient governance | SO 2: Strengthen policy, planning, monitoring, evaluation, reporting and sector information | Implemented monitoring, evaluation and reporting guidelines | Reviewed DAFF monitoring, evaluation and reporting guidelines | Guidelines have been drafted for ratification by MINTECH. MER guidelines for DAFF were approved in 2012. |  |  |
|  |  | Analysed economic trends for the sector | Quarterly reports on economic indicators and trends for the sector compiled | Comprehensive economic reports available for commercial agriculture, but not for smallholder and subsistence producers as well as forestry and fisheries sub-sectors. |  |  |
|  |  | Comprehensive statistical database for the sector | Updated statistical information and reports compiled | Fairly comprehensive statistics on commercial agriculture, but lack of reliable statistics on smallholder and subsistence producers as well as forestry and fisheries sub-sectors. |  |  |

### Policy Development and Planning

| Sub-programme: Policy Development and Planning |
| --- |
| Strategic goal | Strategic objective | Indicator | Actual performance against target | Challenges | Corrective Measures |
|  |  |  | Target | Actual |  |  |
| SG 6: Effective and efficient governance | SO 2: Strengthen policy, planning, monitoring, evaluation, reporting and sector information | DAFF’s strategic objectives aligned to MTSF | Approved Strategic Plan | In preparation for the approval of the Strategic Plan 2013/14-16/17, the following processes were undertaken: The planning QRM took place in November 2012. High level priorities were identified in response to the MTSF. Strategic planning was facilitated with all the Branches to ensure DAFF’s strategic objectives align with the MTSF. The second draft Strategic Plan was submitted to Treasury on 30 November 2012, as required. DAFF continues to interact with PDAs by participating in provincial planning and performance review sessions to ensure alignment to the MTSF and the Presidential Outcomes. |  |  |
|  |  | Improved programme and project management system | Approved programme planning and development system | The methodology to improve programme planning and development systems has been developed, finalised and is ready to be submitted for approval. | As a result of the changes, focus was on the formulation of methodology for programme planning and assessment, which has been developed. |  |
|  |  | Policy formulation and development framework implemented | Policy framework developed | The new framework for policy formulation and development has been developed and is undergoing departmental approval processes. The policy framework is an instrument to be utilized to review existing policies. |  |  |
|  |  | Targeted R&D programme developed | Targeted R&D programme developed | ARC has developed the targeted research programmes and projects as commissioned by DAFF. The preliminary reports of the research programmes are expected in February 2013. A consortium of Universities signed the MOUs in Q2 to implement a number of R&D projects in targeted areas to support smallholder producers. |  |  |

### Stakeholder Relations/Fisheries Partnership Management

| Sub-programme: Stakeholder Relations/Fisheries Partnership Management |
| --- |
| Strategic Goal | Strategic Objective | Indicator | Actual performance against target | Challenges | Corrective Measures |
|  |  |  | Target | Actual |  |  |
| SG 6: Effective and efficient governance | SO 1: Establish and strengthen cooperative governance and functional relations with local and international stakeholders | Enhanced stakeholder participation with national departments and other two spheres of government and relevant stakeholders | Ensure the development of an Intergovernmental Strategy | A draft Intergovernmental Strategy has been developed. Currently, the process of consultation with the three departmental functions i.e. agriculture, forestry and fisheries together with the technical directorates within DAFF, is taking place. |  |  |
| SG 6: Effective and efficient governance | SO 4: Improve departmental service excellence through implementation of quality standards, Batho Pele principles and general legislative mandate | Oversee the implementation of the deployment framework to commodity groups and municipalities | Efficient stakeholder service delivery | The Stakeholder Engagement Strategy has been finalised and is currently undergoing departmental approval processes. Meetings were held with the following commodity groups: Wildlife Ranching SA; Red Meat Industry Forum; Milk Producers’ Organisation; Pork Producers Organisation; and National Wool Growers Association. |  |  |
| SG 6: Effective and efficient governance | SO 5: Provide leadership and manage communication and information | Aligned DAFF Communication Strategy | Refine and oversee the implementation of the DAFF Communication Strategy | The DAFF Communication Strategy was approved and submitted to GCIS, and is being implemented. |  |  |

# AGRICULTURAL PRODUCTION, HEALTH AND FOOD SAFETY

Purpose

Manage the risks associated with animal diseases, plant pests, genetically modified organisms (GMOs) and registration of products used in agriculture; promote food safety and create an enabling environment for increased and sustainable agricultural production.

The programme comprises three sub-programmes, namely Plant Production and Health; Animal Production and Health; and Inspection and Laboratory Services.

Plant Production and Health: Focuses on increasing agricultural productivity with the emphasis on a sustainable plant production system, efficient use of genetic resources and manages risks associated with plant pests, diseases and GMOs.

Animal Production and Health: Aims to improve livestock production through the implementation of animal production and health strategies, projects and programmes founded on sound animal disease risk management principles, an informed extension service and sustainable natural resources management.

Inspection and Laboratory Services: Focuses on the provision of leadership, guidance and support in ensuring compliance with agricultural legislation and regulatory frameworks and overseeing the effective implementation of risk management strategies and plans for regulated agricultural products.

## PERFORMANCE AGAINST MEASURABLE OBJECTIVES

### Animal Production and Health

| Sub-programme: Animal Production and Health |
| --- |
| Strategic Goal | Strategic Objective | Indicator | Actual performance against target | Challenges | Corrective measures |
|  |  |  | Target | Actual |  |  |
| SG 1: Increase profitable production of food, fibre and timber products by all categories of producers | SO 1: Promote efficient production, handling and processing of food, fibre and timber | Number of new producers participating in animal production schemes (cumulative) | 1 300 new producers | 865 new producers participated in animal production schemes. | Availability of financial resources is a challenge. | Submission of budgetary requests. |
|  |  | Number of beneficiaries benefiting from commodity strategies | 200 beneficiaries benefiting from pig commodity strategy | 113 pig farmers benefited from the pig commodity strategy. |  |  |
|  |  | Regulatory frameworks approved by Parliament | Approve Compulsory Community Service Framework (CCS) | The Veterinary and Para-Veterinary Professions Amendment Bill was signed by the State President during Quarter 3 and preparations and finalisation of the regulations, which will form part of the CCS framework, has commenced. |  |  |
|  |  | Number of primary animal health care awareness campaigns | 4 | 3 awareness campaigns were conducted: Rabies; Meat safety awareness; and Animal Identification. | The implementation is dependent on the availability of officials to do compulsory community service who still could not be appointed due to the as yet unapproved legal framework. | Finalisation of the operations and agreement on the approach to final structural changes needed by the provinces with the financial officers. |
| SG 3: Effective national and regulatory and risk management system | SO 2: Establish and maintain effective early-warning and mitigation systems | Number of reports on early detections and reaction time to outbreaks of animal diseases and pests | 6 | 9 reports on early detections and reaction time to outbreaks of animal diseases were submitted to the OIE. |  |  |

### Plant Production and Health

| Sub-programme: Plant Production and Health |
| --- |
| Strategic Goal | Strategic Objective | Indicator | Actual performance against target | Challenges | Reason for variance |
|  |  |  | Target | Actual |  |  |
| SG 1: Increase profitable production of food, fibre and timber products by all categories of producers | SO 1: Promote efficient production, handling and processing of food, fibre and timber | Number of plant-related commodity strategies implemented | Vegetable commodity strategy implemented | The strategy is undergoing approval processes. During Q3 about 350 vegetable farmers were supported. |  |  |
|  |  | Sanitary and Phyto Sanitary (SPS) Strategy developed | 2 Plant Health (Phytosanitary) Policy and Plant Protection Bill | The Draft Plant Health (Phytosanitary) Policy has been approved by the Minister and the Plant Protection Bill has been published in government gazette No. 35823, for public comments. |  |  |
| SG 2: Sustained management of natural resources | SO 2: Ensure protection of indigenous genetic resources | Genetic resources for food and agriculture monitored | Plants and animal genetic resources | The monitoring report for plant genetic resource was completed. The compilation of the animal genetic resource report is in progress. |  |  |
| SG 3: Effective national and regulatory and risk management systems | SO 2: Establish and maintain effective early-warning and mitigation systems | Surveillance of plant diseases and pests conducted | Bactrocera invadens surveillance and quarantine plant, pests and diseases | A Bactrocera invadens surveillance was conducted. |  |  |

### Inspection and Laboratory Services

| Sub-programme: Inspection and Laboratory Services |
| --- |
| Strategic Goal | Strategic Objective | Indicator | Actual performance against target | Reason for variance | Corrective measures |
|  |  |  | Target | Actual |  |  |
| SG 3: Effective national and regulatory and risk management systems | SO 1: Manage the level of risks associated with food, diseases, pests, natural disasters and trade | Number of reports on regulatory compliance and monitoring interventions | 4 | 3 regulatory compliance and monitoring intervention reports were compiled. |  |  |
|  |  | Number of reports on regulatory framework instruments approved | 1 Liquor Products Bill | Public comments were received and are being considered for inclusion in the draft Liquor Products Amendment Bill. |  |  |
| SG 1: Increase profitable production of food, fibre and timber products by all categories of producers | SO 1: Promote efficient production, handling and processing of food, fibre and timber | SPS Strategy developed | SPS enhanced | Drafting of SPS Strategy is work in progress. |  |  |

# FOOD SECURITY AND AGRARIAN REFORM

Purpose

The programme facilitates and promotes food security and agrarian reform programmes and initiatives. It comprises three sub-programmes, namely food security; sector capacity development; and national extension support services.

Food Security: Provides national frameworks to promote sustainable household food security programmes through improving the production systems of subsistence and smallholder producers in the agriculture, forestry and fisheries sector to achieve food security livelihoods and facilitate the provision of inputs, implements and infrastructure support.

Sector Capacity: Facilitates the provision of agriculture, forestry and fisheries education and training in support of sustainable growth and equitable participation in the sector. This will be achieved by facilitating and supporting education and training skills, promoting the development of centres of excellence on skills training and develop, manage and coordinate the sector transformation policy and strategy in line with the government objectives for the Department.

National Extension Support Services: Provides national extension policies, norms and standards on research and technology development. Provides strategic leadership and guidance for the planning, coordination and implementation of extension and advisory services in the sector. It also provides leadership and strategic support in the implementation of norms and standards for extension.

## PERFORMANCE AGAINST MEASURABLE OBJECTIVES

### Food Security

| Sub-programme: Food Security |
| --- |
| Strategic Goal | Strategic Objective | Indicator | Actual performance against target | Challenges | Corrective measures |
|  |  |  | Target | Actual |  |  |
| SG 1: Increased profitable production of food, fibre and timber products by all categories of producers | SO 2: Coordinate government food security initiatives | Green Paper gazetted | Gazette Green Paper on Food Security | Draft food security policy document is available. The IMC is meeting on 5 March 2013, and the draft food security policy will be discussed before tabling in Parliament for approval. | There have been delays with the meeting of the IMC on food security. |  |
|  |  | Zero Hunger Campaign implemented | Develop business case and co-ordinate implementation of Zero Hunger Campaign | Principles of Zero Hunger Campaign are being implemented in a government project called Public Private Partnership (PPP) for Food Security, Nutrition and Health. | Contextual interpretation and understanding of the Zero Hunger Campaign as a slogan emulating the State's intention to attain food security. | Implementation of Zero Hunger through Public Private Partnerships. |
|  |  | Number of smallholder producers supported through smallholder strategy | 15 000 | A total of 21 000 were identified by DAFF in the last financial year. 15 000 were targeted to be supported this financial year. A total of 682 smallholder producers were supported through CASP and the llima/Letsema interventions 99 from the Northern Cape and 583 from the Western Cape were supported. | The timing of identification in relation to submission of funding proposals by provinces | Engage aggressively with PDAs before the process of compiling business begins. |
| SG 1: Increased profitable production of food, fibre and timber products by all categories | SO 2: Coordinate government food security initiatives | Mechanisation policy implemented | Develop comprehensive mechanisation policy and implement tractor scheme | Mechanization policy for household food production support was developed and distributed for comments within DAFF. Tractor scheme rollout: 504 tractors delivered and 2 436 (100%) of implements delivered. All deliveries verified and checked against specifications. All the equipment has been delivered to sites indicated by provinces. In Eastern Cape, Free State, Limpopo and North West all the tractors and trailers are registered and operational. In Gauteng all tractors and trailers are registered and some have been distributed to projects, while others are still not distributed. In the Northern Cape not all tractors and trailers are registered yet. | Reliable information due to lack of mechanization statistics. Production not linked to mechanization statistics. In the Western Cape tractors are not registered. The e-Natis system requires a micro dot to be etched onto tractors and trailers before it can be registered. | Improve mechanization statistics. The Department to assist provinces where possible with logistics. |

### Sector Capacity Development

| Sub-programme: Sector Capacity Development |
| --- |
| Strategic Goal | Strategic Objective | Indicator | Actual performance against target | Challenges | Corrective measures |
|  |  |  | Target | Actual |  |  |
| SG 4: A transformed and united sector | SO 3: Improve social working conditions in the sector | Approved sector audit report by Social and Protection Cluster | Audit sector processes and deliverables | The Vulnerable Workers Delivery Forum did not meet because of the farm workers wages protest in Western Cape. |  |  |
|  |  | Provincial vulnerable delivery units established | 5 provinces (FS, WC, LP, MP, KZN) | Free State, Western Cape , Kwa- Zulu Natal, and Mpumalanga have confirmed the existence of delivery units. | Budgetary constraints hampered some provinces in establishing provincial delivery units. |  |
| SG 4: A transformed and united sector | SO 4: Provide leadership and support to research, training and extension in the sector | Producers completing training programmes | Coordinate training programmes for 15 000 smallholder producers | 8 637 beneficiaries were trained for the quarter under review. A cumulative total of 15 899 for the year has been achieved. |  |  |
|  |  | Approved Agricultural Training Institutions (ATIs) Green Paper | 7 agricultural colleges transformed into ATIs | Colleges of agriculture received accreditation from the Council of Higher Education to offer 3 year diploma programmes namely; Cedara, Glen, Fort Cox, Elsenberg, Gadi and Lowveld. The 3 year diploma is one of the elements for transforming colleges into ATIs. |  |  |

### National Support Services

| Sub-programme: National Support Services |
| --- |
| Strategic Goal | Strategic Objective | Indicator | Actual performance against target | Challenges | Corrective measures |
|  |  |  | Target | Actual |  |  |
| SG 4: A transformed and united sector | SO 4: Provide leadership and support to research, training and extension in the sector | Coordinate the provision of comprehensive training and extension support | Evaluate Extension Recovery Plan | The Extension Recovery Plan was evaluated and the report is undergoing departmental approval processes. |  |  |
|  |  | Develop national extension policy | Develop national extension policy | The draft national extension policy has been compiled and circulated for comments. |  |  |

# ECONOMIC DEVELOPMENT, TRADE AND MARKETING

Purpose

Ensure value chain integration; facilitation of market access for agriculture, forestry and fisheries products in support of economic growth, job creation and development.

The programme comprises the following three sub-programmes, namely International Relations and Trade; Agro- processing and Marketing; and Cooperatives and Rural Enterprise Development.

International Relations and Trade: Facilitates, coordinates and supports international relations and international trade for the agriculture, forestry and fisheries sectors through the development and implementation of appropriate policies and programmes.

Cooperatives and Rural Enterprise Development: Facilitates and supports the implementation of programmes and initiatives to ensure the promotion and participation of the agriculture, forestry and fisheries sectors in the economic development of businesses.

Agro-processing and marketing: Ensures the conversion/transformation of primary agriculture, forestry and fisheries commodities into value-added products and ensures domestic and international market access.

## PERFORMANCE AGAINST MEASURABLE OBJECTIVES

### Agro-Processing and Marketing

| Sub-programme: Agro-processing and Marketing |
| --- |
| Strategic Goal | Strategic Objective | Indicator | Actual performance against target | Challenges | Corrective Measures |
|  |  |  | Target | Actual |  |  |
| SG 5: Increased contribution of the sector to economic growth | SO 1: Increase growth, income and sustainable job opportunities in the value chain | Value chain networks established and institutionalized | Fisheries value chain network established | The fisheries value chain network was established. |  |  |
|  |  | Sector strategies developed and implemented | Facilitate the implementation of Marketing Strategy | Certain pillars of the marketing strategy such as provision of marketing information, training of farmers, and establishment of value chains, are being implemented. |  |  |
|  |  |  | Contribute to the implementation of intergovernmental agro-processing programmes | Discussions with the dti is on-going. | Role clarity between DAFF and the dti needs to be finalised. |  |

### Cooperatives and Rural Enterprise Development

| Sub-programme: Cooperatives and Rural Enterprise Development |
| --- |
| Strategic Goal | Strategic Objective | Indicator | Actual performance against target | Challenges | Corrective Measures |
|  |  |  | Target | Actual |  |  |
| SG 1: Increased profitable production of food, fibre and timber products by all categories of producers | SO 2: Coordinate government food security initiative | Increased number of smallholder producers institutionalised | Percentage of smallholder producers organized into commodity associations | 1 (one) poultry commodity group was established in Limpopo consisting of 13 farmers. |  |  |
|  |  |  | 108 cooperatives established | 36 cooperatives have been established and registered during Q3. This brings the cumulative figure to 96 cooperatives involving 853 farmers. |  |  |
| SG 5: Increased contribution of the sector to economic growth | SO 1: Increase growth, income and sustainable job opportunities in the value chain | Sector Charters implemented | Implementation of Agriculture and Forestry Charters monitored | Forestry Charter (undertakings): 1.) Afforestation Scoping reports for the Environmental Impact Assessments Studies in the Eastern Cape submitted to the authorizing institution: DEA. 2.) Draft report on forestry transport infrastructure requirements produced. 3.) TORs developed for re-advertising of the tender to develop guidelines and training for four subsectors: growers, saw millers, honey production and pole production. 4.) Second draft of the State Forest Plantation Growth Strategy developed and circulated for final comments. 5.) Transfer Agreement for MMM plantation. Tender for the development of the business plan re-advertised. Transfer agreement in place and awaiting approval. 6.) Decommissioning of Lowveld plantations. Presentation of the Cab Memo to the Economic Cluster took place on 28 October 2012. The AgriBEE Sector Codes in terms of Section 9 (1) of the BBBEE Act 53 of 2003, was approved by the Minister of Trade and Industry and was published in the Government Gazette. | Improved target. |  |
|  |  | Sector strategies developed and implemented | Integrated SMME Strategy developed | Literature review on Integrated SMME Strategy is being conducted. |  |  |

### International Relations and Trade

| Sub-programme: International Relations and Trade |
| --- |
| Strategic Goal | Strategic Objective | Indicator | Actual performance against target | Challenges | Corrective Measure |
|  |  |  | Target | Actual |  |  |
| SG 5: Increased contribution of the sector to economic growth | SO 1: Increase growth, income and sustainable job opportunities in the value chain | Improved international relations and trade | Trade and international relations strategies implemented | The trade strategy is undergoing approval processes. |  |  |
| SG 5: Increased contribution of the sector to economic growth | SO 3: Increase domestic and international market access for South African and African agricultural, forestry and fisheries products | Increased intra-African trade | Participate in tripartite Free Trade Agreement (FTA)negotiations | Participated in Common Markets for Eastern and Southern Africa (COMESA)-Eastern African Cooperation (EAC)- South African Development Community (SADC) Tripartite and FTA negotiations on market access and trade related matters. |  |  |
| SG 6: Effective and efficient governance | SO 1: Establish and strengthen cooperative governance and functional relations with local and international stakeholders | New cooperation agreements signed | Negotiate and sign new agreements | Bilateral engagements with countries that South Africa does not have agreements with: Mauritius, Senegal, Egypt and Ethiopia. There is agreement with Ethiopia and will now start with approval process. |  |  |
|  |  | DAFF participation in multilateral forums strengthened | 100% participation in strategic multilateral forums | Participated in various regional and international forums G20, Food and Agriculture Organisation (FAO), Organisation for Economic Cooperation and Development (OECD), Office of International Epizootics (OIE), International Organisation of Vine and Wine (OIV), Internationa Fund for Agricultural Development (IFAD), European Union, etc. |  |  |

# FORESTRY AND NATURAL RESOURCES MANAGEMENT

Purpose

Develop and facilitate the implementation of policies and targeted programmes to ensure management of forests, sustainable use and protection of land and water as well as managing agricultural risks and disasters.

There are three sub-programmes in the Forestry Programme, namely Forestry Operations; Forestry Development and Regulations; and Natural Resources Management.

Forestry Operations: To ensure sustainable management of forestry operations through managing state forests and woodlands, other state assets in the region and to render coordination and operational support.

Forestry Development and Regulations: Ensures effective development of policies for forestry regulation and oversight by promoting the optimum development of arboriculture, commercial and urban forestry and the development of small-scale forestry.

Natural Resources Management: Will facilitate the development of infrastructure and the sustainable use of natural resources through an enabling framework for the sustainable management of woodlands and indigenous forests, the efficient development and revitalisation of irrigation schemes and water use. The sub-programme will facilitate climate change mitigation and adaptation, risk and disaster management as well as promote, regulate and coordinate the sustainable use of natural resources (land and soil).

## PERFORMANCE AGAINST MEASURABLE OBJECTIVES

### Forestry Development and Regulations

| Sub-programme: Forestry Development and Regulations |
| --- |
| Strategic Goal | Strategic Objective | Indicator | Actual performance against target | Challenges | Corrective Measures |
|  |  |  | Target | Actual |  |  |
| SG 2: Sustained management of natural resources | SO 1: Ensure the sustainable management and efficient use of natural resources | Forestry adaptation plans developed and implemented | Develop forestry adaptation plans | Forestry adaptation plan is work in progress and will contribute to the broader departmental climate change adaptation and mitigation plans. |  |  |
| SG 5: Increased contribution of the sector to economic growth and development | SO 2: Increase the level of public and private investment for agricultural, forestry and fisheries products | Forestry protocols and strategies implemented | Implement Charter undertakings (Environmental Impact Assessment conducted in the Eastern Cape; Sawlog strategy approved; and Rossbach Business Plan developed. | Environmental Impact Assessment finalized and reports for all sites submitted to Eastern Cape Provincial Department of Environmental Affairs and Tourism. The Sawlog strategy has been approved. The business plan for the DAFF Rossbach plantation in Limpopo has been developed, for the purpose of transferring the plantation to the communities. |  |  |

### Forestry Operations

| Sub-programme: Forestry Operations |
| --- |
| Strategic Goal | Strategic Objective | Indicator | Actual performance against target | Challenges | Corrective Measures |
|  |  |  | Target | Actual |  |  |
| SG 1: Increased profitable production of food, fibre and timber products by all categories of producers | SO 2: Coordinate government food security | Number of small producers supported with training and linked to potential funders | 1 000 | 556 small forestry producers supported with training and linked to funders. |  |  |
| SG 2: Sustained management of natural resources | SO 1: Ensure the sustainable management and efficient use of natural resources | Number of ha planted/afforested | Facilitate afforestation of 10 000 ha | Facilitation of afforestation of 200 ha has been done. | Budget constraints are hampering the achievement of this target. |  |
| SG 5: Increased contribution of the sector to economic growth and development | SO 2: Increase the level of public and private investment for agricultural, forestry and fisheries products | Number of jobs created (refurbishment of Category B&C plantations) | 2 300 jobs | 514 temporary jobs have been created. |  |  |

### Natural Resources Management

| Sub-programme: Natural Resources Management |
| --- |
| Strategic Goal | Strategic Objective | Indicator | Actual performance against target | Challenges | Corrective Measures |
|  |  |  | Target | Actual |  |  |
| SG 1: Increased profitable production of food, fibre and timber products by all categories of producers | SO 2: Coordinate government food security | Number of LandCare jobs created (105 000 opportunities = 454 Full Time Equivalents) | 130 Full Time Equivalents (FTEs) | 15 FTEs were created at the end of Quarter 3. |  |  |
|  |  | Number of state land jobs created (300 job opportunities) | 60 job opportunities | 53 temporary jobs were created on state land at the end of Quarter 3. |  |  |
| SG 2: Sustained management of natural resources | SO 1: Ensure the sustainable management and efficient use of natural resources | 1 250 ha of irrigation schemes revitalized | Revitalized 250 ha of smallholder government irrigation schemes | 93 ha of the 125 ha at Makhatinie irrigation scheme have been revitalized by the end of Quarter 3. The intervention is funded through Ilima /Letsema. | No revitalizing has taken place on the targeted 125 ha at Taung, as a result of the reprioritization of funds by North West PDA. |  |
|  |  | Number of ha (agricultural land, woodlands and indigenous forests) rehabilitated | 10 000 ha | A cumulative total of 88 552 ha already rehabilitated through LandCare, CARA and Working for Water. | Hectares provided include provincial equitable share funds as well as the incentive grant from EPWP, which increased the number of hectares rehabilitated. The initial allocation was focused only on the national LandCare grant. |  |
|  |  | Climate change adaptation and mitigation plans implemented | Climate change adaptation and mitigation plans approved | The draft plan has been finalised and is ready to go through the departmental approval processes. |  |  |
| SG 5: Increased contribution of the sector to economic growth and development | SO 2: Increase the level of public and private investment for agricultural, forestry and fisheries products | Disaster risk management system improved | Disaster risk mitigation strategies implemented | Repairing of agricultural infrastructure through the implementation of the Flood Assistance Scheme in North West, Eastern Cape, Northern Cape, Free State, Gauteng Province and Limpopo is ongoing. |  |  |

# FISHERIES MANAGEMENT

Purpose

Promote the development, management, monitoring and sustainable uses of marine living resources and the development of South Africa’s fisheries sectors. Sustainable livelihoods will be achieved through aquaculture growth and fisheries economic development.

The programme comprises four sub-programmes, namely Aquaculture and Economic Development; Fisheries Research and Development; Marine Resource Management; and Monitoring, Control and Surveillance.

Aquaculture and Economic Development: Will ensure aquaculture growth and fisheries economic development for sustainable livelihoods by providing public support and an integrated platform for management of aquaculture.

Fisheries Research and Development: To ensure the promotion of the sustainable development of fisheries resources and ecosystems by conducting and supporting appropriate research.

Marine Resource Management: Ensures the sustainable utilisation and equitable and orderly access to the marine living resources through improved management and regulation.

Monitoring, Control and Surveillance: Ensure the protection and promotion of sustainable use of marine living resources by intensifying enforcement and compliance.

## PERFORMANCE AGAINST MEASURABLE OBJECTIVES

### Aquaculture and Economic Development

| Sub-programme: Aquaculture and Economic Development |
| --- |
| Strategic Goal | Strategic Objective | Indicator | Actual Performance against Target | Challenges | Corrective Measures |
|  |  |  | Target | Actual |  |  |
| SG 1: Increased profitable production of food, fiber and timber products by all categories of producers (subsistence, smallholder and commercial) | SO 2: To coordinate government food security initiatives. | Number of fish farms revitalized | 5 fish farms | Progress has been made in facilitating the revitalization of 5 farms: Disaneng Aquaculture Farm (North West) Hamburg Aquaculture Project (Eastern Cape), The construction of 3 fish farms in Xhariep, namely: Gotswamentsing project in Koffiefontein, Springfontein and Lephoi project in Bethulie. |  |  |
|  |  | Number of EPWP jobs created | 1 000 Working for Fisheries Programme jobs | A total of 1 062 jobs have been created through implementation of catch data monitors (3 projects), harbour maintenance (3 projects), anti-poaching (1 project), Northern Cape fishing facilities (2 projects) and MCS Observers projects under the Working for Fisheries programme (WFFP). |  |  |
| SG 5: Increased contribution of the sector to economic growth and development | SO1: Increase growth, income and sustainable job opportunities in the value chain | Number of fishing harbours revitalized | 2 fishing harbours | The Koolbaai and Gansbaai harbours are being repaired and maintained for revitalization processes. |  |  |
|  | SO 2: Increase the level of public and private investment for agricultural, forestry and fisheries products | Improved aquaculture management and compliance | Implement environmental Integrity Framework for Marine Aquaculture | Development of the Environmental Integrity Framework for Marine Aquaculture has been completed. |  |  |
| SG 1: Increased profitable production of food, fibre and timber products by all categories of producers (subsistence, smallholder and commercial) | SO 2: To coordinate government food security initiatives. | Number of Aquaculture Development Zones (ADZ) revitalized | 1 Aquaculture Development Zone | Existing abalone hub in Hermanus identified as potential ADZ and processes initiated in collaboration with the Western Cape province. |  |  |
|  |  | Number of hatcheries revitalized | 1 hatchery | Due to the delays and challenges experienced in acquiring land from Department of Public Works, a decision was taken by the Fisheries Branch that the Cape Agulhas Municipality be appointed to run this project as they have made land available for the establishment of the hatchery. | The previous bid will be cancelled. | A letter has been sent to the Chairperson of the Bid Adjudication Committee requesting cancellation of the bid to allow appointment of the Cape Agulhas Municipality to implement the project. |

### Fisheries Research and Development

| Sub-programme: Fisheries Research and Development |
| --- |
| Strategic Goal | Strategic Objective | Indicator | Actual Performance against Target | Challenges | Corrective Measures |
|  |  |  | Target | Actual |  |  |
| SG 2: Sustained management of natural resources | SO 1: Ensure the Sustainable management and efficient use of natural resources | Number of new fishery sectors established | Conduct feasibility study on two new fisheries | Data is continued to be collected and monitored for the following fisheries: Livebait (tuna fishery) and KZN Redeye (net fishery). Livebait (shark fishery): The New Fisheries Scientific Working Group did not approve the use of small pelagic species. | New fisheries require more than just scientific support – they also require dedicated economic, business development and administrative support. Without such support it is exceptionally difficult for new fisheries to develop. |  |
|  |  | Aquaculture research and capacity development programme implemented | Finalised MoUs with two universities | The University of the Free State MoU was signed by both parties, DAFF and UFS during Quarter 3. MoU for the University of Limpopo was signed in Q2. This is for the implementation of aquaculture research and capacity development programme. |  |  |

### Marine Resources Management

| Sub-programme: Marine Resources Management |
| --- |
| Strategic Goal | Strategic Objective | Indicator | Actual Performance against Target | Challenges | Corrective measures |
|  |  |  | Target | Actual |  |  |
| SG 1: Increased profitable production of food, fibre and timber products by all categories of producers (subsistence, smallholder and commercial) | SO 2: To coordinate government food security initiatives. | Widening source for food security | Utilization of anchovy for human consumption | A workshop to finalize the analysis and review of various processing methods, infrastructure and markets to determine the feasibility of marketing anchovy as a cheap source of protein for human consumption is planned for 6-7 March 2013. | Delays in securing participation of the Peruvian experts. |  |
| SG 2: Sustained management of natural resources | SO 1: To ensure the sustainable management and efficient use of natural resources. | Increased biomass of fish resources | Implementation of recovery strategies | The Total Allowable Catch for then fishing season was approved. Abalone TAC submission for the 2012/13 fishing season was approved at 150 tons, which is the same as for 2011/12. This translates to 455 Rights Holders and 3 182 crew for Linefish and 2 426 tons for West Coast Rock Lobster. In the Hake sector, the TAC for 2012/13 was set at 145 tons. The approved global season was spilt accordingly. |  |  |
|  |  | Improved access to fishery resources | Allocation of fishing rights in eight sectors | The bid for the allocation of fishing rights in the eight sectors to be split into two (the one for the policy review process and the other one for the rights allocation process) and to be re-advertised due to lack of suitable service providers. |  |  |
|  |  |  | Allocation of rights in fish processing establishments | Fish processing establishment guidelines will further be circulated to ensure ample consultation as there has been delays with stakeholder consultation. |  |  |

### Monitoring, Control and Surveillance

| Sub-programme: Monitoring, Control and Surveillance |
| --- |
| Strategic Goal | Strategic Objective | Indicator | Actual Performance against Target | Reason for Variance |
|  |  |  | Target | Actual |  |
| SG 1: Increased profitable production of food, fibre and timber products by all categories of producers (subsistence, smallholder and commercial) | SO 2: To coordinate government food security initiatives | Improved compliance and protection of marine living resources | Inspections on 1 400 vessels | A total of 266 (126 landings and 140 sea) vessels were inspected, both at sea and landing sides, during Quarter 3. This brings to a total of 1 797 inspections of vessels in 5 key fisheries for the first three quarters. |  |
|  |  |  | Review of permits and rights holders compliance | A total of 237 permit and rights holders were reviewed for compliance with policies to date. Only 72 were reviewed for quarter 3 (included in the cumulative figure) |  |

# CONCLUSION

- Strengthen interdepartmental cooperation and collaboration for the development of production infrastructure (SIP 11) and other supporting policies and programmes.

- Facilitate implementation of Food Security Production Intervention targeting an additional one million hectares for production.

- Improved cooperation with the provinces and local government to enhance governance in the sector.

- Accelerate collaboration with stakeholders through existing forums.